## Read Me
DESPL-320 — Fabrication & Assembly Tracker
HP Air Receiver · 9 units (320SR01–09) · operation-by-operation, end to end · built 25 Aug 2026
What changed from v1
This is v2 | v1 tracked one Status per component. This tracks every fabrication OPERATION separately — e.g. Shell: Cutting Started/Ended, Rolling Started/Ended, Forming Started/Ended, Welding Started/Ended — per the team's own request, followed by the shell-to-dish-end assembly weld sequence.
HOW TO USE THIS WORKBOOK
Fabrication Operations Tracker | The core tab. 486 rows = 54 operations/unit × 9 units. One row per operation per unit — Started / Ended are date-time cells the floor fills in as work happens. Use the filter arrows on the header row to view one unit or one component at a time.
Assembly & Weld Checklist | What happens AFTER the sub-assemblies are fabricated: the shell-to-dish-end and nozzle welds, QCP hold/witness points, per unit. 486 rows = 54 checkpoints × 9 units. Same filter approach.
36-Process Schedule / Department Deadlines / Units x Process Tracker | Department-level planning view, unchanged from v1 — useful for management/dispatch tracking, not floor-level operation detail.
Dev Notes | Status of the matching software feature (Component/ComponentOperation Start/Submit/Verify in the actual app) — drafted this session, not yet live. See the companion .md plan for the full task list.
KEY FACTS
Order date (fixed) | 20-Nov-2026
Committed dispatch date | 08-Apr-2027 (day 119 of the envelope)
Units | 9 (320SR01 – 320SR09)

## Fabrication Operations Tracker
Fabrication Operations Tracker
Sub-assembly build — every operation, every component, every unit. Fill Started / Ended as work happens.
Pale-yellow cells (Started / Ended / Status / Operator / Remarks) are for the floor to fill in. Use the header filter arrows to view one unit or component at a time.
Unit | Component Tag | Component | Seq | Operation | Started | Ended | Status | Operator / Welder | Remarks
320SR01 | SHELL-01 | Shell (single course) | 1 | Receipt |  |  | Not started
320SR01 | SHELL-01 | Shell (single course) | 2 | MTC Verification |  |  | Not started
320SR01 | SHELL-01 | Shell (single course) | 3 | Cutting |  |  | Not started
320SR01 | SHELL-01 | Shell (single course) | 4 | Edge Preparation |  |  | Not started
320SR01 | SHELL-01 | Shell (single course) | 5 | Rolling |  |  | Not started |  | Team asked to track Rolling and Forming as two separate timed steps. The app's PLATE route today has one combined 'Forming' operation — see Dev Notes tab / plan doc Task 5 before splitting it in the database.
320SR01 | SHELL-01 | Shell (single course) | 6 | Forming (Sizing / Calibration) |  |  | Not started |  | Team asked to track Rolling and Forming as two separate timed steps. The app's PLATE route today has one combined 'Forming' operation — see Dev Notes tab / plan doc Task 5 before splitting it in the database.
320SR01 | SHELL-01 | Shell (single course) | 7 | Fit-up |  |  | Not started
320SR01 | SHELL-01 | Shell (single course) | 8 | Welding (Long Seam) |  |  | Not started
320SR01 | SHELL-01 | Shell (single course) | 9 | RT/UT |  |  | Not started
320SR01 | SHELL-01 | Shell (single course) | 10 | Grinding |  |  | Not started
320SR01 | SHELL-01 | Shell (single course) | 11 | Inspection |  |  | Not started
320SR01 | TOP-HEAD-01 | Top Dished End (head) | 1 | Plate Cutting |  |  | Not started
320SR01 | TOP-HEAD-01 | Top Dished End (head) | 2 | Pressing / Spinning (Hot Forming) |  |  | Not started
320SR01 | TOP-HEAD-01 | Top Dished End (head) | 3 | Trimming |  |  | Not started
320SR01 | TOP-HEAD-01 | Top Dished End (head) | 4 | NDT |  |  | Not started
320SR01 | TOP-HEAD-01 | Top Dished End (head) | 5 | Inspection |  |  | Not started
320SR01 | BOTTOM-HEAD-01 | Bottom Dished End (head) | 1 | Plate Cutting |  |  | Not started
320SR01 | BOTTOM-HEAD-01 | Bottom Dished End (head) | 2 | Pressing / Spinning (Hot Forming) |  |  | Not started
320SR01 | BOTTOM-HEAD-01 | Bottom Dished End (head) | 3 | Trimming |  |  | Not started
320SR01 | BOTTOM-HEAD-01 | Bottom Dished End (head) | 4 | NDT |  |  | Not started
320SR01 | BOTTOM-HEAD-01 | Bottom Dished End (head) | 5 | Inspection |  |  | Not started
320SR01 | SKIRT-01 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 1 | Plate Rolling |  |  | Not started
320SR01 | SKIRT-01 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 2 | Welding |  |  | Not started
320SR01 | SKIRT-01 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 3 | Machining |  |  | Not started
320SR01 | SKIRT-01 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 4 | Inspection |  |  | Not started
320SR01 | N1-01 | Nozzle N1 (flange, per detail) | 1 | Receipt |  |  | Not started
320SR01 | N1-01 | Nozzle N1 (flange, per detail) | 2 | Machining |  |  | Not started
320SR01 | N1-01 | Nozzle N1 (flange, per detail) | 3 | Facing |  |  | Not started
320SR01 | N1-01 | Nozzle N1 (flange, per detail) | 4 | Drilling |  |  | Not started
320SR01 | N1-01 | Nozzle N1 (flange, per detail) | 5 | Inspection |  |  | Not started
320SR01 | N2-01 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 1 | Receipt |  |  | Not started
320SR01 | N2-01 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 2 | Cutting |  |  | Not started
320SR01 | N2-01 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 3 | Beveling |  |  | Not started
320SR01 | N2-01 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 4 | Fit-up |  |  | Not started
320SR01 | N2-01 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 5 | Welding |  |  | Not started
320SR01 | N2-01 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 6 | RT/PT |  |  | Not started
320SR01 | N2-01 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 7 | Inspection |  |  | Not started
320SR01 | N3-01 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 1 | Receipt |  |  | Not started
320SR01 | N3-01 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 2 | Machining |  |  | Not started
320SR01 | N3-01 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 3 | NDT |  |  | Not started
320SR01 | N3-01 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 4 | Inspection |  |  | Not started
320SR01 | N4-01 | Nozzle N4 (coupling) | 1 | Receipt |  |  | Not started
320SR01 | N4-01 | Nozzle N4 (coupling) | 2 | Thread Inspection |  |  | Not started
320SR01 | N4-01 | Nozzle N4 (coupling) | 3 | Dimension Check |  |  | Not started
320SR01 | N5-01 | Nozzle N5 (coupling) | 1 | Receipt |  |  | Not started
320SR01 | N5-01 | Nozzle N5 (coupling) | 2 | Thread Inspection |  |  | Not started
320SR01 | N5-01 | Nozzle N5 (coupling) | 3 | Dimension Check |  |  | Not started
320SR01 | N6-01 | Nozzle N6 (coupling) | 1 | Receipt |  |  | Not started
320SR01 | N6-01 | Nozzle N6 (coupling) | 2 | Thread Inspection |  |  | Not started
320SR01 | N6-01 | Nozzle N6 (coupling) | 3 | Dimension Check |  |  | Not started
320SR01 | M1-01 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 1 | Receipt |  |  | Not started
320SR01 | M1-01 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 2 | Machining |  |  | Not started
320SR01 | M1-01 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 3 | NDT |  |  | Not started
320SR01 | M1-01 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 4 | Inspection |  |  | Not started
320SR02 | SHELL-02 | Shell (single course) | 1 | Receipt |  |  | Not started
320SR02 | SHELL-02 | Shell (single course) | 2 | MTC Verification |  |  | Not started
320SR02 | SHELL-02 | Shell (single course) | 3 | Cutting |  |  | Not started
320SR02 | SHELL-02 | Shell (single course) | 4 | Edge Preparation |  |  | Not started
320SR02 | SHELL-02 | Shell (single course) | 5 | Rolling |  |  | Not started |  | Team asked to track Rolling and Forming as two separate timed steps. The app's PLATE route today has one combined 'Forming' operation — see Dev Notes tab / plan doc Task 5 before splitting it in the database.
320SR02 | SHELL-02 | Shell (single course) | 6 | Forming (Sizing / Calibration) |  |  | Not started |  | Team asked to track Rolling and Forming as two separate timed steps. The app's PLATE route today has one combined 'Forming' operation — see Dev Notes tab / plan doc Task 5 before splitting it in the database.
320SR02 | SHELL-02 | Shell (single course) | 7 | Fit-up |  |  | Not started
320SR02 | SHELL-02 | Shell (single course) | 8 | Welding (Long Seam) |  |  | Not started
320SR02 | SHELL-02 | Shell (single course) | 9 | RT/UT |  |  | Not started
320SR02 | SHELL-02 | Shell (single course) | 10 | Grinding |  |  | Not started
320SR02 | SHELL-02 | Shell (single course) | 11 | Inspection |  |  | Not started
320SR02 | TOP-HEAD-02 | Top Dished End (head) | 1 | Plate Cutting |  |  | Not started
320SR02 | TOP-HEAD-02 | Top Dished End (head) | 2 | Pressing / Spinning (Hot Forming) |  |  | Not started
320SR02 | TOP-HEAD-02 | Top Dished End (head) | 3 | Trimming |  |  | Not started
320SR02 | TOP-HEAD-02 | Top Dished End (head) | 4 | NDT |  |  | Not started
320SR02 | TOP-HEAD-02 | Top Dished End (head) | 5 | Inspection |  |  | Not started
320SR02 | BOTTOM-HEAD-02 | Bottom Dished End (head) | 1 | Plate Cutting |  |  | Not started
320SR02 | BOTTOM-HEAD-02 | Bottom Dished End (head) | 2 | Pressing / Spinning (Hot Forming) |  |  | Not started
320SR02 | BOTTOM-HEAD-02 | Bottom Dished End (head) | 3 | Trimming |  |  | Not started
320SR02 | BOTTOM-HEAD-02 | Bottom Dished End (head) | 4 | NDT |  |  | Not started
320SR02 | BOTTOM-HEAD-02 | Bottom Dished End (head) | 5 | Inspection |  |  | Not started
320SR02 | SKIRT-02 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 1 | Plate Rolling |  |  | Not started
320SR02 | SKIRT-02 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 2 | Welding |  |  | Not started
320SR02 | SKIRT-02 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 3 | Machining |  |  | Not started
320SR02 | SKIRT-02 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 4 | Inspection |  |  | Not started
320SR02 | N1-02 | Nozzle N1 (flange, per detail) | 1 | Receipt |  |  | Not started
320SR02 | N1-02 | Nozzle N1 (flange, per detail) | 2 | Machining |  |  | Not started
320SR02 | N1-02 | Nozzle N1 (flange, per detail) | 3 | Facing |  |  | Not started
320SR02 | N1-02 | Nozzle N1 (flange, per detail) | 4 | Drilling |  |  | Not started
320SR02 | N1-02 | Nozzle N1 (flange, per detail) | 5 | Inspection |  |  | Not started
320SR02 | N2-02 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 1 | Receipt |  |  | Not started
320SR02 | N2-02 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 2 | Cutting |  |  | Not started
320SR02 | N2-02 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 3 | Beveling |  |  | Not started
320SR02 | N2-02 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 4 | Fit-up |  |  | Not started
320SR02 | N2-02 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 5 | Welding |  |  | Not started
320SR02 | N2-02 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 6 | RT/PT |  |  | Not started
320SR02 | N2-02 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 7 | Inspection |  |  | Not started
320SR02 | N3-02 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 1 | Receipt |  |  | Not started
320SR02 | N3-02 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 2 | Machining |  |  | Not started
320SR02 | N3-02 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 3 | NDT |  |  | Not started
320SR02 | N3-02 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 4 | Inspection |  |  | Not started
320SR02 | N4-02 | Nozzle N4 (coupling) | 1 | Receipt |  |  | Not started
320SR02 | N4-02 | Nozzle N4 (coupling) | 2 | Thread Inspection |  |  | Not started
320SR02 | N4-02 | Nozzle N4 (coupling) | 3 | Dimension Check |  |  | Not started
320SR02 | N5-02 | Nozzle N5 (coupling) | 1 | Receipt |  |  | Not started
320SR02 | N5-02 | Nozzle N5 (coupling) | 2 | Thread Inspection |  |  | Not started
320SR02 | N5-02 | Nozzle N5 (coupling) | 3 | Dimension Check |  |  | Not started
320SR02 | N6-02 | Nozzle N6 (coupling) | 1 | Receipt |  |  | Not started
320SR02 | N6-02 | Nozzle N6 (coupling) | 2 | Thread Inspection |  |  | Not started
320SR02 | N6-02 | Nozzle N6 (coupling) | 3 | Dimension Check |  |  | Not started
320SR02 | M1-02 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 1 | Receipt |  |  | Not started
320SR02 | M1-02 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 2 | Machining |  |  | Not started
320SR02 | M1-02 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 3 | NDT |  |  | Not started
320SR02 | M1-02 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 4 | Inspection |  |  | Not started
320SR03 | SHELL-03 | Shell (single course) | 1 | Receipt |  |  | Not started
320SR03 | SHELL-03 | Shell (single course) | 2 | MTC Verification |  |  | Not started
320SR03 | SHELL-03 | Shell (single course) | 3 | Cutting |  |  | Not started
320SR03 | SHELL-03 | Shell (single course) | 4 | Edge Preparation |  |  | Not started
320SR03 | SHELL-03 | Shell (single course) | 5 | Rolling |  |  | Not started |  | Team asked to track Rolling and Forming as two separate timed steps. The app's PLATE route today has one combined 'Forming' operation — see Dev Notes tab / plan doc Task 5 before splitting it in the database.
320SR03 | SHELL-03 | Shell (single course) | 6 | Forming (Sizing / Calibration) |  |  | Not started |  | Team asked to track Rolling and Forming as two separate timed steps. The app's PLATE route today has one combined 'Forming' operation — see Dev Notes tab / plan doc Task 5 before splitting it in the database.
320SR03 | SHELL-03 | Shell (single course) | 7 | Fit-up |  |  | Not started
320SR03 | SHELL-03 | Shell (single course) | 8 | Welding (Long Seam) |  |  | Not started
320SR03 | SHELL-03 | Shell (single course) | 9 | RT/UT |  |  | Not started
320SR03 | SHELL-03 | Shell (single course) | 10 | Grinding |  |  | Not started
320SR03 | SHELL-03 | Shell (single course) | 11 | Inspection |  |  | Not started
320SR03 | TOP-HEAD-03 | Top Dished End (head) | 1 | Plate Cutting |  |  | Not started
320SR03 | TOP-HEAD-03 | Top Dished End (head) | 2 | Pressing / Spinning (Hot Forming) |  |  | Not started
320SR03 | TOP-HEAD-03 | Top Dished End (head) | 3 | Trimming |  |  | Not started
320SR03 | TOP-HEAD-03 | Top Dished End (head) | 4 | NDT |  |  | Not started
320SR03 | TOP-HEAD-03 | Top Dished End (head) | 5 | Inspection |  |  | Not started
320SR03 | BOTTOM-HEAD-03 | Bottom Dished End (head) | 1 | Plate Cutting |  |  | Not started
320SR03 | BOTTOM-HEAD-03 | Bottom Dished End (head) | 2 | Pressing / Spinning (Hot Forming) |  |  | Not started
320SR03 | BOTTOM-HEAD-03 | Bottom Dished End (head) | 3 | Trimming |  |  | Not started
320SR03 | BOTTOM-HEAD-03 | Bottom Dished End (head) | 4 | NDT |  |  | Not started
320SR03 | BOTTOM-HEAD-03 | Bottom Dished End (head) | 5 | Inspection |  |  | Not started
320SR03 | SKIRT-03 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 1 | Plate Rolling |  |  | Not started
320SR03 | SKIRT-03 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 2 | Welding |  |  | Not started
320SR03 | SKIRT-03 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 3 | Machining |  |  | Not started
320SR03 | SKIRT-03 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 4 | Inspection |  |  | Not started
320SR03 | N1-03 | Nozzle N1 (flange, per detail) | 1 | Receipt |  |  | Not started
320SR03 | N1-03 | Nozzle N1 (flange, per detail) | 2 | Machining |  |  | Not started
320SR03 | N1-03 | Nozzle N1 (flange, per detail) | 3 | Facing |  |  | Not started
320SR03 | N1-03 | Nozzle N1 (flange, per detail) | 4 | Drilling |  |  | Not started
320SR03 | N1-03 | Nozzle N1 (flange, per detail) | 5 | Inspection |  |  | Not started
320SR03 | N2-03 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 1 | Receipt |  |  | Not started
320SR03 | N2-03 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 2 | Cutting |  |  | Not started
320SR03 | N2-03 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 3 | Beveling |  |  | Not started
320SR03 | N2-03 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 4 | Fit-up |  |  | Not started
320SR03 | N2-03 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 5 | Welding |  |  | Not started
320SR03 | N2-03 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 6 | RT/PT |  |  | Not started
320SR03 | N2-03 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 7 | Inspection |  |  | Not started
320SR03 | N3-03 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 1 | Receipt |  |  | Not started
320SR03 | N3-03 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 2 | Machining |  |  | Not started
320SR03 | N3-03 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 3 | NDT |  |  | Not started
320SR03 | N3-03 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 4 | Inspection |  |  | Not started
320SR03 | N4-03 | Nozzle N4 (coupling) | 1 | Receipt |  |  | Not started
320SR03 | N4-03 | Nozzle N4 (coupling) | 2 | Thread Inspection |  |  | Not started
320SR03 | N4-03 | Nozzle N4 (coupling) | 3 | Dimension Check |  |  | Not started
320SR03 | N5-03 | Nozzle N5 (coupling) | 1 | Receipt |  |  | Not started
320SR03 | N5-03 | Nozzle N5 (coupling) | 2 | Thread Inspection |  |  | Not started
320SR03 | N5-03 | Nozzle N5 (coupling) | 3 | Dimension Check |  |  | Not started
320SR03 | N6-03 | Nozzle N6 (coupling) | 1 | Receipt |  |  | Not started
320SR03 | N6-03 | Nozzle N6 (coupling) | 2 | Thread Inspection |  |  | Not started
320SR03 | N6-03 | Nozzle N6 (coupling) | 3 | Dimension Check |  |  | Not started
320SR03 | M1-03 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 1 | Receipt |  |  | Not started
320SR03 | M1-03 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 2 | Machining |  |  | Not started
320SR03 | M1-03 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 3 | NDT |  |  | Not started
320SR03 | M1-03 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 4 | Inspection |  |  | Not started
320SR04 | SHELL-04 | Shell (single course) | 1 | Receipt |  |  | Not started
320SR04 | SHELL-04 | Shell (single course) | 2 | MTC Verification |  |  | Not started
320SR04 | SHELL-04 | Shell (single course) | 3 | Cutting |  |  | Not started
320SR04 | SHELL-04 | Shell (single course) | 4 | Edge Preparation |  |  | Not started
320SR04 | SHELL-04 | Shell (single course) | 5 | Rolling |  |  | Not started |  | Team asked to track Rolling and Forming as two separate timed steps. The app's PLATE route today has one combined 'Forming' operation — see Dev Notes tab / plan doc Task 5 before splitting it in the database.
320SR04 | SHELL-04 | Shell (single course) | 6 | Forming (Sizing / Calibration) |  |  | Not started |  | Team asked to track Rolling and Forming as two separate timed steps. The app's PLATE route today has one combined 'Forming' operation — see Dev Notes tab / plan doc Task 5 before splitting it in the database.
320SR04 | SHELL-04 | Shell (single course) | 7 | Fit-up |  |  | Not started
320SR04 | SHELL-04 | Shell (single course) | 8 | Welding (Long Seam) |  |  | Not started
320SR04 | SHELL-04 | Shell (single course) | 9 | RT/UT |  |  | Not started
320SR04 | SHELL-04 | Shell (single course) | 10 | Grinding |  |  | Not started
320SR04 | SHELL-04 | Shell (single course) | 11 | Inspection |  |  | Not started
320SR04 | TOP-HEAD-04 | Top Dished End (head) | 1 | Plate Cutting |  |  | Not started
320SR04 | TOP-HEAD-04 | Top Dished End (head) | 2 | Pressing / Spinning (Hot Forming) |  |  | Not started
320SR04 | TOP-HEAD-04 | Top Dished End (head) | 3 | Trimming |  |  | Not started
320SR04 | TOP-HEAD-04 | Top Dished End (head) | 4 | NDT |  |  | Not started
320SR04 | TOP-HEAD-04 | Top Dished End (head) | 5 | Inspection |  |  | Not started
320SR04 | BOTTOM-HEAD-04 | Bottom Dished End (head) | 1 | Plate Cutting |  |  | Not started
320SR04 | BOTTOM-HEAD-04 | Bottom Dished End (head) | 2 | Pressing / Spinning (Hot Forming) |  |  | Not started
320SR04 | BOTTOM-HEAD-04 | Bottom Dished End (head) | 3 | Trimming |  |  | Not started
320SR04 | BOTTOM-HEAD-04 | Bottom Dished End (head) | 4 | NDT |  |  | Not started
320SR04 | BOTTOM-HEAD-04 | Bottom Dished End (head) | 5 | Inspection |  |  | Not started
320SR04 | SKIRT-04 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 1 | Plate Rolling |  |  | Not started
320SR04 | SKIRT-04 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 2 | Welding |  |  | Not started
320SR04 | SKIRT-04 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 3 | Machining |  |  | Not started
320SR04 | SKIRT-04 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 4 | Inspection |  |  | Not started
320SR04 | N1-04 | Nozzle N1 (flange, per detail) | 1 | Receipt |  |  | Not started
320SR04 | N1-04 | Nozzle N1 (flange, per detail) | 2 | Machining |  |  | Not started
320SR04 | N1-04 | Nozzle N1 (flange, per detail) | 3 | Facing |  |  | Not started
320SR04 | N1-04 | Nozzle N1 (flange, per detail) | 4 | Drilling |  |  | Not started
320SR04 | N1-04 | Nozzle N1 (flange, per detail) | 5 | Inspection |  |  | Not started
320SR04 | N2-04 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 1 | Receipt |  |  | Not started
320SR04 | N2-04 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 2 | Cutting |  |  | Not started
320SR04 | N2-04 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 3 | Beveling |  |  | Not started
320SR04 | N2-04 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 4 | Fit-up |  |  | Not started
320SR04 | N2-04 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 5 | Welding |  |  | Not started
320SR04 | N2-04 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 6 | RT/PT |  |  | Not started
320SR04 | N2-04 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 7 | Inspection |  |  | Not started
320SR04 | N3-04 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 1 | Receipt |  |  | Not started
320SR04 | N3-04 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 2 | Machining |  |  | Not started
320SR04 | N3-04 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 3 | NDT |  |  | Not started
320SR04 | N3-04 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 4 | Inspection |  |  | Not started
320SR04 | N4-04 | Nozzle N4 (coupling) | 1 | Receipt |  |  | Not started
320SR04 | N4-04 | Nozzle N4 (coupling) | 2 | Thread Inspection |  |  | Not started
320SR04 | N4-04 | Nozzle N4 (coupling) | 3 | Dimension Check |  |  | Not started
320SR04 | N5-04 | Nozzle N5 (coupling) | 1 | Receipt |  |  | Not started
320SR04 | N5-04 | Nozzle N5 (coupling) | 2 | Thread Inspection |  |  | Not started
320SR04 | N5-04 | Nozzle N5 (coupling) | 3 | Dimension Check |  |  | Not started
320SR04 | N6-04 | Nozzle N6 (coupling) | 1 | Receipt |  |  | Not started
320SR04 | N6-04 | Nozzle N6 (coupling) | 2 | Thread Inspection |  |  | Not started
320SR04 | N6-04 | Nozzle N6 (coupling) | 3 | Dimension Check |  |  | Not started
320SR04 | M1-04 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 1 | Receipt |  |  | Not started
320SR04 | M1-04 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 2 | Machining |  |  | Not started
320SR04 | M1-04 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 3 | NDT |  |  | Not started
320SR04 | M1-04 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 4 | Inspection |  |  | Not started
320SR05 | SHELL-05 | Shell (single course) | 1 | Receipt |  |  | Not started
320SR05 | SHELL-05 | Shell (single course) | 2 | MTC Verification |  |  | Not started
320SR05 | SHELL-05 | Shell (single course) | 3 | Cutting |  |  | Not started
320SR05 | SHELL-05 | Shell (single course) | 4 | Edge Preparation |  |  | Not started
320SR05 | SHELL-05 | Shell (single course) | 5 | Rolling |  |  | Not started |  | Team asked to track Rolling and Forming as two separate timed steps. The app's PLATE route today has one combined 'Forming' operation — see Dev Notes tab / plan doc Task 5 before splitting it in the database.
320SR05 | SHELL-05 | Shell (single course) | 6 | Forming (Sizing / Calibration) |  |  | Not started |  | Team asked to track Rolling and Forming as two separate timed steps. The app's PLATE route today has one combined 'Forming' operation — see Dev Notes tab / plan doc Task 5 before splitting it in the database.
320SR05 | SHELL-05 | Shell (single course) | 7 | Fit-up |  |  | Not started
320SR05 | SHELL-05 | Shell (single course) | 8 | Welding (Long Seam) |  |  | Not started
320SR05 | SHELL-05 | Shell (single course) | 9 | RT/UT |  |  | Not started
320SR05 | SHELL-05 | Shell (single course) | 10 | Grinding |  |  | Not started
320SR05 | SHELL-05 | Shell (single course) | 11 | Inspection |  |  | Not started
320SR05 | TOP-HEAD-05 | Top Dished End (head) | 1 | Plate Cutting |  |  | Not started
320SR05 | TOP-HEAD-05 | Top Dished End (head) | 2 | Pressing / Spinning (Hot Forming) |  |  | Not started
320SR05 | TOP-HEAD-05 | Top Dished End (head) | 3 | Trimming |  |  | Not started
320SR05 | TOP-HEAD-05 | Top Dished End (head) | 4 | NDT |  |  | Not started
320SR05 | TOP-HEAD-05 | Top Dished End (head) | 5 | Inspection |  |  | Not started
320SR05 | BOTTOM-HEAD-05 | Bottom Dished End (head) | 1 | Plate Cutting |  |  | Not started
320SR05 | BOTTOM-HEAD-05 | Bottom Dished End (head) | 2 | Pressing / Spinning (Hot Forming) |  |  | Not started
320SR05 | BOTTOM-HEAD-05 | Bottom Dished End (head) | 3 | Trimming |  |  | Not started
320SR05 | BOTTOM-HEAD-05 | Bottom Dished End (head) | 4 | NDT |  |  | Not started
320SR05 | BOTTOM-HEAD-05 | Bottom Dished End (head) | 5 | Inspection |  |  | Not started
320SR05 | SKIRT-05 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 1 | Plate Rolling |  |  | Not started
320SR05 | SKIRT-05 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 2 | Welding |  |  | Not started
320SR05 | SKIRT-05 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 3 | Machining |  |  | Not started
320SR05 | SKIRT-05 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 4 | Inspection |  |  | Not started
320SR05 | N1-05 | Nozzle N1 (flange, per detail) | 1 | Receipt |  |  | Not started
320SR05 | N1-05 | Nozzle N1 (flange, per detail) | 2 | Machining |  |  | Not started
320SR05 | N1-05 | Nozzle N1 (flange, per detail) | 3 | Facing |  |  | Not started
320SR05 | N1-05 | Nozzle N1 (flange, per detail) | 4 | Drilling |  |  | Not started
320SR05 | N1-05 | Nozzle N1 (flange, per detail) | 5 | Inspection |  |  | Not started
320SR05 | N2-05 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 1 | Receipt |  |  | Not started
320SR05 | N2-05 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 2 | Cutting |  |  | Not started
320SR05 | N2-05 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 3 | Beveling |  |  | Not started
320SR05 | N2-05 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 4 | Fit-up |  |  | Not started
320SR05 | N2-05 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 5 | Welding |  |  | Not started
320SR05 | N2-05 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 6 | RT/PT |  |  | Not started
320SR05 | N2-05 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 7 | Inspection |  |  | Not started
320SR05 | N3-05 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 1 | Receipt |  |  | Not started
320SR05 | N3-05 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 2 | Machining |  |  | Not started
320SR05 | N3-05 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 3 | NDT |  |  | Not started
320SR05 | N3-05 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 4 | Inspection |  |  | Not started
320SR05 | N4-05 | Nozzle N4 (coupling) | 1 | Receipt |  |  | Not started
320SR05 | N4-05 | Nozzle N4 (coupling) | 2 | Thread Inspection |  |  | Not started
320SR05 | N4-05 | Nozzle N4 (coupling) | 3 | Dimension Check |  |  | Not started
320SR05 | N5-05 | Nozzle N5 (coupling) | 1 | Receipt |  |  | Not started
320SR05 | N5-05 | Nozzle N5 (coupling) | 2 | Thread Inspection |  |  | Not started
320SR05 | N5-05 | Nozzle N5 (coupling) | 3 | Dimension Check |  |  | Not started
320SR05 | N6-05 | Nozzle N6 (coupling) | 1 | Receipt |  |  | Not started
320SR05 | N6-05 | Nozzle N6 (coupling) | 2 | Thread Inspection |  |  | Not started
320SR05 | N6-05 | Nozzle N6 (coupling) | 3 | Dimension Check |  |  | Not started
320SR05 | M1-05 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 1 | Receipt |  |  | Not started
320SR05 | M1-05 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 2 | Machining |  |  | Not started
320SR05 | M1-05 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 3 | NDT |  |  | Not started
320SR05 | M1-05 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 4 | Inspection |  |  | Not started
320SR06 | SHELL-06 | Shell (single course) | 1 | Receipt |  |  | Not started
320SR06 | SHELL-06 | Shell (single course) | 2 | MTC Verification |  |  | Not started
320SR06 | SHELL-06 | Shell (single course) | 3 | Cutting |  |  | Not started
320SR06 | SHELL-06 | Shell (single course) | 4 | Edge Preparation |  |  | Not started
320SR06 | SHELL-06 | Shell (single course) | 5 | Rolling |  |  | Not started |  | Team asked to track Rolling and Forming as two separate timed steps. The app's PLATE route today has one combined 'Forming' operation — see Dev Notes tab / plan doc Task 5 before splitting it in the database.
320SR06 | SHELL-06 | Shell (single course) | 6 | Forming (Sizing / Calibration) |  |  | Not started |  | Team asked to track Rolling and Forming as two separate timed steps. The app's PLATE route today has one combined 'Forming' operation — see Dev Notes tab / plan doc Task 5 before splitting it in the database.
320SR06 | SHELL-06 | Shell (single course) | 7 | Fit-up |  |  | Not started
320SR06 | SHELL-06 | Shell (single course) | 8 | Welding (Long Seam) |  |  | Not started
320SR06 | SHELL-06 | Shell (single course) | 9 | RT/UT |  |  | Not started
320SR06 | SHELL-06 | Shell (single course) | 10 | Grinding |  |  | Not started
320SR06 | SHELL-06 | Shell (single course) | 11 | Inspection |  |  | Not started
320SR06 | TOP-HEAD-06 | Top Dished End (head) | 1 | Plate Cutting |  |  | Not started
320SR06 | TOP-HEAD-06 | Top Dished End (head) | 2 | Pressing / Spinning (Hot Forming) |  |  | Not started
320SR06 | TOP-HEAD-06 | Top Dished End (head) | 3 | Trimming |  |  | Not started
320SR06 | TOP-HEAD-06 | Top Dished End (head) | 4 | NDT |  |  | Not started
320SR06 | TOP-HEAD-06 | Top Dished End (head) | 5 | Inspection |  |  | Not started
320SR06 | BOTTOM-HEAD-06 | Bottom Dished End (head) | 1 | Plate Cutting |  |  | Not started
320SR06 | BOTTOM-HEAD-06 | Bottom Dished End (head) | 2 | Pressing / Spinning (Hot Forming) |  |  | Not started
320SR06 | BOTTOM-HEAD-06 | Bottom Dished End (head) | 3 | Trimming |  |  | Not started
320SR06 | BOTTOM-HEAD-06 | Bottom Dished End (head) | 4 | NDT |  |  | Not started
320SR06 | BOTTOM-HEAD-06 | Bottom Dished End (head) | 5 | Inspection |  |  | Not started
320SR06 | SKIRT-06 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 1 | Plate Rolling |  |  | Not started
320SR06 | SKIRT-06 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 2 | Welding |  |  | Not started
320SR06 | SKIRT-06 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 3 | Machining |  |  | Not started
320SR06 | SKIRT-06 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 4 | Inspection |  |  | Not started
320SR06 | N1-06 | Nozzle N1 (flange, per detail) | 1 | Receipt |  |  | Not started
320SR06 | N1-06 | Nozzle N1 (flange, per detail) | 2 | Machining |  |  | Not started
320SR06 | N1-06 | Nozzle N1 (flange, per detail) | 3 | Facing |  |  | Not started
320SR06 | N1-06 | Nozzle N1 (flange, per detail) | 4 | Drilling |  |  | Not started
320SR06 | N1-06 | Nozzle N1 (flange, per detail) | 5 | Inspection |  |  | Not started
320SR06 | N2-06 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 1 | Receipt |  |  | Not started
320SR06 | N2-06 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 2 | Cutting |  |  | Not started
320SR06 | N2-06 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 3 | Beveling |  |  | Not started
320SR06 | N2-06 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 4 | Fit-up |  |  | Not started
320SR06 | N2-06 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 5 | Welding |  |  | Not started
320SR06 | N2-06 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 6 | RT/PT |  |  | Not started
320SR06 | N2-06 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 7 | Inspection |  |  | Not started
320SR06 | N3-06 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 1 | Receipt |  |  | Not started
320SR06 | N3-06 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 2 | Machining |  |  | Not started
320SR06 | N3-06 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 3 | NDT |  |  | Not started
320SR06 | N3-06 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 4 | Inspection |  |  | Not started
320SR06 | N4-06 | Nozzle N4 (coupling) | 1 | Receipt |  |  | Not started
320SR06 | N4-06 | Nozzle N4 (coupling) | 2 | Thread Inspection |  |  | Not started
320SR06 | N4-06 | Nozzle N4 (coupling) | 3 | Dimension Check |  |  | Not started
320SR06 | N5-06 | Nozzle N5 (coupling) | 1 | Receipt |  |  | Not started
320SR06 | N5-06 | Nozzle N5 (coupling) | 2 | Thread Inspection |  |  | Not started
320SR06 | N5-06 | Nozzle N5 (coupling) | 3 | Dimension Check |  |  | Not started
320SR06 | N6-06 | Nozzle N6 (coupling) | 1 | Receipt |  |  | Not started
320SR06 | N6-06 | Nozzle N6 (coupling) | 2 | Thread Inspection |  |  | Not started
320SR06 | N6-06 | Nozzle N6 (coupling) | 3 | Dimension Check |  |  | Not started
320SR06 | M1-06 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 1 | Receipt |  |  | Not started
320SR06 | M1-06 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 2 | Machining |  |  | Not started
320SR06 | M1-06 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 3 | NDT |  |  | Not started
320SR06 | M1-06 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 4 | Inspection |  |  | Not started
320SR07 | SHELL-07 | Shell (single course) | 1 | Receipt |  |  | Not started
320SR07 | SHELL-07 | Shell (single course) | 2 | MTC Verification |  |  | Not started
320SR07 | SHELL-07 | Shell (single course) | 3 | Cutting |  |  | Not started
320SR07 | SHELL-07 | Shell (single course) | 4 | Edge Preparation |  |  | Not started
320SR07 | SHELL-07 | Shell (single course) | 5 | Rolling |  |  | Not started |  | Team asked to track Rolling and Forming as two separate timed steps. The app's PLATE route today has one combined 'Forming' operation — see Dev Notes tab / plan doc Task 5 before splitting it in the database.
320SR07 | SHELL-07 | Shell (single course) | 6 | Forming (Sizing / Calibration) |  |  | Not started |  | Team asked to track Rolling and Forming as two separate timed steps. The app's PLATE route today has one combined 'Forming' operation — see Dev Notes tab / plan doc Task 5 before splitting it in the database.
320SR07 | SHELL-07 | Shell (single course) | 7 | Fit-up |  |  | Not started
320SR07 | SHELL-07 | Shell (single course) | 8 | Welding (Long Seam) |  |  | Not started
320SR07 | SHELL-07 | Shell (single course) | 9 | RT/UT |  |  | Not started
320SR07 | SHELL-07 | Shell (single course) | 10 | Grinding |  |  | Not started
320SR07 | SHELL-07 | Shell (single course) | 11 | Inspection |  |  | Not started
320SR07 | TOP-HEAD-07 | Top Dished End (head) | 1 | Plate Cutting |  |  | Not started
320SR07 | TOP-HEAD-07 | Top Dished End (head) | 2 | Pressing / Spinning (Hot Forming) |  |  | Not started
320SR07 | TOP-HEAD-07 | Top Dished End (head) | 3 | Trimming |  |  | Not started
320SR07 | TOP-HEAD-07 | Top Dished End (head) | 4 | NDT |  |  | Not started
320SR07 | TOP-HEAD-07 | Top Dished End (head) | 5 | Inspection |  |  | Not started
320SR07 | BOTTOM-HEAD-07 | Bottom Dished End (head) | 1 | Plate Cutting |  |  | Not started
320SR07 | BOTTOM-HEAD-07 | Bottom Dished End (head) | 2 | Pressing / Spinning (Hot Forming) |  |  | Not started
320SR07 | BOTTOM-HEAD-07 | Bottom Dished End (head) | 3 | Trimming |  |  | Not started
320SR07 | BOTTOM-HEAD-07 | Bottom Dished End (head) | 4 | NDT |  |  | Not started
320SR07 | BOTTOM-HEAD-07 | Bottom Dished End (head) | 5 | Inspection |  |  | Not started
320SR07 | SKIRT-07 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 1 | Plate Rolling |  |  | Not started
320SR07 | SKIRT-07 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 2 | Welding |  |  | Not started
320SR07 | SKIRT-07 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 3 | Machining |  |  | Not started
320SR07 | SKIRT-07 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 4 | Inspection |  |  | Not started
320SR07 | N1-07 | Nozzle N1 (flange, per detail) | 1 | Receipt |  |  | Not started
320SR07 | N1-07 | Nozzle N1 (flange, per detail) | 2 | Machining |  |  | Not started
320SR07 | N1-07 | Nozzle N1 (flange, per detail) | 3 | Facing |  |  | Not started
320SR07 | N1-07 | Nozzle N1 (flange, per detail) | 4 | Drilling |  |  | Not started
320SR07 | N1-07 | Nozzle N1 (flange, per detail) | 5 | Inspection |  |  | Not started
320SR07 | N2-07 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 1 | Receipt |  |  | Not started
320SR07 | N2-07 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 2 | Cutting |  |  | Not started
320SR07 | N2-07 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 3 | Beveling |  |  | Not started
320SR07 | N2-07 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 4 | Fit-up |  |  | Not started
320SR07 | N2-07 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 5 | Welding |  |  | Not started
320SR07 | N2-07 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 6 | RT/PT |  |  | Not started
320SR07 | N2-07 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 7 | Inspection |  |  | Not started
320SR07 | N3-07 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 1 | Receipt |  |  | Not started
320SR07 | N3-07 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 2 | Machining |  |  | Not started
320SR07 | N3-07 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 3 | NDT |  |  | Not started
320SR07 | N3-07 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 4 | Inspection |  |  | Not started
320SR07 | N4-07 | Nozzle N4 (coupling) | 1 | Receipt |  |  | Not started
320SR07 | N4-07 | Nozzle N4 (coupling) | 2 | Thread Inspection |  |  | Not started
320SR07 | N4-07 | Nozzle N4 (coupling) | 3 | Dimension Check |  |  | Not started
320SR07 | N5-07 | Nozzle N5 (coupling) | 1 | Receipt |  |  | Not started
320SR07 | N5-07 | Nozzle N5 (coupling) | 2 | Thread Inspection |  |  | Not started
320SR07 | N5-07 | Nozzle N5 (coupling) | 3 | Dimension Check |  |  | Not started
320SR07 | N6-07 | Nozzle N6 (coupling) | 1 | Receipt |  |  | Not started
320SR07 | N6-07 | Nozzle N6 (coupling) | 2 | Thread Inspection |  |  | Not started
320SR07 | N6-07 | Nozzle N6 (coupling) | 3 | Dimension Check |  |  | Not started
320SR07 | M1-07 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 1 | Receipt |  |  | Not started
320SR07 | M1-07 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 2 | Machining |  |  | Not started
320SR07 | M1-07 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 3 | NDT |  |  | Not started
320SR07 | M1-07 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 4 | Inspection |  |  | Not started
320SR08 | SHELL-08 | Shell (single course) | 1 | Receipt |  |  | Not started
320SR08 | SHELL-08 | Shell (single course) | 2 | MTC Verification |  |  | Not started
320SR08 | SHELL-08 | Shell (single course) | 3 | Cutting |  |  | Not started
320SR08 | SHELL-08 | Shell (single course) | 4 | Edge Preparation |  |  | Not started
320SR08 | SHELL-08 | Shell (single course) | 5 | Rolling |  |  | Not started |  | Team asked to track Rolling and Forming as two separate timed steps. The app's PLATE route today has one combined 'Forming' operation — see Dev Notes tab / plan doc Task 5 before splitting it in the database.
320SR08 | SHELL-08 | Shell (single course) | 6 | Forming (Sizing / Calibration) |  |  | Not started |  | Team asked to track Rolling and Forming as two separate timed steps. The app's PLATE route today has one combined 'Forming' operation — see Dev Notes tab / plan doc Task 5 before splitting it in the database.
320SR08 | SHELL-08 | Shell (single course) | 7 | Fit-up |  |  | Not started
320SR08 | SHELL-08 | Shell (single course) | 8 | Welding (Long Seam) |  |  | Not started
320SR08 | SHELL-08 | Shell (single course) | 9 | RT/UT |  |  | Not started
320SR08 | SHELL-08 | Shell (single course) | 10 | Grinding |  |  | Not started
320SR08 | SHELL-08 | Shell (single course) | 11 | Inspection |  |  | Not started
320SR08 | TOP-HEAD-08 | Top Dished End (head) | 1 | Plate Cutting |  |  | Not started
320SR08 | TOP-HEAD-08 | Top Dished End (head) | 2 | Pressing / Spinning (Hot Forming) |  |  | Not started
320SR08 | TOP-HEAD-08 | Top Dished End (head) | 3 | Trimming |  |  | Not started
320SR08 | TOP-HEAD-08 | Top Dished End (head) | 4 | NDT |  |  | Not started
320SR08 | TOP-HEAD-08 | Top Dished End (head) | 5 | Inspection |  |  | Not started
320SR08 | BOTTOM-HEAD-08 | Bottom Dished End (head) | 1 | Plate Cutting |  |  | Not started
320SR08 | BOTTOM-HEAD-08 | Bottom Dished End (head) | 2 | Pressing / Spinning (Hot Forming) |  |  | Not started
320SR08 | BOTTOM-HEAD-08 | Bottom Dished End (head) | 3 | Trimming |  |  | Not started
320SR08 | BOTTOM-HEAD-08 | Bottom Dished End (head) | 4 | NDT |  |  | Not started
320SR08 | BOTTOM-HEAD-08 | Bottom Dished End (head) | 5 | Inspection |  |  | Not started
320SR08 | SKIRT-08 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 1 | Plate Rolling |  |  | Not started
320SR08 | SKIRT-08 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 2 | Welding |  |  | Not started
320SR08 | SKIRT-08 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 3 | Machining |  |  | Not started
320SR08 | SKIRT-08 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 4 | Inspection |  |  | Not started
320SR08 | N1-08 | Nozzle N1 (flange, per detail) | 1 | Receipt |  |  | Not started
320SR08 | N1-08 | Nozzle N1 (flange, per detail) | 2 | Machining |  |  | Not started
320SR08 | N1-08 | Nozzle N1 (flange, per detail) | 3 | Facing |  |  | Not started
320SR08 | N1-08 | Nozzle N1 (flange, per detail) | 4 | Drilling |  |  | Not started
320SR08 | N1-08 | Nozzle N1 (flange, per detail) | 5 | Inspection |  |  | Not started
320SR08 | N2-08 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 1 | Receipt |  |  | Not started
320SR08 | N2-08 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 2 | Cutting |  |  | Not started
320SR08 | N2-08 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 3 | Beveling |  |  | Not started
320SR08 | N2-08 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 4 | Fit-up |  |  | Not started
320SR08 | N2-08 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 5 | Welding |  |  | Not started
320SR08 | N2-08 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 6 | RT/PT |  |  | Not started
320SR08 | N2-08 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 7 | Inspection |  |  | Not started
320SR08 | N3-08 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 1 | Receipt |  |  | Not started
320SR08 | N3-08 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 2 | Machining |  |  | Not started
320SR08 | N3-08 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 3 | NDT |  |  | Not started
320SR08 | N3-08 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 4 | Inspection |  |  | Not started
320SR08 | N4-08 | Nozzle N4 (coupling) | 1 | Receipt |  |  | Not started
320SR08 | N4-08 | Nozzle N4 (coupling) | 2 | Thread Inspection |  |  | Not started
320SR08 | N4-08 | Nozzle N4 (coupling) | 3 | Dimension Check |  |  | Not started
320SR08 | N5-08 | Nozzle N5 (coupling) | 1 | Receipt |  |  | Not started
320SR08 | N5-08 | Nozzle N5 (coupling) | 2 | Thread Inspection |  |  | Not started
320SR08 | N5-08 | Nozzle N5 (coupling) | 3 | Dimension Check |  |  | Not started
320SR08 | N6-08 | Nozzle N6 (coupling) | 1 | Receipt |  |  | Not started
320SR08 | N6-08 | Nozzle N6 (coupling) | 2 | Thread Inspection |  |  | Not started
320SR08 | N6-08 | Nozzle N6 (coupling) | 3 | Dimension Check |  |  | Not started
320SR08 | M1-08 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 1 | Receipt |  |  | Not started
320SR08 | M1-08 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 2 | Machining |  |  | Not started
320SR08 | M1-08 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 3 | NDT |  |  | Not started
320SR08 | M1-08 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 4 | Inspection |  |  | Not started
320SR09 | SHELL-09 | Shell (single course) | 1 | Receipt |  |  | Not started
320SR09 | SHELL-09 | Shell (single course) | 2 | MTC Verification |  |  | Not started
320SR09 | SHELL-09 | Shell (single course) | 3 | Cutting |  |  | Not started
320SR09 | SHELL-09 | Shell (single course) | 4 | Edge Preparation |  |  | Not started
320SR09 | SHELL-09 | Shell (single course) | 5 | Rolling |  |  | Not started |  | Team asked to track Rolling and Forming as two separate timed steps. The app's PLATE route today has one combined 'Forming' operation — see Dev Notes tab / plan doc Task 5 before splitting it in the database.
320SR09 | SHELL-09 | Shell (single course) | 6 | Forming (Sizing / Calibration) |  |  | Not started |  | Team asked to track Rolling and Forming as two separate timed steps. The app's PLATE route today has one combined 'Forming' operation — see Dev Notes tab / plan doc Task 5 before splitting it in the database.
320SR09 | SHELL-09 | Shell (single course) | 7 | Fit-up |  |  | Not started
320SR09 | SHELL-09 | Shell (single course) | 8 | Welding (Long Seam) |  |  | Not started
320SR09 | SHELL-09 | Shell (single course) | 9 | RT/UT |  |  | Not started
320SR09 | SHELL-09 | Shell (single course) | 10 | Grinding |  |  | Not started
320SR09 | SHELL-09 | Shell (single course) | 11 | Inspection |  |  | Not started
320SR09 | TOP-HEAD-09 | Top Dished End (head) | 1 | Plate Cutting |  |  | Not started
320SR09 | TOP-HEAD-09 | Top Dished End (head) | 2 | Pressing / Spinning (Hot Forming) |  |  | Not started
320SR09 | TOP-HEAD-09 | Top Dished End (head) | 3 | Trimming |  |  | Not started
320SR09 | TOP-HEAD-09 | Top Dished End (head) | 4 | NDT |  |  | Not started
320SR09 | TOP-HEAD-09 | Top Dished End (head) | 5 | Inspection |  |  | Not started
320SR09 | BOTTOM-HEAD-09 | Bottom Dished End (head) | 1 | Plate Cutting |  |  | Not started
320SR09 | BOTTOM-HEAD-09 | Bottom Dished End (head) | 2 | Pressing / Spinning (Hot Forming) |  |  | Not started
320SR09 | BOTTOM-HEAD-09 | Bottom Dished End (head) | 3 | Trimming |  |  | Not started
320SR09 | BOTTOM-HEAD-09 | Bottom Dished End (head) | 4 | NDT |  |  | Not started
320SR09 | BOTTOM-HEAD-09 | Bottom Dished End (head) | 5 | Inspection |  |  | Not started
320SR09 | SKIRT-09 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 1 | Plate Rolling |  |  | Not started
320SR09 | SKIRT-09 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 2 | Welding |  |  | Not started
320SR09 | SKIRT-09 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 3 | Machining |  |  | Not started
320SR09 | SKIRT-09 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | 4 | Inspection |  |  | Not started
320SR09 | N1-09 | Nozzle N1 (flange, per detail) | 1 | Receipt |  |  | Not started
320SR09 | N1-09 | Nozzle N1 (flange, per detail) | 2 | Machining |  |  | Not started
320SR09 | N1-09 | Nozzle N1 (flange, per detail) | 3 | Facing |  |  | Not started
320SR09 | N1-09 | Nozzle N1 (flange, per detail) | 4 | Drilling |  |  | Not started
320SR09 | N1-09 | Nozzle N1 (flange, per detail) | 5 | Inspection |  |  | Not started
320SR09 | N2-09 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 1 | Receipt |  |  | Not started
320SR09 | N2-09 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 2 | Cutting |  |  | Not started
320SR09 | N2-09 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 3 | Beveling |  |  | Not started
320SR09 | N2-09 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 4 | Fit-up |  |  | Not started
320SR09 | N2-09 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 5 | Welding |  |  | Not started
320SR09 | N2-09 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 6 | RT/PT |  |  | Not started
320SR09 | N2-09 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | 7 | Inspection |  |  | Not started
320SR09 | N3-09 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 1 | Receipt |  |  | Not started
320SR09 | N3-09 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 2 | Machining |  |  | Not started
320SR09 | N3-09 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 3 | NDT |  |  | Not started
320SR09 | N3-09 | Nozzle N3 (SRN forging + flange + 3x stiffener) | 4 | Inspection |  |  | Not started
320SR09 | N4-09 | Nozzle N4 (coupling) | 1 | Receipt |  |  | Not started
320SR09 | N4-09 | Nozzle N4 (coupling) | 2 | Thread Inspection |  |  | Not started
320SR09 | N4-09 | Nozzle N4 (coupling) | 3 | Dimension Check |  |  | Not started
320SR09 | N5-09 | Nozzle N5 (coupling) | 1 | Receipt |  |  | Not started
320SR09 | N5-09 | Nozzle N5 (coupling) | 2 | Thread Inspection |  |  | Not started
320SR09 | N5-09 | Nozzle N5 (coupling) | 3 | Dimension Check |  |  | Not started
320SR09 | N6-09 | Nozzle N6 (coupling) | 1 | Receipt |  |  | Not started
320SR09 | N6-09 | Nozzle N6 (coupling) | 2 | Thread Inspection |  |  | Not started
320SR09 | N6-09 | Nozzle N6 (coupling) | 3 | Dimension Check |  |  | Not started
320SR09 | M1-09 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 1 | Receipt |  |  | Not started
320SR09 | M1-09 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 2 | Machining |  |  | Not started
320SR09 | M1-09 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 3 | NDT |  |  | Not started
320SR09 | M1-09 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | 4 | Inspection |  |  | Not started

## Assembly & Weld Checklist
Assembly & Weld Sequence Checklist
The shell-to-dish-end and nozzle assembly, per unit — 54 real QCP checkpoints already live in the app's QCP data. P=Perform W=Witness H=Hold R=Review.
Pale-yellow cells (Started / Completed / Cleared By / Status / Remarks) are for QC to fill in as each checkpoint clears per unit. Red = Hold point, amber = Witness point.
Unit | Sub-assembly | Sr No | Activity | DESPL | BUYER TPI | Started | Completed | Cleared by | Status | Remarks
320SR01 | A. Document & Procedure Gate | 1.1 | Drawing Approval | P | R |  |  |  | Pending
320SR01 | A. Document & Procedure Gate | 1.2 | Review And Approval Of Quality Contol Plan | P | R |  |  |  | Pending
320SR01 | A. Document & Procedure Gate | 1.3 | Hot Forming Proceude, Ht Procedure, Rt Procedure, Pt Procedure, Paut & Tofd Procedure | H | R |  |  |  | Pending
320SR01 | A. Document & Procedure Gate | 2.1 | Welding Procedure & Performance Qualification | P | R |  |  |  | Pending
320SR01 | B. Material Inspection & Traceability | 3.1 | Pressure Part - Plates,Pipes/Forgings/Flange/ Fittings | H | W |  |  |  | Pending
320SR01 | B. Material Inspection & Traceability | 3.2 | Non Pressure Parts & Attachment To Pressure Parts | H | R |  |  |  | Pending
320SR01 | B. Material Inspection & Traceability | 3.3 | Welding Consumable | R | R |  |  |  | Pending
320SR01 | B. Material Inspection & Traceability | 3.4 | Weld Plan/Weld Map | P | R |  |  |  | Pending
320SR01 | C. Shell & Head Prep | 4.1 | Transfer Of Marking And Cutting (Shell And Dished End) | H | R |  |  |  | Pending
320SR01 | D. Head Sub-Assembly | 4.2 | Inspection Of Top & Bottom Dished | R | R |  |  |  | Pending
320SR01 | D. Head Sub-Assembly | 4.2 | Simulation Heat Treatment Of Test Coupon After Forming & Testing | R | R |  |  |  | Pending
320SR01 | D. Head Sub-Assembly | 4.4 | Weld Edge Preparation Of Top & Bottom Dished End | P | R |  |  |  | Pending
320SR01 | E. Shell Sub-Assembly (LS-1) | 4.5 | Shell Weld Edge Preparation | P | R |  |  |  | Pending
320SR01 | E. Shell Sub-Assembly (LS-1) | 4.5 | L' Seam Set Up Of Shell (Ls-1 ) Along With Ptc | P | R |  |  |  | Pending
320SR01 | E. Shell Sub-Assembly (LS-1) | 4.5 | Weld Long Seam Of Shell (Ls-1 ) | P | R |  |  |  | Pending
320SR01 | E. Shell Sub-Assembly (LS-1) | 4.5 | Weld Visual Of Ls-1 | P | R |  |  |  | Pending
320SR01 | E. Shell Sub-Assembly (LS-1) | 4.5 | Paut/Tofd Of Ls-1 | P | W |  |  |  | Pending
320SR01 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Nozzle To Flange/Elbow Set Up (M1/N2/N3) | P | R |  |  |  | Pending
320SR01 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Weld Of Nozzle To Flange/Elbow (M1/N2/N3) | P | R |  |  |  | Pending
320SR01 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Weld Visual Of Cs Joint Nozzle M1/N2/N3 | P | R |  |  |  | Pending
320SR01 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Rt Circ Seam Of Nozzle Pipe To Flange (M1/N2/N3) | P | R |  |  |  | Pending
320SR01 | G. Shell + Bottom Head (CS-2) | 4.7 | Bottom Dished End To Shell Set Up (Cs-2) | P | R |  |  |  | Pending
320SR01 | G. Shell + Bottom Head (CS-2) | 4.7 | Weld Circ Seam Of Bottom Dishend To Shell (Cs-2) | P | R |  |  |  | Pending
320SR01 | G. Shell + Bottom Head (CS-2) | 4.7 | Weld Visual Of Cs -2 | P | R |  |  |  | Pending
320SR01 | G. Shell + Bottom Head (CS-2) | 4.7 | Paut/Tofd Of Cs-2 | P | W |  |  |  | Pending
320SR01 | H. Nozzle & Manway Sub-Assembly | 4.8 | Marking For Nozzle On Shell And Dished End (M1, N1 To N6) | P | R |  |  |  | Pending
320SR01 | H. Nozzle & Manway Sub-Assembly | 4.8 | Nozzle To Shell & Dished End Set Up (M1/N1/N2/N3/N4/N5/N6) | P | R |  |  |  | Pending
320SR01 | H. Nozzle & Manway Sub-Assembly | 4.8 | Weld Of Nozzle To Shell & Dished End (M1/N1/N2/N3/N4/N5/N6) | P | R |  |  |  | Pending
320SR01 | H. Nozzle & Manway Sub-Assembly | 4.8 | Weld Visual Of Nozzle To Shell & Dished End (M1/N1/N2/N3/N4/N5/N6) | P | R |  |  |  | Pending
320SR01 | H. Nozzle & Manway Sub-Assembly | 4.8 | Ultrasonic Test Of Nozzle To Shell & Dished End (M1/N1/N2/N3) | P | R |  |  |  | Pending
320SR01 | I. Final Closure Gate | 4.9 | Clearance Of Shell Before Closing Dished End Set Up | P | R |  |  |  | Pending
320SR01 | J. Shell + Top Head (CS-1) | 4.10 | Top Dished End To Shell Set Up (Cs- 1) | P | R |  |  |  | Pending
320SR01 | J. Shell + Top Head (CS-1) | 4.10 | Weld Circ Seam Of Top Dishend To Shell (Cs-1) | P | R |  |  |  | Pending
320SR01 | J. Shell + Top Head (CS-1) | 4.10 | Weld Visual Of Cs -1 | P | R |  |  |  | Pending
320SR01 | J. Shell + Top Head (CS-1) | 4.10 | Paut/Tofd Of Cs-1 | P | W |  |  |  | Pending
320SR01 | K. Attachments Sub-Assembly | 4.11 | Lifting Lug & Name Plate Bracket Set Up | P | R |  |  |  | Pending
320SR01 | K. Attachments Sub-Assembly | 4.12 | Weld Of Lifting Lug | P | R |  |  |  | Pending
320SR01 | K. Attachments Sub-Assembly | 4.12 | Weld Of Name Plate Bracket | P | R |  |  |  | Pending
320SR01 | L. Skirt Sub-Assembly | 4.13 | Skirt Support Set Up | P | R |  |  |  | Pending
320SR01 | L. Skirt Sub-Assembly | 4.14 | Weld Skirt Support | P | R |  |  |  | Pending
320SR01 | M. Pre-PWHT Gate | 4.15 | Clearance Befor Pwht | P | W |  |  |  | Pending
320SR01 | N. Heat Treatment & Post-PWHT NDT | 5.1 | Inspection Of Vessel Heat Treatment | R | R |  |  |  | Pending
320SR01 | N. Heat Treatment & Post-PWHT NDT | 5.2 | Weld Visual Of All Weld Joints | P | W |  |  |  | Pending
320SR01 | N. Heat Treatment & Post-PWHT NDT | 5.3 | Mpt Of All Weld Joint | P | W |  |  |  | Pending
320SR01 | N. Heat Treatment & Post-PWHT NDT | 5.4 | Rt Testing On All Butt Weld Joints(M1/N2/N3) Paut/Tofd For L'Seam & C'Seam Joints. (After Pwht). | P | W |  |  |  | Pending
320SR01 | O. Hydrostatic Test | 6.1 | Clearance For Hydrostatic Test | P | R |  |  |  | Pending
320SR01 | O. Hydrostatic Test | 6.2 | Before Hydrostatic Test Clearance | P | R |  |  |  | Pending
320SR01 | O. Hydrostatic Test | 6.3 | Hydrostatic Test | P | W |  |  |  | Pending
320SR01 | O. Hydrostatic Test | 6.4 | Mpt / Lpt All Weld Joints After Hydro Test | P | W |  |  |  | Pending
320SR01 | P. Surface Treatment & Painting | 7.1 | Cleaning & Surface Preparation | P | R |  |  |  | Pending
320SR01 | P. Surface Treatment & Painting | 7.2 | Painting | P | W |  |  |  | Pending
320SR01 | Q. Final Inspection, Nameplate & MDR | 8.1 | Verification Of Name Plate | P | R |  |  |  | Pending
320SR01 | Q. Final Inspection, Nameplate & MDR | 8.2 | Attachment Of Name Plate To Name Plate Bracket | P | R |  |  |  | Pending
320SR01 | Q. Final Inspection, Nameplate & MDR | 9.1 | Documentation | R | R |  |  |  | Pending
320SR02 | A. Document & Procedure Gate | 1.1 | Drawing Approval | P | R |  |  |  | Pending
320SR02 | A. Document & Procedure Gate | 1.2 | Review And Approval Of Quality Contol Plan | P | R |  |  |  | Pending
320SR02 | A. Document & Procedure Gate | 1.3 | Hot Forming Proceude, Ht Procedure, Rt Procedure, Pt Procedure, Paut & Tofd Procedure | H | R |  |  |  | Pending
320SR02 | A. Document & Procedure Gate | 2.1 | Welding Procedure & Performance Qualification | P | R |  |  |  | Pending
320SR02 | B. Material Inspection & Traceability | 3.1 | Pressure Part - Plates,Pipes/Forgings/Flange/ Fittings | H | W |  |  |  | Pending
320SR02 | B. Material Inspection & Traceability | 3.2 | Non Pressure Parts & Attachment To Pressure Parts | H | R |  |  |  | Pending
320SR02 | B. Material Inspection & Traceability | 3.3 | Welding Consumable | R | R |  |  |  | Pending
320SR02 | B. Material Inspection & Traceability | 3.4 | Weld Plan/Weld Map | P | R |  |  |  | Pending
320SR02 | C. Shell & Head Prep | 4.1 | Transfer Of Marking And Cutting (Shell And Dished End) | H | R |  |  |  | Pending
320SR02 | D. Head Sub-Assembly | 4.2 | Inspection Of Top & Bottom Dished | R | R |  |  |  | Pending
320SR02 | D. Head Sub-Assembly | 4.2 | Simulation Heat Treatment Of Test Coupon After Forming & Testing | R | R |  |  |  | Pending
320SR02 | D. Head Sub-Assembly | 4.4 | Weld Edge Preparation Of Top & Bottom Dished End | P | R |  |  |  | Pending
320SR02 | E. Shell Sub-Assembly (LS-1) | 4.5 | Shell Weld Edge Preparation | P | R |  |  |  | Pending
320SR02 | E. Shell Sub-Assembly (LS-1) | 4.5 | L' Seam Set Up Of Shell (Ls-1 ) Along With Ptc | P | R |  |  |  | Pending
320SR02 | E. Shell Sub-Assembly (LS-1) | 4.5 | Weld Long Seam Of Shell (Ls-1 ) | P | R |  |  |  | Pending
320SR02 | E. Shell Sub-Assembly (LS-1) | 4.5 | Weld Visual Of Ls-1 | P | R |  |  |  | Pending
320SR02 | E. Shell Sub-Assembly (LS-1) | 4.5 | Paut/Tofd Of Ls-1 | P | W |  |  |  | Pending
320SR02 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Nozzle To Flange/Elbow Set Up (M1/N2/N3) | P | R |  |  |  | Pending
320SR02 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Weld Of Nozzle To Flange/Elbow (M1/N2/N3) | P | R |  |  |  | Pending
320SR02 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Weld Visual Of Cs Joint Nozzle M1/N2/N3 | P | R |  |  |  | Pending
320SR02 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Rt Circ Seam Of Nozzle Pipe To Flange (M1/N2/N3) | P | R |  |  |  | Pending
320SR02 | G. Shell + Bottom Head (CS-2) | 4.7 | Bottom Dished End To Shell Set Up (Cs-2) | P | R |  |  |  | Pending
320SR02 | G. Shell + Bottom Head (CS-2) | 4.7 | Weld Circ Seam Of Bottom Dishend To Shell (Cs-2) | P | R |  |  |  | Pending
320SR02 | G. Shell + Bottom Head (CS-2) | 4.7 | Weld Visual Of Cs -2 | P | R |  |  |  | Pending
320SR02 | G. Shell + Bottom Head (CS-2) | 4.7 | Paut/Tofd Of Cs-2 | P | W |  |  |  | Pending
320SR02 | H. Nozzle & Manway Sub-Assembly | 4.8 | Marking For Nozzle On Shell And Dished End (M1, N1 To N6) | P | R |  |  |  | Pending
320SR02 | H. Nozzle & Manway Sub-Assembly | 4.8 | Nozzle To Shell & Dished End Set Up (M1/N1/N2/N3/N4/N5/N6) | P | R |  |  |  | Pending
320SR02 | H. Nozzle & Manway Sub-Assembly | 4.8 | Weld Of Nozzle To Shell & Dished End (M1/N1/N2/N3/N4/N5/N6) | P | R |  |  |  | Pending
320SR02 | H. Nozzle & Manway Sub-Assembly | 4.8 | Weld Visual Of Nozzle To Shell & Dished End (M1/N1/N2/N3/N4/N5/N6) | P | R |  |  |  | Pending
320SR02 | H. Nozzle & Manway Sub-Assembly | 4.8 | Ultrasonic Test Of Nozzle To Shell & Dished End (M1/N1/N2/N3) | P | R |  |  |  | Pending
320SR02 | I. Final Closure Gate | 4.9 | Clearance Of Shell Before Closing Dished End Set Up | P | R |  |  |  | Pending
320SR02 | J. Shell + Top Head (CS-1) | 4.10 | Top Dished End To Shell Set Up (Cs- 1) | P | R |  |  |  | Pending
320SR02 | J. Shell + Top Head (CS-1) | 4.10 | Weld Circ Seam Of Top Dishend To Shell (Cs-1) | P | R |  |  |  | Pending
320SR02 | J. Shell + Top Head (CS-1) | 4.10 | Weld Visual Of Cs -1 | P | R |  |  |  | Pending
320SR02 | J. Shell + Top Head (CS-1) | 4.10 | Paut/Tofd Of Cs-1 | P | W |  |  |  | Pending
320SR02 | K. Attachments Sub-Assembly | 4.11 | Lifting Lug & Name Plate Bracket Set Up | P | R |  |  |  | Pending
320SR02 | K. Attachments Sub-Assembly | 4.12 | Weld Of Lifting Lug | P | R |  |  |  | Pending
320SR02 | K. Attachments Sub-Assembly | 4.12 | Weld Of Name Plate Bracket | P | R |  |  |  | Pending
320SR02 | L. Skirt Sub-Assembly | 4.13 | Skirt Support Set Up | P | R |  |  |  | Pending
320SR02 | L. Skirt Sub-Assembly | 4.14 | Weld Skirt Support | P | R |  |  |  | Pending
320SR02 | M. Pre-PWHT Gate | 4.15 | Clearance Befor Pwht | P | W |  |  |  | Pending
320SR02 | N. Heat Treatment & Post-PWHT NDT | 5.1 | Inspection Of Vessel Heat Treatment | R | R |  |  |  | Pending
320SR02 | N. Heat Treatment & Post-PWHT NDT | 5.2 | Weld Visual Of All Weld Joints | P | W |  |  |  | Pending
320SR02 | N. Heat Treatment & Post-PWHT NDT | 5.3 | Mpt Of All Weld Joint | P | W |  |  |  | Pending
320SR02 | N. Heat Treatment & Post-PWHT NDT | 5.4 | Rt Testing On All Butt Weld Joints(M1/N2/N3) Paut/Tofd For L'Seam & C'Seam Joints. (After Pwht). | P | W |  |  |  | Pending
320SR02 | O. Hydrostatic Test | 6.1 | Clearance For Hydrostatic Test | P | R |  |  |  | Pending
320SR02 | O. Hydrostatic Test | 6.2 | Before Hydrostatic Test Clearance | P | R |  |  |  | Pending
320SR02 | O. Hydrostatic Test | 6.3 | Hydrostatic Test | P | W |  |  |  | Pending
320SR02 | O. Hydrostatic Test | 6.4 | Mpt / Lpt All Weld Joints After Hydro Test | P | W |  |  |  | Pending
320SR02 | P. Surface Treatment & Painting | 7.1 | Cleaning & Surface Preparation | P | R |  |  |  | Pending
320SR02 | P. Surface Treatment & Painting | 7.2 | Painting | P | W |  |  |  | Pending
320SR02 | Q. Final Inspection, Nameplate & MDR | 8.1 | Verification Of Name Plate | P | R |  |  |  | Pending
320SR02 | Q. Final Inspection, Nameplate & MDR | 8.2 | Attachment Of Name Plate To Name Plate Bracket | P | R |  |  |  | Pending
320SR02 | Q. Final Inspection, Nameplate & MDR | 9.1 | Documentation | R | R |  |  |  | Pending
320SR03 | A. Document & Procedure Gate | 1.1 | Drawing Approval | P | R |  |  |  | Pending
320SR03 | A. Document & Procedure Gate | 1.2 | Review And Approval Of Quality Contol Plan | P | R |  |  |  | Pending
320SR03 | A. Document & Procedure Gate | 1.3 | Hot Forming Proceude, Ht Procedure, Rt Procedure, Pt Procedure, Paut & Tofd Procedure | H | R |  |  |  | Pending
320SR03 | A. Document & Procedure Gate | 2.1 | Welding Procedure & Performance Qualification | P | R |  |  |  | Pending
320SR03 | B. Material Inspection & Traceability | 3.1 | Pressure Part - Plates,Pipes/Forgings/Flange/ Fittings | H | W |  |  |  | Pending
320SR03 | B. Material Inspection & Traceability | 3.2 | Non Pressure Parts & Attachment To Pressure Parts | H | R |  |  |  | Pending
320SR03 | B. Material Inspection & Traceability | 3.3 | Welding Consumable | R | R |  |  |  | Pending
320SR03 | B. Material Inspection & Traceability | 3.4 | Weld Plan/Weld Map | P | R |  |  |  | Pending
320SR03 | C. Shell & Head Prep | 4.1 | Transfer Of Marking And Cutting (Shell And Dished End) | H | R |  |  |  | Pending
320SR03 | D. Head Sub-Assembly | 4.2 | Inspection Of Top & Bottom Dished | R | R |  |  |  | Pending
320SR03 | D. Head Sub-Assembly | 4.2 | Simulation Heat Treatment Of Test Coupon After Forming & Testing | R | R |  |  |  | Pending
320SR03 | D. Head Sub-Assembly | 4.4 | Weld Edge Preparation Of Top & Bottom Dished End | P | R |  |  |  | Pending
320SR03 | E. Shell Sub-Assembly (LS-1) | 4.5 | Shell Weld Edge Preparation | P | R |  |  |  | Pending
320SR03 | E. Shell Sub-Assembly (LS-1) | 4.5 | L' Seam Set Up Of Shell (Ls-1 ) Along With Ptc | P | R |  |  |  | Pending
320SR03 | E. Shell Sub-Assembly (LS-1) | 4.5 | Weld Long Seam Of Shell (Ls-1 ) | P | R |  |  |  | Pending
320SR03 | E. Shell Sub-Assembly (LS-1) | 4.5 | Weld Visual Of Ls-1 | P | R |  |  |  | Pending
320SR03 | E. Shell Sub-Assembly (LS-1) | 4.5 | Paut/Tofd Of Ls-1 | P | W |  |  |  | Pending
320SR03 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Nozzle To Flange/Elbow Set Up (M1/N2/N3) | P | R |  |  |  | Pending
320SR03 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Weld Of Nozzle To Flange/Elbow (M1/N2/N3) | P | R |  |  |  | Pending
320SR03 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Weld Visual Of Cs Joint Nozzle M1/N2/N3 | P | R |  |  |  | Pending
320SR03 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Rt Circ Seam Of Nozzle Pipe To Flange (M1/N2/N3) | P | R |  |  |  | Pending
320SR03 | G. Shell + Bottom Head (CS-2) | 4.7 | Bottom Dished End To Shell Set Up (Cs-2) | P | R |  |  |  | Pending
320SR03 | G. Shell + Bottom Head (CS-2) | 4.7 | Weld Circ Seam Of Bottom Dishend To Shell (Cs-2) | P | R |  |  |  | Pending
320SR03 | G. Shell + Bottom Head (CS-2) | 4.7 | Weld Visual Of Cs -2 | P | R |  |  |  | Pending
320SR03 | G. Shell + Bottom Head (CS-2) | 4.7 | Paut/Tofd Of Cs-2 | P | W |  |  |  | Pending
320SR03 | H. Nozzle & Manway Sub-Assembly | 4.8 | Marking For Nozzle On Shell And Dished End (M1, N1 To N6) | P | R |  |  |  | Pending
320SR03 | H. Nozzle & Manway Sub-Assembly | 4.8 | Nozzle To Shell & Dished End Set Up (M1/N1/N2/N3/N4/N5/N6) | P | R |  |  |  | Pending
320SR03 | H. Nozzle & Manway Sub-Assembly | 4.8 | Weld Of Nozzle To Shell & Dished End (M1/N1/N2/N3/N4/N5/N6) | P | R |  |  |  | Pending
320SR03 | H. Nozzle & Manway Sub-Assembly | 4.8 | Weld Visual Of Nozzle To Shell & Dished End (M1/N1/N2/N3/N4/N5/N6) | P | R |  |  |  | Pending
320SR03 | H. Nozzle & Manway Sub-Assembly | 4.8 | Ultrasonic Test Of Nozzle To Shell & Dished End (M1/N1/N2/N3) | P | R |  |  |  | Pending
320SR03 | I. Final Closure Gate | 4.9 | Clearance Of Shell Before Closing Dished End Set Up | P | R |  |  |  | Pending
320SR03 | J. Shell + Top Head (CS-1) | 4.10 | Top Dished End To Shell Set Up (Cs- 1) | P | R |  |  |  | Pending
320SR03 | J. Shell + Top Head (CS-1) | 4.10 | Weld Circ Seam Of Top Dishend To Shell (Cs-1) | P | R |  |  |  | Pending
320SR03 | J. Shell + Top Head (CS-1) | 4.10 | Weld Visual Of Cs -1 | P | R |  |  |  | Pending
320SR03 | J. Shell + Top Head (CS-1) | 4.10 | Paut/Tofd Of Cs-1 | P | W |  |  |  | Pending
320SR03 | K. Attachments Sub-Assembly | 4.11 | Lifting Lug & Name Plate Bracket Set Up | P | R |  |  |  | Pending
320SR03 | K. Attachments Sub-Assembly | 4.12 | Weld Of Lifting Lug | P | R |  |  |  | Pending
320SR03 | K. Attachments Sub-Assembly | 4.12 | Weld Of Name Plate Bracket | P | R |  |  |  | Pending
320SR03 | L. Skirt Sub-Assembly | 4.13 | Skirt Support Set Up | P | R |  |  |  | Pending
320SR03 | L. Skirt Sub-Assembly | 4.14 | Weld Skirt Support | P | R |  |  |  | Pending
320SR03 | M. Pre-PWHT Gate | 4.15 | Clearance Befor Pwht | P | W |  |  |  | Pending
320SR03 | N. Heat Treatment & Post-PWHT NDT | 5.1 | Inspection Of Vessel Heat Treatment | R | R |  |  |  | Pending
320SR03 | N. Heat Treatment & Post-PWHT NDT | 5.2 | Weld Visual Of All Weld Joints | P | W |  |  |  | Pending
320SR03 | N. Heat Treatment & Post-PWHT NDT | 5.3 | Mpt Of All Weld Joint | P | W |  |  |  | Pending
320SR03 | N. Heat Treatment & Post-PWHT NDT | 5.4 | Rt Testing On All Butt Weld Joints(M1/N2/N3) Paut/Tofd For L'Seam & C'Seam Joints. (After Pwht). | P | W |  |  |  | Pending
320SR03 | O. Hydrostatic Test | 6.1 | Clearance For Hydrostatic Test | P | R |  |  |  | Pending
320SR03 | O. Hydrostatic Test | 6.2 | Before Hydrostatic Test Clearance | P | R |  |  |  | Pending
320SR03 | O. Hydrostatic Test | 6.3 | Hydrostatic Test | P | W |  |  |  | Pending
320SR03 | O. Hydrostatic Test | 6.4 | Mpt / Lpt All Weld Joints After Hydro Test | P | W |  |  |  | Pending
320SR03 | P. Surface Treatment & Painting | 7.1 | Cleaning & Surface Preparation | P | R |  |  |  | Pending
320SR03 | P. Surface Treatment & Painting | 7.2 | Painting | P | W |  |  |  | Pending
320SR03 | Q. Final Inspection, Nameplate & MDR | 8.1 | Verification Of Name Plate | P | R |  |  |  | Pending
320SR03 | Q. Final Inspection, Nameplate & MDR | 8.2 | Attachment Of Name Plate To Name Plate Bracket | P | R |  |  |  | Pending
320SR03 | Q. Final Inspection, Nameplate & MDR | 9.1 | Documentation | R | R |  |  |  | Pending
320SR04 | A. Document & Procedure Gate | 1.1 | Drawing Approval | P | R |  |  |  | Pending
320SR04 | A. Document & Procedure Gate | 1.2 | Review And Approval Of Quality Contol Plan | P | R |  |  |  | Pending
320SR04 | A. Document & Procedure Gate | 1.3 | Hot Forming Proceude, Ht Procedure, Rt Procedure, Pt Procedure, Paut & Tofd Procedure | H | R |  |  |  | Pending
320SR04 | A. Document & Procedure Gate | 2.1 | Welding Procedure & Performance Qualification | P | R |  |  |  | Pending
320SR04 | B. Material Inspection & Traceability | 3.1 | Pressure Part - Plates,Pipes/Forgings/Flange/ Fittings | H | W |  |  |  | Pending
320SR04 | B. Material Inspection & Traceability | 3.2 | Non Pressure Parts & Attachment To Pressure Parts | H | R |  |  |  | Pending
320SR04 | B. Material Inspection & Traceability | 3.3 | Welding Consumable | R | R |  |  |  | Pending
320SR04 | B. Material Inspection & Traceability | 3.4 | Weld Plan/Weld Map | P | R |  |  |  | Pending
320SR04 | C. Shell & Head Prep | 4.1 | Transfer Of Marking And Cutting (Shell And Dished End) | H | R |  |  |  | Pending
320SR04 | D. Head Sub-Assembly | 4.2 | Inspection Of Top & Bottom Dished | R | R |  |  |  | Pending
320SR04 | D. Head Sub-Assembly | 4.2 | Simulation Heat Treatment Of Test Coupon After Forming & Testing | R | R |  |  |  | Pending
320SR04 | D. Head Sub-Assembly | 4.4 | Weld Edge Preparation Of Top & Bottom Dished End | P | R |  |  |  | Pending
320SR04 | E. Shell Sub-Assembly (LS-1) | 4.5 | Shell Weld Edge Preparation | P | R |  |  |  | Pending
320SR04 | E. Shell Sub-Assembly (LS-1) | 4.5 | L' Seam Set Up Of Shell (Ls-1 ) Along With Ptc | P | R |  |  |  | Pending
320SR04 | E. Shell Sub-Assembly (LS-1) | 4.5 | Weld Long Seam Of Shell (Ls-1 ) | P | R |  |  |  | Pending
320SR04 | E. Shell Sub-Assembly (LS-1) | 4.5 | Weld Visual Of Ls-1 | P | R |  |  |  | Pending
320SR04 | E. Shell Sub-Assembly (LS-1) | 4.5 | Paut/Tofd Of Ls-1 | P | W |  |  |  | Pending
320SR04 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Nozzle To Flange/Elbow Set Up (M1/N2/N3) | P | R |  |  |  | Pending
320SR04 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Weld Of Nozzle To Flange/Elbow (M1/N2/N3) | P | R |  |  |  | Pending
320SR04 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Weld Visual Of Cs Joint Nozzle M1/N2/N3 | P | R |  |  |  | Pending
320SR04 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Rt Circ Seam Of Nozzle Pipe To Flange (M1/N2/N3) | P | R |  |  |  | Pending
320SR04 | G. Shell + Bottom Head (CS-2) | 4.7 | Bottom Dished End To Shell Set Up (Cs-2) | P | R |  |  |  | Pending
320SR04 | G. Shell + Bottom Head (CS-2) | 4.7 | Weld Circ Seam Of Bottom Dishend To Shell (Cs-2) | P | R |  |  |  | Pending
320SR04 | G. Shell + Bottom Head (CS-2) | 4.7 | Weld Visual Of Cs -2 | P | R |  |  |  | Pending
320SR04 | G. Shell + Bottom Head (CS-2) | 4.7 | Paut/Tofd Of Cs-2 | P | W |  |  |  | Pending
320SR04 | H. Nozzle & Manway Sub-Assembly | 4.8 | Marking For Nozzle On Shell And Dished End (M1, N1 To N6) | P | R |  |  |  | Pending
320SR04 | H. Nozzle & Manway Sub-Assembly | 4.8 | Nozzle To Shell & Dished End Set Up (M1/N1/N2/N3/N4/N5/N6) | P | R |  |  |  | Pending
320SR04 | H. Nozzle & Manway Sub-Assembly | 4.8 | Weld Of Nozzle To Shell & Dished End (M1/N1/N2/N3/N4/N5/N6) | P | R |  |  |  | Pending
320SR04 | H. Nozzle & Manway Sub-Assembly | 4.8 | Weld Visual Of Nozzle To Shell & Dished End (M1/N1/N2/N3/N4/N5/N6) | P | R |  |  |  | Pending
320SR04 | H. Nozzle & Manway Sub-Assembly | 4.8 | Ultrasonic Test Of Nozzle To Shell & Dished End (M1/N1/N2/N3) | P | R |  |  |  | Pending
320SR04 | I. Final Closure Gate | 4.9 | Clearance Of Shell Before Closing Dished End Set Up | P | R |  |  |  | Pending
320SR04 | J. Shell + Top Head (CS-1) | 4.10 | Top Dished End To Shell Set Up (Cs- 1) | P | R |  |  |  | Pending
320SR04 | J. Shell + Top Head (CS-1) | 4.10 | Weld Circ Seam Of Top Dishend To Shell (Cs-1) | P | R |  |  |  | Pending
320SR04 | J. Shell + Top Head (CS-1) | 4.10 | Weld Visual Of Cs -1 | P | R |  |  |  | Pending
320SR04 | J. Shell + Top Head (CS-1) | 4.10 | Paut/Tofd Of Cs-1 | P | W |  |  |  | Pending
320SR04 | K. Attachments Sub-Assembly | 4.11 | Lifting Lug & Name Plate Bracket Set Up | P | R |  |  |  | Pending
320SR04 | K. Attachments Sub-Assembly | 4.12 | Weld Of Lifting Lug | P | R |  |  |  | Pending
320SR04 | K. Attachments Sub-Assembly | 4.12 | Weld Of Name Plate Bracket | P | R |  |  |  | Pending
320SR04 | L. Skirt Sub-Assembly | 4.13 | Skirt Support Set Up | P | R |  |  |  | Pending
320SR04 | L. Skirt Sub-Assembly | 4.14 | Weld Skirt Support | P | R |  |  |  | Pending
320SR04 | M. Pre-PWHT Gate | 4.15 | Clearance Befor Pwht | P | W |  |  |  | Pending
320SR04 | N. Heat Treatment & Post-PWHT NDT | 5.1 | Inspection Of Vessel Heat Treatment | R | R |  |  |  | Pending
320SR04 | N. Heat Treatment & Post-PWHT NDT | 5.2 | Weld Visual Of All Weld Joints | P | W |  |  |  | Pending
320SR04 | N. Heat Treatment & Post-PWHT NDT | 5.3 | Mpt Of All Weld Joint | P | W |  |  |  | Pending
320SR04 | N. Heat Treatment & Post-PWHT NDT | 5.4 | Rt Testing On All Butt Weld Joints(M1/N2/N3) Paut/Tofd For L'Seam & C'Seam Joints. (After Pwht). | P | W |  |  |  | Pending
320SR04 | O. Hydrostatic Test | 6.1 | Clearance For Hydrostatic Test | P | R |  |  |  | Pending
320SR04 | O. Hydrostatic Test | 6.2 | Before Hydrostatic Test Clearance | P | R |  |  |  | Pending
320SR04 | O. Hydrostatic Test | 6.3 | Hydrostatic Test | P | W |  |  |  | Pending
320SR04 | O. Hydrostatic Test | 6.4 | Mpt / Lpt All Weld Joints After Hydro Test | P | W |  |  |  | Pending
320SR04 | P. Surface Treatment & Painting | 7.1 | Cleaning & Surface Preparation | P | R |  |  |  | Pending
320SR04 | P. Surface Treatment & Painting | 7.2 | Painting | P | W |  |  |  | Pending
320SR04 | Q. Final Inspection, Nameplate & MDR | 8.1 | Verification Of Name Plate | P | R |  |  |  | Pending
320SR04 | Q. Final Inspection, Nameplate & MDR | 8.2 | Attachment Of Name Plate To Name Plate Bracket | P | R |  |  |  | Pending
320SR04 | Q. Final Inspection, Nameplate & MDR | 9.1 | Documentation | R | R |  |  |  | Pending
320SR05 | A. Document & Procedure Gate | 1.1 | Drawing Approval | P | R |  |  |  | Pending
320SR05 | A. Document & Procedure Gate | 1.2 | Review And Approval Of Quality Contol Plan | P | R |  |  |  | Pending
320SR05 | A. Document & Procedure Gate | 1.3 | Hot Forming Proceude, Ht Procedure, Rt Procedure, Pt Procedure, Paut & Tofd Procedure | H | R |  |  |  | Pending
320SR05 | A. Document & Procedure Gate | 2.1 | Welding Procedure & Performance Qualification | P | R |  |  |  | Pending
320SR05 | B. Material Inspection & Traceability | 3.1 | Pressure Part - Plates,Pipes/Forgings/Flange/ Fittings | H | W |  |  |  | Pending
320SR05 | B. Material Inspection & Traceability | 3.2 | Non Pressure Parts & Attachment To Pressure Parts | H | R |  |  |  | Pending
320SR05 | B. Material Inspection & Traceability | 3.3 | Welding Consumable | R | R |  |  |  | Pending
320SR05 | B. Material Inspection & Traceability | 3.4 | Weld Plan/Weld Map | P | R |  |  |  | Pending
320SR05 | C. Shell & Head Prep | 4.1 | Transfer Of Marking And Cutting (Shell And Dished End) | H | R |  |  |  | Pending
320SR05 | D. Head Sub-Assembly | 4.2 | Inspection Of Top & Bottom Dished | R | R |  |  |  | Pending
320SR05 | D. Head Sub-Assembly | 4.2 | Simulation Heat Treatment Of Test Coupon After Forming & Testing | R | R |  |  |  | Pending
320SR05 | D. Head Sub-Assembly | 4.4 | Weld Edge Preparation Of Top & Bottom Dished End | P | R |  |  |  | Pending
320SR05 | E. Shell Sub-Assembly (LS-1) | 4.5 | Shell Weld Edge Preparation | P | R |  |  |  | Pending
320SR05 | E. Shell Sub-Assembly (LS-1) | 4.5 | L' Seam Set Up Of Shell (Ls-1 ) Along With Ptc | P | R |  |  |  | Pending
320SR05 | E. Shell Sub-Assembly (LS-1) | 4.5 | Weld Long Seam Of Shell (Ls-1 ) | P | R |  |  |  | Pending
320SR05 | E. Shell Sub-Assembly (LS-1) | 4.5 | Weld Visual Of Ls-1 | P | R |  |  |  | Pending
320SR05 | E. Shell Sub-Assembly (LS-1) | 4.5 | Paut/Tofd Of Ls-1 | P | W |  |  |  | Pending
320SR05 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Nozzle To Flange/Elbow Set Up (M1/N2/N3) | P | R |  |  |  | Pending
320SR05 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Weld Of Nozzle To Flange/Elbow (M1/N2/N3) | P | R |  |  |  | Pending
320SR05 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Weld Visual Of Cs Joint Nozzle M1/N2/N3 | P | R |  |  |  | Pending
320SR05 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Rt Circ Seam Of Nozzle Pipe To Flange (M1/N2/N3) | P | R |  |  |  | Pending
320SR05 | G. Shell + Bottom Head (CS-2) | 4.7 | Bottom Dished End To Shell Set Up (Cs-2) | P | R |  |  |  | Pending
320SR05 | G. Shell + Bottom Head (CS-2) | 4.7 | Weld Circ Seam Of Bottom Dishend To Shell (Cs-2) | P | R |  |  |  | Pending
320SR05 | G. Shell + Bottom Head (CS-2) | 4.7 | Weld Visual Of Cs -2 | P | R |  |  |  | Pending
320SR05 | G. Shell + Bottom Head (CS-2) | 4.7 | Paut/Tofd Of Cs-2 | P | W |  |  |  | Pending
320SR05 | H. Nozzle & Manway Sub-Assembly | 4.8 | Marking For Nozzle On Shell And Dished End (M1, N1 To N6) | P | R |  |  |  | Pending
320SR05 | H. Nozzle & Manway Sub-Assembly | 4.8 | Nozzle To Shell & Dished End Set Up (M1/N1/N2/N3/N4/N5/N6) | P | R |  |  |  | Pending
320SR05 | H. Nozzle & Manway Sub-Assembly | 4.8 | Weld Of Nozzle To Shell & Dished End (M1/N1/N2/N3/N4/N5/N6) | P | R |  |  |  | Pending
320SR05 | H. Nozzle & Manway Sub-Assembly | 4.8 | Weld Visual Of Nozzle To Shell & Dished End (M1/N1/N2/N3/N4/N5/N6) | P | R |  |  |  | Pending
320SR05 | H. Nozzle & Manway Sub-Assembly | 4.8 | Ultrasonic Test Of Nozzle To Shell & Dished End (M1/N1/N2/N3) | P | R |  |  |  | Pending
320SR05 | I. Final Closure Gate | 4.9 | Clearance Of Shell Before Closing Dished End Set Up | P | R |  |  |  | Pending
320SR05 | J. Shell + Top Head (CS-1) | 4.10 | Top Dished End To Shell Set Up (Cs- 1) | P | R |  |  |  | Pending
320SR05 | J. Shell + Top Head (CS-1) | 4.10 | Weld Circ Seam Of Top Dishend To Shell (Cs-1) | P | R |  |  |  | Pending
320SR05 | J. Shell + Top Head (CS-1) | 4.10 | Weld Visual Of Cs -1 | P | R |  |  |  | Pending
320SR05 | J. Shell + Top Head (CS-1) | 4.10 | Paut/Tofd Of Cs-1 | P | W |  |  |  | Pending
320SR05 | K. Attachments Sub-Assembly | 4.11 | Lifting Lug & Name Plate Bracket Set Up | P | R |  |  |  | Pending
320SR05 | K. Attachments Sub-Assembly | 4.12 | Weld Of Lifting Lug | P | R |  |  |  | Pending
320SR05 | K. Attachments Sub-Assembly | 4.12 | Weld Of Name Plate Bracket | P | R |  |  |  | Pending
320SR05 | L. Skirt Sub-Assembly | 4.13 | Skirt Support Set Up | P | R |  |  |  | Pending
320SR05 | L. Skirt Sub-Assembly | 4.14 | Weld Skirt Support | P | R |  |  |  | Pending
320SR05 | M. Pre-PWHT Gate | 4.15 | Clearance Befor Pwht | P | W |  |  |  | Pending
320SR05 | N. Heat Treatment & Post-PWHT NDT | 5.1 | Inspection Of Vessel Heat Treatment | R | R |  |  |  | Pending
320SR05 | N. Heat Treatment & Post-PWHT NDT | 5.2 | Weld Visual Of All Weld Joints | P | W |  |  |  | Pending
320SR05 | N. Heat Treatment & Post-PWHT NDT | 5.3 | Mpt Of All Weld Joint | P | W |  |  |  | Pending
320SR05 | N. Heat Treatment & Post-PWHT NDT | 5.4 | Rt Testing On All Butt Weld Joints(M1/N2/N3) Paut/Tofd For L'Seam & C'Seam Joints. (After Pwht). | P | W |  |  |  | Pending
320SR05 | O. Hydrostatic Test | 6.1 | Clearance For Hydrostatic Test | P | R |  |  |  | Pending
320SR05 | O. Hydrostatic Test | 6.2 | Before Hydrostatic Test Clearance | P | R |  |  |  | Pending
320SR05 | O. Hydrostatic Test | 6.3 | Hydrostatic Test | P | W |  |  |  | Pending
320SR05 | O. Hydrostatic Test | 6.4 | Mpt / Lpt All Weld Joints After Hydro Test | P | W |  |  |  | Pending
320SR05 | P. Surface Treatment & Painting | 7.1 | Cleaning & Surface Preparation | P | R |  |  |  | Pending
320SR05 | P. Surface Treatment & Painting | 7.2 | Painting | P | W |  |  |  | Pending
320SR05 | Q. Final Inspection, Nameplate & MDR | 8.1 | Verification Of Name Plate | P | R |  |  |  | Pending
320SR05 | Q. Final Inspection, Nameplate & MDR | 8.2 | Attachment Of Name Plate To Name Plate Bracket | P | R |  |  |  | Pending
320SR05 | Q. Final Inspection, Nameplate & MDR | 9.1 | Documentation | R | R |  |  |  | Pending
320SR06 | A. Document & Procedure Gate | 1.1 | Drawing Approval | P | R |  |  |  | Pending
320SR06 | A. Document & Procedure Gate | 1.2 | Review And Approval Of Quality Contol Plan | P | R |  |  |  | Pending
320SR06 | A. Document & Procedure Gate | 1.3 | Hot Forming Proceude, Ht Procedure, Rt Procedure, Pt Procedure, Paut & Tofd Procedure | H | R |  |  |  | Pending
320SR06 | A. Document & Procedure Gate | 2.1 | Welding Procedure & Performance Qualification | P | R |  |  |  | Pending
320SR06 | B. Material Inspection & Traceability | 3.1 | Pressure Part - Plates,Pipes/Forgings/Flange/ Fittings | H | W |  |  |  | Pending
320SR06 | B. Material Inspection & Traceability | 3.2 | Non Pressure Parts & Attachment To Pressure Parts | H | R |  |  |  | Pending
320SR06 | B. Material Inspection & Traceability | 3.3 | Welding Consumable | R | R |  |  |  | Pending
320SR06 | B. Material Inspection & Traceability | 3.4 | Weld Plan/Weld Map | P | R |  |  |  | Pending
320SR06 | C. Shell & Head Prep | 4.1 | Transfer Of Marking And Cutting (Shell And Dished End) | H | R |  |  |  | Pending
320SR06 | D. Head Sub-Assembly | 4.2 | Inspection Of Top & Bottom Dished | R | R |  |  |  | Pending
320SR06 | D. Head Sub-Assembly | 4.2 | Simulation Heat Treatment Of Test Coupon After Forming & Testing | R | R |  |  |  | Pending
320SR06 | D. Head Sub-Assembly | 4.4 | Weld Edge Preparation Of Top & Bottom Dished End | P | R |  |  |  | Pending
320SR06 | E. Shell Sub-Assembly (LS-1) | 4.5 | Shell Weld Edge Preparation | P | R |  |  |  | Pending
320SR06 | E. Shell Sub-Assembly (LS-1) | 4.5 | L' Seam Set Up Of Shell (Ls-1 ) Along With Ptc | P | R |  |  |  | Pending
320SR06 | E. Shell Sub-Assembly (LS-1) | 4.5 | Weld Long Seam Of Shell (Ls-1 ) | P | R |  |  |  | Pending
320SR06 | E. Shell Sub-Assembly (LS-1) | 4.5 | Weld Visual Of Ls-1 | P | R |  |  |  | Pending
320SR06 | E. Shell Sub-Assembly (LS-1) | 4.5 | Paut/Tofd Of Ls-1 | P | W |  |  |  | Pending
320SR06 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Nozzle To Flange/Elbow Set Up (M1/N2/N3) | P | R |  |  |  | Pending
320SR06 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Weld Of Nozzle To Flange/Elbow (M1/N2/N3) | P | R |  |  |  | Pending
320SR06 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Weld Visual Of Cs Joint Nozzle M1/N2/N3 | P | R |  |  |  | Pending
320SR06 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Rt Circ Seam Of Nozzle Pipe To Flange (M1/N2/N3) | P | R |  |  |  | Pending
320SR06 | G. Shell + Bottom Head (CS-2) | 4.7 | Bottom Dished End To Shell Set Up (Cs-2) | P | R |  |  |  | Pending
320SR06 | G. Shell + Bottom Head (CS-2) | 4.7 | Weld Circ Seam Of Bottom Dishend To Shell (Cs-2) | P | R |  |  |  | Pending
320SR06 | G. Shell + Bottom Head (CS-2) | 4.7 | Weld Visual Of Cs -2 | P | R |  |  |  | Pending
320SR06 | G. Shell + Bottom Head (CS-2) | 4.7 | Paut/Tofd Of Cs-2 | P | W |  |  |  | Pending
320SR06 | H. Nozzle & Manway Sub-Assembly | 4.8 | Marking For Nozzle On Shell And Dished End (M1, N1 To N6) | P | R |  |  |  | Pending
320SR06 | H. Nozzle & Manway Sub-Assembly | 4.8 | Nozzle To Shell & Dished End Set Up (M1/N1/N2/N3/N4/N5/N6) | P | R |  |  |  | Pending
320SR06 | H. Nozzle & Manway Sub-Assembly | 4.8 | Weld Of Nozzle To Shell & Dished End (M1/N1/N2/N3/N4/N5/N6) | P | R |  |  |  | Pending
320SR06 | H. Nozzle & Manway Sub-Assembly | 4.8 | Weld Visual Of Nozzle To Shell & Dished End (M1/N1/N2/N3/N4/N5/N6) | P | R |  |  |  | Pending
320SR06 | H. Nozzle & Manway Sub-Assembly | 4.8 | Ultrasonic Test Of Nozzle To Shell & Dished End (M1/N1/N2/N3) | P | R |  |  |  | Pending
320SR06 | I. Final Closure Gate | 4.9 | Clearance Of Shell Before Closing Dished End Set Up | P | R |  |  |  | Pending
320SR06 | J. Shell + Top Head (CS-1) | 4.10 | Top Dished End To Shell Set Up (Cs- 1) | P | R |  |  |  | Pending
320SR06 | J. Shell + Top Head (CS-1) | 4.10 | Weld Circ Seam Of Top Dishend To Shell (Cs-1) | P | R |  |  |  | Pending
320SR06 | J. Shell + Top Head (CS-1) | 4.10 | Weld Visual Of Cs -1 | P | R |  |  |  | Pending
320SR06 | J. Shell + Top Head (CS-1) | 4.10 | Paut/Tofd Of Cs-1 | P | W |  |  |  | Pending
320SR06 | K. Attachments Sub-Assembly | 4.11 | Lifting Lug & Name Plate Bracket Set Up | P | R |  |  |  | Pending
320SR06 | K. Attachments Sub-Assembly | 4.12 | Weld Of Lifting Lug | P | R |  |  |  | Pending
320SR06 | K. Attachments Sub-Assembly | 4.12 | Weld Of Name Plate Bracket | P | R |  |  |  | Pending
320SR06 | L. Skirt Sub-Assembly | 4.13 | Skirt Support Set Up | P | R |  |  |  | Pending
320SR06 | L. Skirt Sub-Assembly | 4.14 | Weld Skirt Support | P | R |  |  |  | Pending
320SR06 | M. Pre-PWHT Gate | 4.15 | Clearance Befor Pwht | P | W |  |  |  | Pending
320SR06 | N. Heat Treatment & Post-PWHT NDT | 5.1 | Inspection Of Vessel Heat Treatment | R | R |  |  |  | Pending
320SR06 | N. Heat Treatment & Post-PWHT NDT | 5.2 | Weld Visual Of All Weld Joints | P | W |  |  |  | Pending
320SR06 | N. Heat Treatment & Post-PWHT NDT | 5.3 | Mpt Of All Weld Joint | P | W |  |  |  | Pending
320SR06 | N. Heat Treatment & Post-PWHT NDT | 5.4 | Rt Testing On All Butt Weld Joints(M1/N2/N3) Paut/Tofd For L'Seam & C'Seam Joints. (After Pwht). | P | W |  |  |  | Pending
320SR06 | O. Hydrostatic Test | 6.1 | Clearance For Hydrostatic Test | P | R |  |  |  | Pending
320SR06 | O. Hydrostatic Test | 6.2 | Before Hydrostatic Test Clearance | P | R |  |  |  | Pending
320SR06 | O. Hydrostatic Test | 6.3 | Hydrostatic Test | P | W |  |  |  | Pending
320SR06 | O. Hydrostatic Test | 6.4 | Mpt / Lpt All Weld Joints After Hydro Test | P | W |  |  |  | Pending
320SR06 | P. Surface Treatment & Painting | 7.1 | Cleaning & Surface Preparation | P | R |  |  |  | Pending
320SR06 | P. Surface Treatment & Painting | 7.2 | Painting | P | W |  |  |  | Pending
320SR06 | Q. Final Inspection, Nameplate & MDR | 8.1 | Verification Of Name Plate | P | R |  |  |  | Pending
320SR06 | Q. Final Inspection, Nameplate & MDR | 8.2 | Attachment Of Name Plate To Name Plate Bracket | P | R |  |  |  | Pending
320SR06 | Q. Final Inspection, Nameplate & MDR | 9.1 | Documentation | R | R |  |  |  | Pending
320SR07 | A. Document & Procedure Gate | 1.1 | Drawing Approval | P | R |  |  |  | Pending
320SR07 | A. Document & Procedure Gate | 1.2 | Review And Approval Of Quality Contol Plan | P | R |  |  |  | Pending
320SR07 | A. Document & Procedure Gate | 1.3 | Hot Forming Proceude, Ht Procedure, Rt Procedure, Pt Procedure, Paut & Tofd Procedure | H | R |  |  |  | Pending
320SR07 | A. Document & Procedure Gate | 2.1 | Welding Procedure & Performance Qualification | P | R |  |  |  | Pending
320SR07 | B. Material Inspection & Traceability | 3.1 | Pressure Part - Plates,Pipes/Forgings/Flange/ Fittings | H | W |  |  |  | Pending
320SR07 | B. Material Inspection & Traceability | 3.2 | Non Pressure Parts & Attachment To Pressure Parts | H | R |  |  |  | Pending
320SR07 | B. Material Inspection & Traceability | 3.3 | Welding Consumable | R | R |  |  |  | Pending
320SR07 | B. Material Inspection & Traceability | 3.4 | Weld Plan/Weld Map | P | R |  |  |  | Pending
320SR07 | C. Shell & Head Prep | 4.1 | Transfer Of Marking And Cutting (Shell And Dished End) | H | R |  |  |  | Pending
320SR07 | D. Head Sub-Assembly | 4.2 | Inspection Of Top & Bottom Dished | R | R |  |  |  | Pending
320SR07 | D. Head Sub-Assembly | 4.2 | Simulation Heat Treatment Of Test Coupon After Forming & Testing | R | R |  |  |  | Pending
320SR07 | D. Head Sub-Assembly | 4.4 | Weld Edge Preparation Of Top & Bottom Dished End | P | R |  |  |  | Pending
320SR07 | E. Shell Sub-Assembly (LS-1) | 4.5 | Shell Weld Edge Preparation | P | R |  |  |  | Pending
320SR07 | E. Shell Sub-Assembly (LS-1) | 4.5 | L' Seam Set Up Of Shell (Ls-1 ) Along With Ptc | P | R |  |  |  | Pending
320SR07 | E. Shell Sub-Assembly (LS-1) | 4.5 | Weld Long Seam Of Shell (Ls-1 ) | P | R |  |  |  | Pending
320SR07 | E. Shell Sub-Assembly (LS-1) | 4.5 | Weld Visual Of Ls-1 | P | R |  |  |  | Pending
320SR07 | E. Shell Sub-Assembly (LS-1) | 4.5 | Paut/Tofd Of Ls-1 | P | W |  |  |  | Pending
320SR07 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Nozzle To Flange/Elbow Set Up (M1/N2/N3) | P | R |  |  |  | Pending
320SR07 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Weld Of Nozzle To Flange/Elbow (M1/N2/N3) | P | R |  |  |  | Pending
320SR07 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Weld Visual Of Cs Joint Nozzle M1/N2/N3 | P | R |  |  |  | Pending
320SR07 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Rt Circ Seam Of Nozzle Pipe To Flange (M1/N2/N3) | P | R |  |  |  | Pending
320SR07 | G. Shell + Bottom Head (CS-2) | 4.7 | Bottom Dished End To Shell Set Up (Cs-2) | P | R |  |  |  | Pending
320SR07 | G. Shell + Bottom Head (CS-2) | 4.7 | Weld Circ Seam Of Bottom Dishend To Shell (Cs-2) | P | R |  |  |  | Pending
320SR07 | G. Shell + Bottom Head (CS-2) | 4.7 | Weld Visual Of Cs -2 | P | R |  |  |  | Pending
320SR07 | G. Shell + Bottom Head (CS-2) | 4.7 | Paut/Tofd Of Cs-2 | P | W |  |  |  | Pending
320SR07 | H. Nozzle & Manway Sub-Assembly | 4.8 | Marking For Nozzle On Shell And Dished End (M1, N1 To N6) | P | R |  |  |  | Pending
320SR07 | H. Nozzle & Manway Sub-Assembly | 4.8 | Nozzle To Shell & Dished End Set Up (M1/N1/N2/N3/N4/N5/N6) | P | R |  |  |  | Pending
320SR07 | H. Nozzle & Manway Sub-Assembly | 4.8 | Weld Of Nozzle To Shell & Dished End (M1/N1/N2/N3/N4/N5/N6) | P | R |  |  |  | Pending
320SR07 | H. Nozzle & Manway Sub-Assembly | 4.8 | Weld Visual Of Nozzle To Shell & Dished End (M1/N1/N2/N3/N4/N5/N6) | P | R |  |  |  | Pending
320SR07 | H. Nozzle & Manway Sub-Assembly | 4.8 | Ultrasonic Test Of Nozzle To Shell & Dished End (M1/N1/N2/N3) | P | R |  |  |  | Pending
320SR07 | I. Final Closure Gate | 4.9 | Clearance Of Shell Before Closing Dished End Set Up | P | R |  |  |  | Pending
320SR07 | J. Shell + Top Head (CS-1) | 4.10 | Top Dished End To Shell Set Up (Cs- 1) | P | R |  |  |  | Pending
320SR07 | J. Shell + Top Head (CS-1) | 4.10 | Weld Circ Seam Of Top Dishend To Shell (Cs-1) | P | R |  |  |  | Pending
320SR07 | J. Shell + Top Head (CS-1) | 4.10 | Weld Visual Of Cs -1 | P | R |  |  |  | Pending
320SR07 | J. Shell + Top Head (CS-1) | 4.10 | Paut/Tofd Of Cs-1 | P | W |  |  |  | Pending
320SR07 | K. Attachments Sub-Assembly | 4.11 | Lifting Lug & Name Plate Bracket Set Up | P | R |  |  |  | Pending
320SR07 | K. Attachments Sub-Assembly | 4.12 | Weld Of Lifting Lug | P | R |  |  |  | Pending
320SR07 | K. Attachments Sub-Assembly | 4.12 | Weld Of Name Plate Bracket | P | R |  |  |  | Pending
320SR07 | L. Skirt Sub-Assembly | 4.13 | Skirt Support Set Up | P | R |  |  |  | Pending
320SR07 | L. Skirt Sub-Assembly | 4.14 | Weld Skirt Support | P | R |  |  |  | Pending
320SR07 | M. Pre-PWHT Gate | 4.15 | Clearance Befor Pwht | P | W |  |  |  | Pending
320SR07 | N. Heat Treatment & Post-PWHT NDT | 5.1 | Inspection Of Vessel Heat Treatment | R | R |  |  |  | Pending
320SR07 | N. Heat Treatment & Post-PWHT NDT | 5.2 | Weld Visual Of All Weld Joints | P | W |  |  |  | Pending
320SR07 | N. Heat Treatment & Post-PWHT NDT | 5.3 | Mpt Of All Weld Joint | P | W |  |  |  | Pending
320SR07 | N. Heat Treatment & Post-PWHT NDT | 5.4 | Rt Testing On All Butt Weld Joints(M1/N2/N3) Paut/Tofd For L'Seam & C'Seam Joints. (After Pwht). | P | W |  |  |  | Pending
320SR07 | O. Hydrostatic Test | 6.1 | Clearance For Hydrostatic Test | P | R |  |  |  | Pending
320SR07 | O. Hydrostatic Test | 6.2 | Before Hydrostatic Test Clearance | P | R |  |  |  | Pending
320SR07 | O. Hydrostatic Test | 6.3 | Hydrostatic Test | P | W |  |  |  | Pending
320SR07 | O. Hydrostatic Test | 6.4 | Mpt / Lpt All Weld Joints After Hydro Test | P | W |  |  |  | Pending
320SR07 | P. Surface Treatment & Painting | 7.1 | Cleaning & Surface Preparation | P | R |  |  |  | Pending
320SR07 | P. Surface Treatment & Painting | 7.2 | Painting | P | W |  |  |  | Pending
320SR07 | Q. Final Inspection, Nameplate & MDR | 8.1 | Verification Of Name Plate | P | R |  |  |  | Pending
320SR07 | Q. Final Inspection, Nameplate & MDR | 8.2 | Attachment Of Name Plate To Name Plate Bracket | P | R |  |  |  | Pending
320SR07 | Q. Final Inspection, Nameplate & MDR | 9.1 | Documentation | R | R |  |  |  | Pending
320SR08 | A. Document & Procedure Gate | 1.1 | Drawing Approval | P | R |  |  |  | Pending
320SR08 | A. Document & Procedure Gate | 1.2 | Review And Approval Of Quality Contol Plan | P | R |  |  |  | Pending
320SR08 | A. Document & Procedure Gate | 1.3 | Hot Forming Proceude, Ht Procedure, Rt Procedure, Pt Procedure, Paut & Tofd Procedure | H | R |  |  |  | Pending
320SR08 | A. Document & Procedure Gate | 2.1 | Welding Procedure & Performance Qualification | P | R |  |  |  | Pending
320SR08 | B. Material Inspection & Traceability | 3.1 | Pressure Part - Plates,Pipes/Forgings/Flange/ Fittings | H | W |  |  |  | Pending
320SR08 | B. Material Inspection & Traceability | 3.2 | Non Pressure Parts & Attachment To Pressure Parts | H | R |  |  |  | Pending
320SR08 | B. Material Inspection & Traceability | 3.3 | Welding Consumable | R | R |  |  |  | Pending
320SR08 | B. Material Inspection & Traceability | 3.4 | Weld Plan/Weld Map | P | R |  |  |  | Pending
320SR08 | C. Shell & Head Prep | 4.1 | Transfer Of Marking And Cutting (Shell And Dished End) | H | R |  |  |  | Pending
320SR08 | D. Head Sub-Assembly | 4.2 | Inspection Of Top & Bottom Dished | R | R |  |  |  | Pending
320SR08 | D. Head Sub-Assembly | 4.2 | Simulation Heat Treatment Of Test Coupon After Forming & Testing | R | R |  |  |  | Pending
320SR08 | D. Head Sub-Assembly | 4.4 | Weld Edge Preparation Of Top & Bottom Dished End | P | R |  |  |  | Pending
320SR08 | E. Shell Sub-Assembly (LS-1) | 4.5 | Shell Weld Edge Preparation | P | R |  |  |  | Pending
320SR08 | E. Shell Sub-Assembly (LS-1) | 4.5 | L' Seam Set Up Of Shell (Ls-1 ) Along With Ptc | P | R |  |  |  | Pending
320SR08 | E. Shell Sub-Assembly (LS-1) | 4.5 | Weld Long Seam Of Shell (Ls-1 ) | P | R |  |  |  | Pending
320SR08 | E. Shell Sub-Assembly (LS-1) | 4.5 | Weld Visual Of Ls-1 | P | R |  |  |  | Pending
320SR08 | E. Shell Sub-Assembly (LS-1) | 4.5 | Paut/Tofd Of Ls-1 | P | W |  |  |  | Pending
320SR08 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Nozzle To Flange/Elbow Set Up (M1/N2/N3) | P | R |  |  |  | Pending
320SR08 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Weld Of Nozzle To Flange/Elbow (M1/N2/N3) | P | R |  |  |  | Pending
320SR08 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Weld Visual Of Cs Joint Nozzle M1/N2/N3 | P | R |  |  |  | Pending
320SR08 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Rt Circ Seam Of Nozzle Pipe To Flange (M1/N2/N3) | P | R |  |  |  | Pending
320SR08 | G. Shell + Bottom Head (CS-2) | 4.7 | Bottom Dished End To Shell Set Up (Cs-2) | P | R |  |  |  | Pending
320SR08 | G. Shell + Bottom Head (CS-2) | 4.7 | Weld Circ Seam Of Bottom Dishend To Shell (Cs-2) | P | R |  |  |  | Pending
320SR08 | G. Shell + Bottom Head (CS-2) | 4.7 | Weld Visual Of Cs -2 | P | R |  |  |  | Pending
320SR08 | G. Shell + Bottom Head (CS-2) | 4.7 | Paut/Tofd Of Cs-2 | P | W |  |  |  | Pending
320SR08 | H. Nozzle & Manway Sub-Assembly | 4.8 | Marking For Nozzle On Shell And Dished End (M1, N1 To N6) | P | R |  |  |  | Pending
320SR08 | H. Nozzle & Manway Sub-Assembly | 4.8 | Nozzle To Shell & Dished End Set Up (M1/N1/N2/N3/N4/N5/N6) | P | R |  |  |  | Pending
320SR08 | H. Nozzle & Manway Sub-Assembly | 4.8 | Weld Of Nozzle To Shell & Dished End (M1/N1/N2/N3/N4/N5/N6) | P | R |  |  |  | Pending
320SR08 | H. Nozzle & Manway Sub-Assembly | 4.8 | Weld Visual Of Nozzle To Shell & Dished End (M1/N1/N2/N3/N4/N5/N6) | P | R |  |  |  | Pending
320SR08 | H. Nozzle & Manway Sub-Assembly | 4.8 | Ultrasonic Test Of Nozzle To Shell & Dished End (M1/N1/N2/N3) | P | R |  |  |  | Pending
320SR08 | I. Final Closure Gate | 4.9 | Clearance Of Shell Before Closing Dished End Set Up | P | R |  |  |  | Pending
320SR08 | J. Shell + Top Head (CS-1) | 4.10 | Top Dished End To Shell Set Up (Cs- 1) | P | R |  |  |  | Pending
320SR08 | J. Shell + Top Head (CS-1) | 4.10 | Weld Circ Seam Of Top Dishend To Shell (Cs-1) | P | R |  |  |  | Pending
320SR08 | J. Shell + Top Head (CS-1) | 4.10 | Weld Visual Of Cs -1 | P | R |  |  |  | Pending
320SR08 | J. Shell + Top Head (CS-1) | 4.10 | Paut/Tofd Of Cs-1 | P | W |  |  |  | Pending
320SR08 | K. Attachments Sub-Assembly | 4.11 | Lifting Lug & Name Plate Bracket Set Up | P | R |  |  |  | Pending
320SR08 | K. Attachments Sub-Assembly | 4.12 | Weld Of Lifting Lug | P | R |  |  |  | Pending
320SR08 | K. Attachments Sub-Assembly | 4.12 | Weld Of Name Plate Bracket | P | R |  |  |  | Pending
320SR08 | L. Skirt Sub-Assembly | 4.13 | Skirt Support Set Up | P | R |  |  |  | Pending
320SR08 | L. Skirt Sub-Assembly | 4.14 | Weld Skirt Support | P | R |  |  |  | Pending
320SR08 | M. Pre-PWHT Gate | 4.15 | Clearance Befor Pwht | P | W |  |  |  | Pending
320SR08 | N. Heat Treatment & Post-PWHT NDT | 5.1 | Inspection Of Vessel Heat Treatment | R | R |  |  |  | Pending
320SR08 | N. Heat Treatment & Post-PWHT NDT | 5.2 | Weld Visual Of All Weld Joints | P | W |  |  |  | Pending
320SR08 | N. Heat Treatment & Post-PWHT NDT | 5.3 | Mpt Of All Weld Joint | P | W |  |  |  | Pending
320SR08 | N. Heat Treatment & Post-PWHT NDT | 5.4 | Rt Testing On All Butt Weld Joints(M1/N2/N3) Paut/Tofd For L'Seam & C'Seam Joints. (After Pwht). | P | W |  |  |  | Pending
320SR08 | O. Hydrostatic Test | 6.1 | Clearance For Hydrostatic Test | P | R |  |  |  | Pending
320SR08 | O. Hydrostatic Test | 6.2 | Before Hydrostatic Test Clearance | P | R |  |  |  | Pending
320SR08 | O. Hydrostatic Test | 6.3 | Hydrostatic Test | P | W |  |  |  | Pending
320SR08 | O. Hydrostatic Test | 6.4 | Mpt / Lpt All Weld Joints After Hydro Test | P | W |  |  |  | Pending
320SR08 | P. Surface Treatment & Painting | 7.1 | Cleaning & Surface Preparation | P | R |  |  |  | Pending
320SR08 | P. Surface Treatment & Painting | 7.2 | Painting | P | W |  |  |  | Pending
320SR08 | Q. Final Inspection, Nameplate & MDR | 8.1 | Verification Of Name Plate | P | R |  |  |  | Pending
320SR08 | Q. Final Inspection, Nameplate & MDR | 8.2 | Attachment Of Name Plate To Name Plate Bracket | P | R |  |  |  | Pending
320SR08 | Q. Final Inspection, Nameplate & MDR | 9.1 | Documentation | R | R |  |  |  | Pending
320SR09 | A. Document & Procedure Gate | 1.1 | Drawing Approval | P | R |  |  |  | Pending
320SR09 | A. Document & Procedure Gate | 1.2 | Review And Approval Of Quality Contol Plan | P | R |  |  |  | Pending
320SR09 | A. Document & Procedure Gate | 1.3 | Hot Forming Proceude, Ht Procedure, Rt Procedure, Pt Procedure, Paut & Tofd Procedure | H | R |  |  |  | Pending
320SR09 | A. Document & Procedure Gate | 2.1 | Welding Procedure & Performance Qualification | P | R |  |  |  | Pending
320SR09 | B. Material Inspection & Traceability | 3.1 | Pressure Part - Plates,Pipes/Forgings/Flange/ Fittings | H | W |  |  |  | Pending
320SR09 | B. Material Inspection & Traceability | 3.2 | Non Pressure Parts & Attachment To Pressure Parts | H | R |  |  |  | Pending
320SR09 | B. Material Inspection & Traceability | 3.3 | Welding Consumable | R | R |  |  |  | Pending
320SR09 | B. Material Inspection & Traceability | 3.4 | Weld Plan/Weld Map | P | R |  |  |  | Pending
320SR09 | C. Shell & Head Prep | 4.1 | Transfer Of Marking And Cutting (Shell And Dished End) | H | R |  |  |  | Pending
320SR09 | D. Head Sub-Assembly | 4.2 | Inspection Of Top & Bottom Dished | R | R |  |  |  | Pending
320SR09 | D. Head Sub-Assembly | 4.2 | Simulation Heat Treatment Of Test Coupon After Forming & Testing | R | R |  |  |  | Pending
320SR09 | D. Head Sub-Assembly | 4.4 | Weld Edge Preparation Of Top & Bottom Dished End | P | R |  |  |  | Pending
320SR09 | E. Shell Sub-Assembly (LS-1) | 4.5 | Shell Weld Edge Preparation | P | R |  |  |  | Pending
320SR09 | E. Shell Sub-Assembly (LS-1) | 4.5 | L' Seam Set Up Of Shell (Ls-1 ) Along With Ptc | P | R |  |  |  | Pending
320SR09 | E. Shell Sub-Assembly (LS-1) | 4.5 | Weld Long Seam Of Shell (Ls-1 ) | P | R |  |  |  | Pending
320SR09 | E. Shell Sub-Assembly (LS-1) | 4.5 | Weld Visual Of Ls-1 | P | R |  |  |  | Pending
320SR09 | E. Shell Sub-Assembly (LS-1) | 4.5 | Paut/Tofd Of Ls-1 | P | W |  |  |  | Pending
320SR09 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Nozzle To Flange/Elbow Set Up (M1/N2/N3) | P | R |  |  |  | Pending
320SR09 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Weld Of Nozzle To Flange/Elbow (M1/N2/N3) | P | R |  |  |  | Pending
320SR09 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Weld Visual Of Cs Joint Nozzle M1/N2/N3 | P | R |  |  |  | Pending
320SR09 | F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Rt Circ Seam Of Nozzle Pipe To Flange (M1/N2/N3) | P | R |  |  |  | Pending
320SR09 | G. Shell + Bottom Head (CS-2) | 4.7 | Bottom Dished End To Shell Set Up (Cs-2) | P | R |  |  |  | Pending
320SR09 | G. Shell + Bottom Head (CS-2) | 4.7 | Weld Circ Seam Of Bottom Dishend To Shell (Cs-2) | P | R |  |  |  | Pending
320SR09 | G. Shell + Bottom Head (CS-2) | 4.7 | Weld Visual Of Cs -2 | P | R |  |  |  | Pending
320SR09 | G. Shell + Bottom Head (CS-2) | 4.7 | Paut/Tofd Of Cs-2 | P | W |  |  |  | Pending
320SR09 | H. Nozzle & Manway Sub-Assembly | 4.8 | Marking For Nozzle On Shell And Dished End (M1, N1 To N6) | P | R |  |  |  | Pending
320SR09 | H. Nozzle & Manway Sub-Assembly | 4.8 | Nozzle To Shell & Dished End Set Up (M1/N1/N2/N3/N4/N5/N6) | P | R |  |  |  | Pending
320SR09 | H. Nozzle & Manway Sub-Assembly | 4.8 | Weld Of Nozzle To Shell & Dished End (M1/N1/N2/N3/N4/N5/N6) | P | R |  |  |  | Pending
320SR09 | H. Nozzle & Manway Sub-Assembly | 4.8 | Weld Visual Of Nozzle To Shell & Dished End (M1/N1/N2/N3/N4/N5/N6) | P | R |  |  |  | Pending
320SR09 | H. Nozzle & Manway Sub-Assembly | 4.8 | Ultrasonic Test Of Nozzle To Shell & Dished End (M1/N1/N2/N3) | P | R |  |  |  | Pending
320SR09 | I. Final Closure Gate | 4.9 | Clearance Of Shell Before Closing Dished End Set Up | P | R |  |  |  | Pending
320SR09 | J. Shell + Top Head (CS-1) | 4.10 | Top Dished End To Shell Set Up (Cs- 1) | P | R |  |  |  | Pending
320SR09 | J. Shell + Top Head (CS-1) | 4.10 | Weld Circ Seam Of Top Dishend To Shell (Cs-1) | P | R |  |  |  | Pending
320SR09 | J. Shell + Top Head (CS-1) | 4.10 | Weld Visual Of Cs -1 | P | R |  |  |  | Pending
320SR09 | J. Shell + Top Head (CS-1) | 4.10 | Paut/Tofd Of Cs-1 | P | W |  |  |  | Pending
320SR09 | K. Attachments Sub-Assembly | 4.11 | Lifting Lug & Name Plate Bracket Set Up | P | R |  |  |  | Pending
320SR09 | K. Attachments Sub-Assembly | 4.12 | Weld Of Lifting Lug | P | R |  |  |  | Pending
320SR09 | K. Attachments Sub-Assembly | 4.12 | Weld Of Name Plate Bracket | P | R |  |  |  | Pending
320SR09 | L. Skirt Sub-Assembly | 4.13 | Skirt Support Set Up | P | R |  |  |  | Pending
320SR09 | L. Skirt Sub-Assembly | 4.14 | Weld Skirt Support | P | R |  |  |  | Pending
320SR09 | M. Pre-PWHT Gate | 4.15 | Clearance Befor Pwht | P | W |  |  |  | Pending
320SR09 | N. Heat Treatment & Post-PWHT NDT | 5.1 | Inspection Of Vessel Heat Treatment | R | R |  |  |  | Pending
320SR09 | N. Heat Treatment & Post-PWHT NDT | 5.2 | Weld Visual Of All Weld Joints | P | W |  |  |  | Pending
320SR09 | N. Heat Treatment & Post-PWHT NDT | 5.3 | Mpt Of All Weld Joint | P | W |  |  |  | Pending
320SR09 | N. Heat Treatment & Post-PWHT NDT | 5.4 | Rt Testing On All Butt Weld Joints(M1/N2/N3) Paut/Tofd For L'Seam & C'Seam Joints. (After Pwht). | P | W |  |  |  | Pending
320SR09 | O. Hydrostatic Test | 6.1 | Clearance For Hydrostatic Test | P | R |  |  |  | Pending
320SR09 | O. Hydrostatic Test | 6.2 | Before Hydrostatic Test Clearance | P | R |  |  |  | Pending
320SR09 | O. Hydrostatic Test | 6.3 | Hydrostatic Test | P | W |  |  |  | Pending
320SR09 | O. Hydrostatic Test | 6.4 | Mpt / Lpt All Weld Joints After Hydro Test | P | W |  |  |  | Pending
320SR09 | P. Surface Treatment & Painting | 7.1 | Cleaning & Surface Preparation | P | R |  |  |  | Pending
320SR09 | P. Surface Treatment & Painting | 7.2 | Painting | P | W |  |  |  | Pending
320SR09 | Q. Final Inspection, Nameplate & MDR | 8.1 | Verification Of Name Plate | P | R |  |  |  | Pending
320SR09 | Q. Final Inspection, Nameplate & MDR | 8.2 | Attachment Of Name Plate To Name Plate Bracket | P | R |  |  |  | Pending
320SR09 | Q. Final Inspection, Nameplate & MDR | 9.1 | Documentation | R | R |  |  |  | Pending

## 36-Process Schedule
36-Process Schedule
Order date 20-Nov-2026 · max-duration envelope · Sunday week-off · committed dispatch 08-Apr-2027
# | Process | Department | Start by | Finish by | Actual start | Actual finish | Status | Remarks
1 | PO Receipt & Order Review | Projects / PMO | 20-Nov-2026 | 23-Nov-2026 |  |  | Not started
2 | Kick-Off / Pre-Inspection Meeting | Projects / PMO | 23-Nov-2026 | 26-Nov-2026 |  |  | Not started
3 | Engineering – Design Calculation | Design & Detail Engineering | 25-Nov-2026 | 07-Dec-2026 |  |  | Not started
4 | Engineering – Manufacturing Drawings | Design & Detail Engineering | 03-Dec-2026 | 15-Dec-2026 |  |  | Not started
5 | Client Drawing Approval | Design & Detail Engineering | 14-Dec-2026 | 31-Dec-2026 |  |  | Not started
6 | BOM & MTO Finalization | Planning / PPC | 26-Dec-2026 | 31-Dec-2026 |  |  | Not started
7 | Material Procurement – Plates | Procurement | 07-Dec-2026 | 10-Feb-2027 |  |  | Not started
8 | Material Procurement – Pipes/Forgings/Fittings | Procurement | 15-Dec-2026 | 02-Feb-2027 |  |  | Not started
9 | Bought-Out Items Procurement | Procurement | 15-Dec-2026 | 25-Jan-2027 |  |  | Not started
10 | Material Receipt & Incoming Inspection | Stores | 06-Feb-2027 | 10-Feb-2027 |  |  | Not started
11 | Material Identification & Traceability | QC | 08-Feb-2027 | 10-Feb-2027 |  |  | Not started
12 | Cutting / Blanking / Petals | Fabrication Prep | 05-Feb-2027 | 10-Feb-2027 |  |  | Not started
13 | Forming / Rolling / Dishing | Fabrication Prep | 10-Feb-2027 | 18-Feb-2027 |  |  | Not started
14 | Machining | Machine Shop | 10-Feb-2027 | 18-Feb-2027 |  |  | Not started
15 | Shell Fit-Up | Fabrication / Welding | 13-Feb-2027 | 18-Feb-2027 |  |  | Not started
16 | Shell Welding | Fabrication / Welding | 18-Feb-2027 | 26-Feb-2027 |  |  | Not started
17 | Weld NDE | QC | 20-Feb-2027 | 26-Feb-2027 |  |  | Not started
18 | Head/Dish-End Assembly | Fabrication / Welding | 22-Feb-2027 | 26-Feb-2027 |  |  | Not started
19 | Nozzle Fabrication & Fit-Up | Fabrication / Welding | 20-Feb-2027 | 26-Feb-2027 |  |  | Not started
20 | Nozzle Welding | Fabrication / Welding | 01-Mar-2027 | 06-Mar-2027 |  |  | Not started
21 | PWHT / Heat Treatment | Heat Treatment | 01-Mar-2027 | 06-Mar-2027 |  |  | Not started
22 | NDE After Welding/PWHT | QC | 01-Mar-2027 | 06-Mar-2027 |  |  | Not started
23 | Internal & External Attachments | Fabrication / Welding | 06-Mar-2027 | 15-Mar-2027 |  |  | Not started
24 | Final Assembly | Fabrication / Welding | 09-Mar-2027 | 15-Mar-2027 |  |  | Not started
25 | Final Dimensional Inspection | QC | 12-Mar-2027 | 15-Mar-2027 |  |  | Not started
26 | Final Visual Inspection | QC | 13-Mar-2027 | 15-Mar-2027 |  |  | Not started
27 | Hydrostatic / Pressure Test | QC | 12-Mar-2027 | 15-Mar-2027 |  |  | Not started
28 | Draining & Drying | Fabrication / Welding | 12-Mar-2027 | 15-Mar-2027 |  |  | Not started
29 | Surface Preparation | Surface Treatment & Painting | 19-Mar-2027 | 23-Mar-2027 |  |  | Not started
30 | Painting / Coating | Surface Treatment & Painting | 17-Mar-2027 | 23-Mar-2027 |  |  | Not started
31 | Final Inspection | QC | 27-Mar-2027 | 31-Mar-2027 |  |  | Not started
32 | Name Plate & Final Stamping | QC | 30-Mar-2027 | 31-Mar-2027 |  |  | Not started
33 | MDR / Final Documentation | Documentation | 31-Mar-2027 | 08-Apr-2027 |  |  | Not started
34 | Packing & Preservation | Dispatch & Logistics | 05-Apr-2027 | 08-Apr-2027 |  |  | Not started
35 | Dispatch Clearance | Dispatch & Logistics | 06-Apr-2027 | 08-Apr-2027 |  |  | Not started
36 | Dispatch | Dispatch & Logistics | 07-Apr-2027 | 08-Apr-2027 (committed delivery) |  |  | Not started

## Department Deadlines
Department Deadlines
One line per department — hand to department heads today
Department | First activity starts by | Department's own work done by | Notes
Projects / PMO | 20-Nov-2026 | 26-Nov-2026
Design & Detail Engineering | 25-Nov-2026 | 31-Dec-2026
Planning / PPC | 26-Dec-2026 | 31-Dec-2026
Procurement | 07-Dec-2026 | 10-Feb-2027
Stores | 06-Feb-2027 | 10-Feb-2027
Fabrication Prep (cutting/forming) | 05-Feb-2027 | 18-Feb-2027
Machine Shop | 10-Feb-2027 | 18-Feb-2027
Fabrication / Welding | 13-Feb-2027 | 15-Mar-2027 | last of its 8 processes: Draining & Drying
Heat Treatment | 01-Mar-2027 | 06-Mar-2027
QC | 08-Feb-2027 | 31-Mar-2027 | last: Name Plate & Final Stamping) — QC touches 8 separate processes across the whole job, more than any other department
Surface Treatment & Painting | 17-Mar-2027 | 23-Mar-2027
Documentation | 31-Mar-2027 | 08-Apr-2027
Dispatch & Logistics | 05-Apr-2027 | 08-Apr-2027 | dispatch

## Units x Process Tracker
Units × Process Tracker (macro)
Department-level view — 36 processes × 9 units. For daily/weekly management roll-up, not floor operation detail (see Fabrication Operations Tracker for that).
# | Process | Department | Start by | Finish by | 320SR01 | 320SR02 | 320SR03 | 320SR04 | 320SR05 | 320SR06 | 320SR07 | 320SR08 | 320SR09
1 | PO Receipt & Order Review | Projects / PMO | 20-Nov-2026 | 23-Nov-2026 | bar: 320SR01 to 320SR09
2 | Kick-Off / Pre-Inspection Meeting | Projects / PMO | 23-Nov-2026 | 26-Nov-2026 | bar: 320SR01 to 320SR09
3 | Engineering – Design Calculation | Design & Detail Engineering | 25-Nov-2026 | 07-Dec-2026 | bar: 320SR01 to 320SR09
4 | Engineering – Manufacturing Drawings | Design & Detail Engineering | 03-Dec-2026 | 15-Dec-2026 | bar: 320SR01 to 320SR09
5 | Client Drawing Approval | Design & Detail Engineering | 14-Dec-2026 | 31-Dec-2026 | bar: 320SR01 to 320SR09
6 | BOM & MTO Finalization | Planning / PPC | 26-Dec-2026 | 31-Dec-2026 | bar: 320SR01 to 320SR09
7 | Material Procurement – Plates | Procurement | 07-Dec-2026 | 10-Feb-2027 | bar: 320SR01 to 320SR09
8 | Material Procurement – Pipes/Forgings/Fittings | Procurement | 15-Dec-2026 | 02-Feb-2027 | bar: 320SR01 to 320SR09
9 | Bought-Out Items Procurement | Procurement | 15-Dec-2026 | 25-Jan-2027 | bar: 320SR01 to 320SR09
10 | Material Receipt & Incoming Inspection | Stores | 06-Feb-2027 | 10-Feb-2027 | bar: 320SR01 to 320SR09
11 | Material Identification & Traceability | QC | 08-Feb-2027 | 10-Feb-2027 | bar: 320SR01 to 320SR09
12 | Cutting / Blanking / Petals | Fabrication Prep | 05-Feb-2027 | 10-Feb-2027 | bar: 320SR01 to 320SR09
13 | Forming / Rolling / Dishing | Fabrication Prep | 10-Feb-2027 | 18-Feb-2027 | bar: 320SR01 to 320SR09
14 | Machining | Machine Shop | 10-Feb-2027 | 18-Feb-2027 | bar: 320SR01 to 320SR09
15 | Shell Fit-Up | Fabrication / Welding | 13-Feb-2027 | 18-Feb-2027 | bar: 320SR01 to 320SR09
16 | Shell Welding | Fabrication / Welding | 18-Feb-2027 | 26-Feb-2027 | bar: 320SR01 to 320SR09
17 | Weld NDE | QC | 20-Feb-2027 | 26-Feb-2027 | bar: 320SR01 to 320SR09
18 | Head/Dish-End Assembly | Fabrication / Welding | 22-Feb-2027 | 26-Feb-2027 | bar: 320SR01 to 320SR09
19 | Nozzle Fabrication & Fit-Up | Fabrication / Welding | 20-Feb-2027 | 26-Feb-2027 | bar: 320SR01 to 320SR09
20 | Nozzle Welding | Fabrication / Welding | 01-Mar-2027 | 06-Mar-2027 | bar: 320SR01 to 320SR09
21 | PWHT / Heat Treatment | Heat Treatment | 01-Mar-2027 | 06-Mar-2027 | bar: 320SR01 to 320SR09
22 | NDE After Welding/PWHT | QC | 01-Mar-2027 | 06-Mar-2027 | bar: 320SR01 to 320SR09
23 | Internal & External Attachments | Fabrication / Welding | 06-Mar-2027 | 15-Mar-2027 | bar: 320SR01 to 320SR09
24 | Final Assembly | Fabrication / Welding | 09-Mar-2027 | 15-Mar-2027 | bar: 320SR01 to 320SR09
25 | Final Dimensional Inspection | QC | 12-Mar-2027 | 15-Mar-2027 | bar: 320SR01 to 320SR09
26 | Final Visual Inspection | QC | 13-Mar-2027 | 15-Mar-2027 | bar: 320SR01 to 320SR09
27 | Hydrostatic / Pressure Test | QC | 12-Mar-2027 | 15-Mar-2027 | bar: 320SR01 to 320SR09
28 | Draining & Drying | Fabrication / Welding | 12-Mar-2027 | 15-Mar-2027 | bar: 320SR01 to 320SR09
29 | Surface Preparation | Surface Treatment & Painting | 19-Mar-2027 | 23-Mar-2027 | bar: 320SR01 to 320SR09
30 | Painting / Coating | Surface Treatment & Painting | 17-Mar-2027 | 23-Mar-2027 | bar: 320SR01 to 320SR09
31 | Final Inspection | QC | 27-Mar-2027 | 31-Mar-2027 | bar: 320SR01 to 320SR09
32 | Name Plate & Final Stamping | QC | 30-Mar-2027 | 31-Mar-2027 | bar: 320SR01 to 320SR09
33 | MDR / Final Documentation | Documentation | 31-Mar-2027 | 08-Apr-2027 | bar: 320SR01 to 320SR09
34 | Packing & Preservation | Dispatch & Logistics | 05-Apr-2027 | 08-Apr-2027 | bar: 320SR01 to 320SR09
35 | Dispatch Clearance | Dispatch & Logistics | 06-Apr-2027 | 08-Apr-2027 | bar: 320SR01 to 320SR09
36 | Dispatch | Dispatch & Logistics | 07-Apr-2027 | 08-Apr-2027 (committed delivery) | bar: 320SR01 to 320SR09

## Dev Notes
Dev Notes — software build status
Companion to docs/superpowers/plans/2026-08-25-component-operation-tracking.md
1. Read side already exists
src/lib/services/bom-route.ts's projectComponentRoute() + <BomPanel /> already render the planned-vs-actual route for any component that has ComponentOperation rows. It just has nothing to show for DESPL-320 yet (Task 1).
2. Write side — drafted this session, not yet reviewed or wired in
src/lib/services/component.service.ts (start/submit/verify, mirrors process.service.ts's state machine), a schemas.ts snippet, and scripts/seed-despl320-components.ts (idempotent, additive — creates the 99 Component/ComponentOperation rows). None of this has been run against a database or reviewed by the team yet.
3. Still needed before this is live
Merge the schema snippet, review + land component.service.ts, write component.service.test.ts (table-driven, every violation case), build the Server Actions, wire Start/Submit/Verify buttons into <BomPanel />. Full task list in the plan doc.
4. The Rolling vs Forming question
The floor team's own language treats these as 2 separate timed steps for the shell. The app's PLATE route today has ONE combined 'Forming' operation. This workbook tracks them as 2 rows for now (flagged in the Remarks column) — confirm with the floor team whether that's a real second timed step before splitting it in the database (small change, needs confirmation first, not blocking).
5. No fabricated procurement data
Component.bomItemId stays null for all 99 new rows — there's no real BOM/procurement CSV for DESPL-320 the way DE0463/DE0467 have. Material/size shown in this workbook is for floor reference only, not yet in the procurement-tracking tables.