## Read Me
DESPL-320 — Production Tracker
HP Air Receiver · 9 units (320SR01–09) · PN-EM3-HIN-301-MEC-040-DG-4503 Rev A · built 25 Aug 2026
Order date (fixed) | 20-Nov-2026
Committed dispatch date | 08-Apr-2027 (day 119 of the envelope)
Units | 9 (320SR01 – 320SR09)
Design code | ASME SEC VIII DIV 1, Edition 2021
Inspection parties | DESPL (self) + BUYER_TPI
STATUS — production tracker app
Schedule engine | 36-process spine, max-duration envelope, Sunday-only week-off. Matches the tracker's own scheduling logic.
Live in the app already | Job + 36-process schedule (324 ProcessPlan rows, 9 units) + full 54-checkpoint QCP — see 'Dev Notes' tab
URGENT — action needed | The live app's DESPL-320 schedule is currently running on a placeholder demo date, not 20-Nov-2026. See 'Dev Notes' tab §1.
Missing — new work | BOM / component (sub-assembly) register — this workbook's 'Sub-Assembly Register' tab is that data, ready to seed.
Open question (C1) | Should the 119-day envelope also exclude company holidays beyond Sundays? Unconfirmed by SJ — doesn't block starting.
HOW TO USE THIS WORKBOOK
Schedule (36-Process) | Department-level plan — one row per process. Fill Actual Start / Actual Finish / Status as work happens.
Department Deadlines | One line per department — first activity, own work done-by date. Hand to department heads.
Units × Process Tracker | 36 processes × 9 units in one matrix — the floor-level daily tracker. Mark each cell as work completes per unit.
Sub-Assembly Register | Component-level fabrication route (Shell, Heads, Skirt, Nozzles, Manway) — 99 rows, 11 components × 9 units.
Assembly & Weld Checklist | The weld/QCP build sequence, grouped by sub-assembly, with Hold/Witness points flagged — 54 checkpoints × 9 units.
Dev Notes | For whoever picks up the software side — what's already built vs. what's new, and the exact next steps.

## 36-Process Schedule
36-Process Schedule
Order date 20-Nov-2026 · max-duration envelope · Sunday week-off · committed dispatch 08-Apr-2027
Pale-yellow cells (Actual start / Actual finish / Status / Remarks) are for the team to fill in as work happens.
# | Process | Department | Start by | Finish by | Actual start | Actual finish | Status | Remarks
1 | PO Receipt & Order Review | Projects / PMO | 20-Nov-2026 | 23-Nov-2026 |  |  | Not started
2 | Kick-Off / Pre-Inspection Meeting | Projects / PMO | 23-Nov-2026 | 26-Nov-2026 |  |  | Not started
3 | Engineering – Design Calculation | Design & Detail Engineering | 25-Nov-2026 | 07-Dec-2026 |  |  | Not started
4 | Engineering – Manufacturing Drawings | Design & Detail Engineering | 03-Dec-2026 | 15-Dec-2026 |  |  | Not started
5 | Client Drawing Approval | Design & Detail Engineering | 14-Dec-2026 | 31-Dec-2026 |  |  | Not started
6 | BOM & MTO Finalization | Planning / PPC | 26-Dec-2026 | 31-Dec-2026 |  |  | Not started
7 | Material Procurement – Plates | Procurement | 07-Dec-2026 | 10-Feb-2027 |  |  | Not started
8 | Material Procurement – Pipes/Forgings/Fittings | Procurement | 15-Dec-2026 | 02-Feb-2027 |  |  | Not started
9 | Bought-Out Items Procurement | Procurement | 15-Dec-2026 | 25-Jan-2027 |  |  | Not started
10 | Material Receipt & Incoming Inspection | Stores | 06-Feb-2027 | 10-Feb-2027 |  |  | Not started
11 | Material Identification & Traceability | QC | 08-Feb-2027 | 10-Feb-2027 |  |  | Not started
12 | Cutting / Blanking / Petals | Fabrication Prep | 05-Feb-2027 | 10-Feb-2027 |  |  | Not started
13 | Forming / Rolling / Dishing | Fabrication Prep | 10-Feb-2027 | 18-Feb-2027 |  |  | Not started
14 | Machining | Machine Shop | 10-Feb-2027 | 18-Feb-2027 |  |  | Not started
15 | Shell Fit-Up | Fabrication / Welding | 13-Feb-2027 | 18-Feb-2027 |  |  | Not started
16 | Shell Welding | Fabrication / Welding | 18-Feb-2027 | 26-Feb-2027 |  |  | Not started
17 | Weld NDE | QC | 20-Feb-2027 | 26-Feb-2027 |  |  | Not started
18 | Head/Dish-End Assembly | Fabrication / Welding | 22-Feb-2027 | 26-Feb-2027 |  |  | Not started
19 | Nozzle Fabrication & Fit-Up | Fabrication / Welding | 20-Feb-2027 | 26-Feb-2027 |  |  | Not started
20 | Nozzle Welding | Fabrication / Welding | 01-Mar-2027 | 06-Mar-2027 |  |  | Not started
21 | PWHT / Heat Treatment | Heat Treatment | 01-Mar-2027 | 06-Mar-2027 |  |  | Not started
22 | NDE After Welding/PWHT | QC | 01-Mar-2027 | 06-Mar-2027 |  |  | Not started
23 | Internal & External Attachments | Fabrication / Welding | 06-Mar-2027 | 15-Mar-2027 |  |  | Not started
24 | Final Assembly | Fabrication / Welding | 09-Mar-2027 | 15-Mar-2027 |  |  | Not started
25 | Final Dimensional Inspection | QC | 12-Mar-2027 | 15-Mar-2027 |  |  | Not started
26 | Final Visual Inspection | QC | 13-Mar-2027 | 15-Mar-2027 |  |  | Not started
27 | Hydrostatic / Pressure Test | QC | 12-Mar-2027 | 15-Mar-2027 |  |  | Not started
28 | Draining & Drying | Fabrication / Welding | 12-Mar-2027 | 15-Mar-2027 |  |  | Not started
29 | Surface Preparation | Surface Treatment & Painting | 19-Mar-2027 | 23-Mar-2027 |  |  | Not started
30 | Painting / Coating | Surface Treatment & Painting | 17-Mar-2027 | 23-Mar-2027 |  |  | Not started
31 | Final Inspection | QC | 27-Mar-2027 | 31-Mar-2027 |  |  | Not started
32 | Name Plate & Final Stamping | QC | 30-Mar-2027 | 31-Mar-2027 |  |  | Not started
33 | MDR / Final Documentation | Documentation | 31-Mar-2027 | 08-Apr-2027 |  |  | Not started
34 | Packing & Preservation | Dispatch & Logistics | 05-Apr-2027 | 08-Apr-2027 |  |  | Not started
35 | Dispatch Clearance | Dispatch & Logistics | 06-Apr-2027 | 08-Apr-2027 |  |  | Not started
36 | Dispatch | Dispatch & Logistics | 07-Apr-2027 | 08-Apr-2027 (committed delivery) |  |  | Not started

## Department Deadlines
Department Deadlines
One line per department — hand to department heads today
Department | First activity starts by | Department's own work done by | Notes
Projects / PMO | 20-Nov-2026 | 26-Nov-2026
Design & Detail Engineering | 25-Nov-2026 | 31-Dec-2026
Planning / PPC | 26-Dec-2026 | 31-Dec-2026
Procurement | 07-Dec-2026 | 10-Feb-2027
Stores | 06-Feb-2027 | 10-Feb-2027
Fabrication Prep (cutting/forming) | 05-Feb-2027 | 18-Feb-2027
Machine Shop | 10-Feb-2027 | 18-Feb-2027
Fabrication / Welding | 13-Feb-2027 | 15-Mar-2027 | last of its 8 processes: Draining & Drying
Heat Treatment | 01-Mar-2027 | 06-Mar-2027
QC | 08-Feb-2027 | 31-Mar-2027 | last: Name Plate & Final Stamping) — QC touches 8 separate processes across the whole job, more than any other department
Surface Treatment & Painting | 17-Mar-2027 | 23-Mar-2027
Documentation | 31-Mar-2027 | 08-Apr-2027
Dispatch & Logistics | 05-Apr-2027 | 08-Apr-2027 | dispatch

## Units x Process Tracker
Units × Process Tracker
Floor-level daily tracker — 36 processes × 9 units. Mark each cell as a unit completes that process.
Pale-yellow cells (one column per unit) are for the floor to fill in — mark each unit's status per process as it completes.
# | Process | Department | Start by | Finish by | 320SR01 | 320SR02 | 320SR03 | 320SR04 | 320SR05 | 320SR06 | 320SR07 | 320SR08 | 320SR09
1 | PO Receipt & Order Review | Projects / PMO | 20-Nov-2026 | 23-Nov-2026 | bar: 320SR01 to 320SR09
2 | Kick-Off / Pre-Inspection Meeting | Projects / PMO | 23-Nov-2026 | 26-Nov-2026 | bar: 320SR01 to 320SR09
3 | Engineering – Design Calculation | Design & Detail Engineering | 25-Nov-2026 | 07-Dec-2026 | bar: 320SR01 to 320SR09
4 | Engineering – Manufacturing Drawings | Design & Detail Engineering | 03-Dec-2026 | 15-Dec-2026 | bar: 320SR01 to 320SR09
5 | Client Drawing Approval | Design & Detail Engineering | 14-Dec-2026 | 31-Dec-2026 | bar: 320SR01 to 320SR09
6 | BOM & MTO Finalization | Planning / PPC | 26-Dec-2026 | 31-Dec-2026 | bar: 320SR01 to 320SR09
7 | Material Procurement – Plates | Procurement | 07-Dec-2026 | 10-Feb-2027 | bar: 320SR01 to 320SR09
8 | Material Procurement – Pipes/Forgings/Fittings | Procurement | 15-Dec-2026 | 02-Feb-2027 | bar: 320SR01 to 320SR09
9 | Bought-Out Items Procurement | Procurement | 15-Dec-2026 | 25-Jan-2027 | bar: 320SR01 to 320SR09
10 | Material Receipt & Incoming Inspection | Stores | 06-Feb-2027 | 10-Feb-2027 | bar: 320SR01 to 320SR09
11 | Material Identification & Traceability | QC | 08-Feb-2027 | 10-Feb-2027 | bar: 320SR01 to 320SR09
12 | Cutting / Blanking / Petals | Fabrication Prep | 05-Feb-2027 | 10-Feb-2027 | bar: 320SR01 to 320SR09
13 | Forming / Rolling / Dishing | Fabrication Prep | 10-Feb-2027 | 18-Feb-2027 | bar: 320SR01 to 320SR09
14 | Machining | Machine Shop | 10-Feb-2027 | 18-Feb-2027 | bar: 320SR01 to 320SR09
15 | Shell Fit-Up | Fabrication / Welding | 13-Feb-2027 | 18-Feb-2027 | bar: 320SR01 to 320SR09
16 | Shell Welding | Fabrication / Welding | 18-Feb-2027 | 26-Feb-2027 | bar: 320SR01 to 320SR09
17 | Weld NDE | QC | 20-Feb-2027 | 26-Feb-2027 | bar: 320SR01 to 320SR09
18 | Head/Dish-End Assembly | Fabrication / Welding | 22-Feb-2027 | 26-Feb-2027 | bar: 320SR01 to 320SR09
19 | Nozzle Fabrication & Fit-Up | Fabrication / Welding | 20-Feb-2027 | 26-Feb-2027 | bar: 320SR01 to 320SR09
20 | Nozzle Welding | Fabrication / Welding | 01-Mar-2027 | 06-Mar-2027 | bar: 320SR01 to 320SR09
21 | PWHT / Heat Treatment | Heat Treatment | 01-Mar-2027 | 06-Mar-2027 | bar: 320SR01 to 320SR09
22 | NDE After Welding/PWHT | QC | 01-Mar-2027 | 06-Mar-2027 | bar: 320SR01 to 320SR09
23 | Internal & External Attachments | Fabrication / Welding | 06-Mar-2027 | 15-Mar-2027 | bar: 320SR01 to 320SR09
24 | Final Assembly | Fabrication / Welding | 09-Mar-2027 | 15-Mar-2027 | bar: 320SR01 to 320SR09
25 | Final Dimensional Inspection | QC | 12-Mar-2027 | 15-Mar-2027 | bar: 320SR01 to 320SR09
26 | Final Visual Inspection | QC | 13-Mar-2027 | 15-Mar-2027 | bar: 320SR01 to 320SR09
27 | Hydrostatic / Pressure Test | QC | 12-Mar-2027 | 15-Mar-2027 | bar: 320SR01 to 320SR09
28 | Draining & Drying | Fabrication / Welding | 12-Mar-2027 | 15-Mar-2027 | bar: 320SR01 to 320SR09
29 | Surface Preparation | Surface Treatment & Painting | 19-Mar-2027 | 23-Mar-2027 | bar: 320SR01 to 320SR09
30 | Painting / Coating | Surface Treatment & Painting | 17-Mar-2027 | 23-Mar-2027 | bar: 320SR01 to 320SR09
31 | Final Inspection | QC | 27-Mar-2027 | 31-Mar-2027 | bar: 320SR01 to 320SR09
32 | Name Plate & Final Stamping | QC | 30-Mar-2027 | 31-Mar-2027 | bar: 320SR01 to 320SR09
33 | MDR / Final Documentation | Documentation | 31-Mar-2027 | 08-Apr-2027 | bar: 320SR01 to 320SR09
34 | Packing & Preservation | Dispatch & Logistics | 05-Apr-2027 | 08-Apr-2027 | bar: 320SR01 to 320SR09
35 | Dispatch Clearance | Dispatch & Logistics | 06-Apr-2027 | 08-Apr-2027 | bar: 320SR01 to 320SR09
36 | Dispatch | Dispatch & Logistics | 07-Apr-2027 | 08-Apr-2027 (committed delivery) | bar: 320SR01 to 320SR09

## Sub-Assembly Register
Sub-Assembly Register — Component Fabrication Route
11 trackable components x 9 units = 99 rows. Corrects the 10-component/90-row count in the schedule doc's §4.4.
Pale-yellow cells (Status / Remarks) are for the team to fill in as fabrication proceeds.
Unit | Tag | Component | Route (component type) | Weld joint(s) | Material | Status | Remarks
320SR01 | SHELL-01 | Shell (single course) | PLATE: Receipt -> MTC Verification -> Cutting -> Edge Prep -> Rolling/Forming -> Fit-up -> Welding -> RT/UT -> Grinding -> Inspection | LS-1 | SA 516 Gr 485, normalized fine-grain fully killed | Not started
320SR01 | TOP-HEAD-01 | Top Dished End (head) | DISHED_END: Plate Cutting -> Pressing/Spinning -> Trimming -> NDT -> Inspection | CS-1 | SA 516 Gr 485 | Not started
320SR01 | BOTTOM-HEAD-01 | Bottom Dished End (head) | DISHED_END: Plate Cutting -> Pressing/Spinning -> Trimming -> NDT -> Inspection | CS-2 | SA 516 Gr 485 | Not started
320SR01 | SKIRT-01 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | SKIRT: Plate Rolling -> Welding -> Machining -> Inspection | — | Skirt shell SA 516 Gr 485 (16T x 1062W x 7323 DEV.LG, 977 kg); base ring IS 2062 E 250 B (32T x 2187 ID x 2600 OD, 390 kg); 24x gusset plate IS 2062 E 250 B (12T x 127W x 150 LG, 43 kg total) | Not started
320SR01 | N1-01 | Nozzle N1 (flange, per detail) | FLANGE: Receipt -> Machining -> Facing -> Drilling -> Inspection | — | SA 105 | Not started
320SR01 | N2-01 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | PIPE: Receipt -> Cutting -> Beveling -> Fit-up -> Welding -> RT/PT -> Inspection | — | Flange SA 105 (DN25 class); Pipe SA 333 Gr 6 (DN25 SCH.XXS, 1270 LG + 170 LG); Elbow SA 234 Gr WPB (DN25 SCH.XXS 90deg LR); Stiffener SA 516 Gr 485 (6T x 50W x 250 LG); Support Pipe SA 106 Gr B (DN200 SCH80 x 115 LG) | Not started
320SR01 | N3-01 | Nozzle N3 (SRN forging + flange + 3x stiffener) | FORGING: Receipt -> Machining -> NDT -> Inspection | — | SRN SA 266 Gr 2; Flange SA 105 (DN125 SCH.XXS CL.600 WNRF); Stiffener SA 516 Gr 485 (6T x 82W x 80 LG) x3 | Not started
320SR01 | N4-01 | Nozzle N4 (coupling) | COUPLING: Receipt -> Thread Inspection -> Dimension Check | — | SA 105, DN15 SCH.XXS x 6000# BSP | Not started
320SR01 | N5-01 | Nozzle N5 (coupling) | COUPLING: Receipt -> Thread Inspection -> Dimension Check | — | SA 105, DN15 SCH.XXS x 6000# BSP | Not started
320SR01 | N6-01 | Nozzle N6 (coupling) | COUPLING: Receipt -> Thread Inspection -> Dimension Check | — | SA 105, DN15 SCH.XXS x 6000# BSP | Not started
320SR01 | M1-01 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | FORGING: Receipt -> Machining -> NDT -> Inspection | — | SRN SA 266 Gr 2 (DN450x22THK ASME 600CL WNRF) | Not started
320SR02 | SHELL-02 | Shell (single course) | PLATE: Receipt -> MTC Verification -> Cutting -> Edge Prep -> Rolling/Forming -> Fit-up -> Welding -> RT/UT -> Grinding -> Inspection | LS-1 | SA 516 Gr 485, normalized fine-grain fully killed | Not started
320SR02 | TOP-HEAD-02 | Top Dished End (head) | DISHED_END: Plate Cutting -> Pressing/Spinning -> Trimming -> NDT -> Inspection | CS-1 | SA 516 Gr 485 | Not started
320SR02 | BOTTOM-HEAD-02 | Bottom Dished End (head) | DISHED_END: Plate Cutting -> Pressing/Spinning -> Trimming -> NDT -> Inspection | CS-2 | SA 516 Gr 485 | Not started
320SR02 | SKIRT-02 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | SKIRT: Plate Rolling -> Welding -> Machining -> Inspection | — | Skirt shell SA 516 Gr 485 (16T x 1062W x 7323 DEV.LG, 977 kg); base ring IS 2062 E 250 B (32T x 2187 ID x 2600 OD, 390 kg); 24x gusset plate IS 2062 E 250 B (12T x 127W x 150 LG, 43 kg total) | Not started
320SR02 | N1-02 | Nozzle N1 (flange, per detail) | FLANGE: Receipt -> Machining -> Facing -> Drilling -> Inspection | — | SA 105 | Not started
320SR02 | N2-02 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | PIPE: Receipt -> Cutting -> Beveling -> Fit-up -> Welding -> RT/PT -> Inspection | — | Flange SA 105 (DN25 class); Pipe SA 333 Gr 6 (DN25 SCH.XXS, 1270 LG + 170 LG); Elbow SA 234 Gr WPB (DN25 SCH.XXS 90deg LR); Stiffener SA 516 Gr 485 (6T x 50W x 250 LG); Support Pipe SA 106 Gr B (DN200 SCH80 x 115 LG) | Not started
320SR02 | N3-02 | Nozzle N3 (SRN forging + flange + 3x stiffener) | FORGING: Receipt -> Machining -> NDT -> Inspection | — | SRN SA 266 Gr 2; Flange SA 105 (DN125 SCH.XXS CL.600 WNRF); Stiffener SA 516 Gr 485 (6T x 82W x 80 LG) x3 | Not started
320SR02 | N4-02 | Nozzle N4 (coupling) | COUPLING: Receipt -> Thread Inspection -> Dimension Check | — | SA 105, DN15 SCH.XXS x 6000# BSP | Not started
320SR02 | N5-02 | Nozzle N5 (coupling) | COUPLING: Receipt -> Thread Inspection -> Dimension Check | — | SA 105, DN15 SCH.XXS x 6000# BSP | Not started
320SR02 | N6-02 | Nozzle N6 (coupling) | COUPLING: Receipt -> Thread Inspection -> Dimension Check | — | SA 105, DN15 SCH.XXS x 6000# BSP | Not started
320SR02 | M1-02 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | FORGING: Receipt -> Machining -> NDT -> Inspection | — | SRN SA 266 Gr 2 (DN450x22THK ASME 600CL WNRF) | Not started
320SR03 | SHELL-03 | Shell (single course) | PLATE: Receipt -> MTC Verification -> Cutting -> Edge Prep -> Rolling/Forming -> Fit-up -> Welding -> RT/UT -> Grinding -> Inspection | LS-1 | SA 516 Gr 485, normalized fine-grain fully killed | Not started
320SR03 | TOP-HEAD-03 | Top Dished End (head) | DISHED_END: Plate Cutting -> Pressing/Spinning -> Trimming -> NDT -> Inspection | CS-1 | SA 516 Gr 485 | Not started
320SR03 | BOTTOM-HEAD-03 | Bottom Dished End (head) | DISHED_END: Plate Cutting -> Pressing/Spinning -> Trimming -> NDT -> Inspection | CS-2 | SA 516 Gr 485 | Not started
320SR03 | SKIRT-03 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | SKIRT: Plate Rolling -> Welding -> Machining -> Inspection | — | Skirt shell SA 516 Gr 485 (16T x 1062W x 7323 DEV.LG, 977 kg); base ring IS 2062 E 250 B (32T x 2187 ID x 2600 OD, 390 kg); 24x gusset plate IS 2062 E 250 B (12T x 127W x 150 LG, 43 kg total) | Not started
320SR03 | N1-03 | Nozzle N1 (flange, per detail) | FLANGE: Receipt -> Machining -> Facing -> Drilling -> Inspection | — | SA 105 | Not started
320SR03 | N2-03 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | PIPE: Receipt -> Cutting -> Beveling -> Fit-up -> Welding -> RT/PT -> Inspection | — | Flange SA 105 (DN25 class); Pipe SA 333 Gr 6 (DN25 SCH.XXS, 1270 LG + 170 LG); Elbow SA 234 Gr WPB (DN25 SCH.XXS 90deg LR); Stiffener SA 516 Gr 485 (6T x 50W x 250 LG); Support Pipe SA 106 Gr B (DN200 SCH80 x 115 LG) | Not started
320SR03 | N3-03 | Nozzle N3 (SRN forging + flange + 3x stiffener) | FORGING: Receipt -> Machining -> NDT -> Inspection | — | SRN SA 266 Gr 2; Flange SA 105 (DN125 SCH.XXS CL.600 WNRF); Stiffener SA 516 Gr 485 (6T x 82W x 80 LG) x3 | Not started
320SR03 | N4-03 | Nozzle N4 (coupling) | COUPLING: Receipt -> Thread Inspection -> Dimension Check | — | SA 105, DN15 SCH.XXS x 6000# BSP | Not started
320SR03 | N5-03 | Nozzle N5 (coupling) | COUPLING: Receipt -> Thread Inspection -> Dimension Check | — | SA 105, DN15 SCH.XXS x 6000# BSP | Not started
320SR03 | N6-03 | Nozzle N6 (coupling) | COUPLING: Receipt -> Thread Inspection -> Dimension Check | — | SA 105, DN15 SCH.XXS x 6000# BSP | Not started
320SR03 | M1-03 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | FORGING: Receipt -> Machining -> NDT -> Inspection | — | SRN SA 266 Gr 2 (DN450x22THK ASME 600CL WNRF) | Not started
320SR04 | SHELL-04 | Shell (single course) | PLATE: Receipt -> MTC Verification -> Cutting -> Edge Prep -> Rolling/Forming -> Fit-up -> Welding -> RT/UT -> Grinding -> Inspection | LS-1 | SA 516 Gr 485, normalized fine-grain fully killed | Not started
320SR04 | TOP-HEAD-04 | Top Dished End (head) | DISHED_END: Plate Cutting -> Pressing/Spinning -> Trimming -> NDT -> Inspection | CS-1 | SA 516 Gr 485 | Not started
320SR04 | BOTTOM-HEAD-04 | Bottom Dished End (head) | DISHED_END: Plate Cutting -> Pressing/Spinning -> Trimming -> NDT -> Inspection | CS-2 | SA 516 Gr 485 | Not started
320SR04 | SKIRT-04 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | SKIRT: Plate Rolling -> Welding -> Machining -> Inspection | — | Skirt shell SA 516 Gr 485 (16T x 1062W x 7323 DEV.LG, 977 kg); base ring IS 2062 E 250 B (32T x 2187 ID x 2600 OD, 390 kg); 24x gusset plate IS 2062 E 250 B (12T x 127W x 150 LG, 43 kg total) | Not started
320SR04 | N1-04 | Nozzle N1 (flange, per detail) | FLANGE: Receipt -> Machining -> Facing -> Drilling -> Inspection | — | SA 105 | Not started
320SR04 | N2-04 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | PIPE: Receipt -> Cutting -> Beveling -> Fit-up -> Welding -> RT/PT -> Inspection | — | Flange SA 105 (DN25 class); Pipe SA 333 Gr 6 (DN25 SCH.XXS, 1270 LG + 170 LG); Elbow SA 234 Gr WPB (DN25 SCH.XXS 90deg LR); Stiffener SA 516 Gr 485 (6T x 50W x 250 LG); Support Pipe SA 106 Gr B (DN200 SCH80 x 115 LG) | Not started
320SR04 | N3-04 | Nozzle N3 (SRN forging + flange + 3x stiffener) | FORGING: Receipt -> Machining -> NDT -> Inspection | — | SRN SA 266 Gr 2; Flange SA 105 (DN125 SCH.XXS CL.600 WNRF); Stiffener SA 516 Gr 485 (6T x 82W x 80 LG) x3 | Not started
320SR04 | N4-04 | Nozzle N4 (coupling) | COUPLING: Receipt -> Thread Inspection -> Dimension Check | — | SA 105, DN15 SCH.XXS x 6000# BSP | Not started
320SR04 | N5-04 | Nozzle N5 (coupling) | COUPLING: Receipt -> Thread Inspection -> Dimension Check | — | SA 105, DN15 SCH.XXS x 6000# BSP | Not started
320SR04 | N6-04 | Nozzle N6 (coupling) | COUPLING: Receipt -> Thread Inspection -> Dimension Check | — | SA 105, DN15 SCH.XXS x 6000# BSP | Not started
320SR04 | M1-04 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | FORGING: Receipt -> Machining -> NDT -> Inspection | — | SRN SA 266 Gr 2 (DN450x22THK ASME 600CL WNRF) | Not started
320SR05 | SHELL-05 | Shell (single course) | PLATE: Receipt -> MTC Verification -> Cutting -> Edge Prep -> Rolling/Forming -> Fit-up -> Welding -> RT/UT -> Grinding -> Inspection | LS-1 | SA 516 Gr 485, normalized fine-grain fully killed | Not started
320SR05 | TOP-HEAD-05 | Top Dished End (head) | DISHED_END: Plate Cutting -> Pressing/Spinning -> Trimming -> NDT -> Inspection | CS-1 | SA 516 Gr 485 | Not started
320SR05 | BOTTOM-HEAD-05 | Bottom Dished End (head) | DISHED_END: Plate Cutting -> Pressing/Spinning -> Trimming -> NDT -> Inspection | CS-2 | SA 516 Gr 485 | Not started
320SR05 | SKIRT-05 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | SKIRT: Plate Rolling -> Welding -> Machining -> Inspection | — | Skirt shell SA 516 Gr 485 (16T x 1062W x 7323 DEV.LG, 977 kg); base ring IS 2062 E 250 B (32T x 2187 ID x 2600 OD, 390 kg); 24x gusset plate IS 2062 E 250 B (12T x 127W x 150 LG, 43 kg total) | Not started
320SR05 | N1-05 | Nozzle N1 (flange, per detail) | FLANGE: Receipt -> Machining -> Facing -> Drilling -> Inspection | — | SA 105 | Not started
320SR05 | N2-05 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | PIPE: Receipt -> Cutting -> Beveling -> Fit-up -> Welding -> RT/PT -> Inspection | — | Flange SA 105 (DN25 class); Pipe SA 333 Gr 6 (DN25 SCH.XXS, 1270 LG + 170 LG); Elbow SA 234 Gr WPB (DN25 SCH.XXS 90deg LR); Stiffener SA 516 Gr 485 (6T x 50W x 250 LG); Support Pipe SA 106 Gr B (DN200 SCH80 x 115 LG) | Not started
320SR05 | N3-05 | Nozzle N3 (SRN forging + flange + 3x stiffener) | FORGING: Receipt -> Machining -> NDT -> Inspection | — | SRN SA 266 Gr 2; Flange SA 105 (DN125 SCH.XXS CL.600 WNRF); Stiffener SA 516 Gr 485 (6T x 82W x 80 LG) x3 | Not started
320SR05 | N4-05 | Nozzle N4 (coupling) | COUPLING: Receipt -> Thread Inspection -> Dimension Check | — | SA 105, DN15 SCH.XXS x 6000# BSP | Not started
320SR05 | N5-05 | Nozzle N5 (coupling) | COUPLING: Receipt -> Thread Inspection -> Dimension Check | — | SA 105, DN15 SCH.XXS x 6000# BSP | Not started
320SR05 | N6-05 | Nozzle N6 (coupling) | COUPLING: Receipt -> Thread Inspection -> Dimension Check | — | SA 105, DN15 SCH.XXS x 6000# BSP | Not started
320SR05 | M1-05 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | FORGING: Receipt -> Machining -> NDT -> Inspection | — | SRN SA 266 Gr 2 (DN450x22THK ASME 600CL WNRF) | Not started
320SR06 | SHELL-06 | Shell (single course) | PLATE: Receipt -> MTC Verification -> Cutting -> Edge Prep -> Rolling/Forming -> Fit-up -> Welding -> RT/UT -> Grinding -> Inspection | LS-1 | SA 516 Gr 485, normalized fine-grain fully killed | Not started
320SR06 | TOP-HEAD-06 | Top Dished End (head) | DISHED_END: Plate Cutting -> Pressing/Spinning -> Trimming -> NDT -> Inspection | CS-1 | SA 516 Gr 485 | Not started
320SR06 | BOTTOM-HEAD-06 | Bottom Dished End (head) | DISHED_END: Plate Cutting -> Pressing/Spinning -> Trimming -> NDT -> Inspection | CS-2 | SA 516 Gr 485 | Not started
320SR06 | SKIRT-06 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | SKIRT: Plate Rolling -> Welding -> Machining -> Inspection | — | Skirt shell SA 516 Gr 485 (16T x 1062W x 7323 DEV.LG, 977 kg); base ring IS 2062 E 250 B (32T x 2187 ID x 2600 OD, 390 kg); 24x gusset plate IS 2062 E 250 B (12T x 127W x 150 LG, 43 kg total) | Not started
320SR06 | N1-06 | Nozzle N1 (flange, per detail) | FLANGE: Receipt -> Machining -> Facing -> Drilling -> Inspection | — | SA 105 | Not started
320SR06 | N2-06 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | PIPE: Receipt -> Cutting -> Beveling -> Fit-up -> Welding -> RT/PT -> Inspection | — | Flange SA 105 (DN25 class); Pipe SA 333 Gr 6 (DN25 SCH.XXS, 1270 LG + 170 LG); Elbow SA 234 Gr WPB (DN25 SCH.XXS 90deg LR); Stiffener SA 516 Gr 485 (6T x 50W x 250 LG); Support Pipe SA 106 Gr B (DN200 SCH80 x 115 LG) | Not started
320SR06 | N3-06 | Nozzle N3 (SRN forging + flange + 3x stiffener) | FORGING: Receipt -> Machining -> NDT -> Inspection | — | SRN SA 266 Gr 2; Flange SA 105 (DN125 SCH.XXS CL.600 WNRF); Stiffener SA 516 Gr 485 (6T x 82W x 80 LG) x3 | Not started
320SR06 | N4-06 | Nozzle N4 (coupling) | COUPLING: Receipt -> Thread Inspection -> Dimension Check | — | SA 105, DN15 SCH.XXS x 6000# BSP | Not started
320SR06 | N5-06 | Nozzle N5 (coupling) | COUPLING: Receipt -> Thread Inspection -> Dimension Check | — | SA 105, DN15 SCH.XXS x 6000# BSP | Not started
320SR06 | N6-06 | Nozzle N6 (coupling) | COUPLING: Receipt -> Thread Inspection -> Dimension Check | — | SA 105, DN15 SCH.XXS x 6000# BSP | Not started
320SR06 | M1-06 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | FORGING: Receipt -> Machining -> NDT -> Inspection | — | SRN SA 266 Gr 2 (DN450x22THK ASME 600CL WNRF) | Not started
320SR07 | SHELL-07 | Shell (single course) | PLATE: Receipt -> MTC Verification -> Cutting -> Edge Prep -> Rolling/Forming -> Fit-up -> Welding -> RT/UT -> Grinding -> Inspection | LS-1 | SA 516 Gr 485, normalized fine-grain fully killed | Not started
320SR07 | TOP-HEAD-07 | Top Dished End (head) | DISHED_END: Plate Cutting -> Pressing/Spinning -> Trimming -> NDT -> Inspection | CS-1 | SA 516 Gr 485 | Not started
320SR07 | BOTTOM-HEAD-07 | Bottom Dished End (head) | DISHED_END: Plate Cutting -> Pressing/Spinning -> Trimming -> NDT -> Inspection | CS-2 | SA 516 Gr 485 | Not started
320SR07 | SKIRT-07 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | SKIRT: Plate Rolling -> Welding -> Machining -> Inspection | — | Skirt shell SA 516 Gr 485 (16T x 1062W x 7323 DEV.LG, 977 kg); base ring IS 2062 E 250 B (32T x 2187 ID x 2600 OD, 390 kg); 24x gusset plate IS 2062 E 250 B (12T x 127W x 150 LG, 43 kg total) | Not started
320SR07 | N1-07 | Nozzle N1 (flange, per detail) | FLANGE: Receipt -> Machining -> Facing -> Drilling -> Inspection | — | SA 105 | Not started
320SR07 | N2-07 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | PIPE: Receipt -> Cutting -> Beveling -> Fit-up -> Welding -> RT/PT -> Inspection | — | Flange SA 105 (DN25 class); Pipe SA 333 Gr 6 (DN25 SCH.XXS, 1270 LG + 170 LG); Elbow SA 234 Gr WPB (DN25 SCH.XXS 90deg LR); Stiffener SA 516 Gr 485 (6T x 50W x 250 LG); Support Pipe SA 106 Gr B (DN200 SCH80 x 115 LG) | Not started
320SR07 | N3-07 | Nozzle N3 (SRN forging + flange + 3x stiffener) | FORGING: Receipt -> Machining -> NDT -> Inspection | — | SRN SA 266 Gr 2; Flange SA 105 (DN125 SCH.XXS CL.600 WNRF); Stiffener SA 516 Gr 485 (6T x 82W x 80 LG) x3 | Not started
320SR07 | N4-07 | Nozzle N4 (coupling) | COUPLING: Receipt -> Thread Inspection -> Dimension Check | — | SA 105, DN15 SCH.XXS x 6000# BSP | Not started
320SR07 | N5-07 | Nozzle N5 (coupling) | COUPLING: Receipt -> Thread Inspection -> Dimension Check | — | SA 105, DN15 SCH.XXS x 6000# BSP | Not started
320SR07 | N6-07 | Nozzle N6 (coupling) | COUPLING: Receipt -> Thread Inspection -> Dimension Check | — | SA 105, DN15 SCH.XXS x 6000# BSP | Not started
320SR07 | M1-07 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | FORGING: Receipt -> Machining -> NDT -> Inspection | — | SRN SA 266 Gr 2 (DN450x22THK ASME 600CL WNRF) | Not started
320SR08 | SHELL-08 | Shell (single course) | PLATE: Receipt -> MTC Verification -> Cutting -> Edge Prep -> Rolling/Forming -> Fit-up -> Welding -> RT/UT -> Grinding -> Inspection | LS-1 | SA 516 Gr 485, normalized fine-grain fully killed | Not started
320SR08 | TOP-HEAD-08 | Top Dished End (head) | DISHED_END: Plate Cutting -> Pressing/Spinning -> Trimming -> NDT -> Inspection | CS-1 | SA 516 Gr 485 | Not started
320SR08 | BOTTOM-HEAD-08 | Bottom Dished End (head) | DISHED_END: Plate Cutting -> Pressing/Spinning -> Trimming -> NDT -> Inspection | CS-2 | SA 516 Gr 485 | Not started
320SR08 | SKIRT-08 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | SKIRT: Plate Rolling -> Welding -> Machining -> Inspection | — | Skirt shell SA 516 Gr 485 (16T x 1062W x 7323 DEV.LG, 977 kg); base ring IS 2062 E 250 B (32T x 2187 ID x 2600 OD, 390 kg); 24x gusset plate IS 2062 E 250 B (12T x 127W x 150 LG, 43 kg total) | Not started
320SR08 | N1-08 | Nozzle N1 (flange, per detail) | FLANGE: Receipt -> Machining -> Facing -> Drilling -> Inspection | — | SA 105 | Not started
320SR08 | N2-08 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | PIPE: Receipt -> Cutting -> Beveling -> Fit-up -> Welding -> RT/PT -> Inspection | — | Flange SA 105 (DN25 class); Pipe SA 333 Gr 6 (DN25 SCH.XXS, 1270 LG + 170 LG); Elbow SA 234 Gr WPB (DN25 SCH.XXS 90deg LR); Stiffener SA 516 Gr 485 (6T x 50W x 250 LG); Support Pipe SA 106 Gr B (DN200 SCH80 x 115 LG) | Not started
320SR08 | N3-08 | Nozzle N3 (SRN forging + flange + 3x stiffener) | FORGING: Receipt -> Machining -> NDT -> Inspection | — | SRN SA 266 Gr 2; Flange SA 105 (DN125 SCH.XXS CL.600 WNRF); Stiffener SA 516 Gr 485 (6T x 82W x 80 LG) x3 | Not started
320SR08 | N4-08 | Nozzle N4 (coupling) | COUPLING: Receipt -> Thread Inspection -> Dimension Check | — | SA 105, DN15 SCH.XXS x 6000# BSP | Not started
320SR08 | N5-08 | Nozzle N5 (coupling) | COUPLING: Receipt -> Thread Inspection -> Dimension Check | — | SA 105, DN15 SCH.XXS x 6000# BSP | Not started
320SR08 | N6-08 | Nozzle N6 (coupling) | COUPLING: Receipt -> Thread Inspection -> Dimension Check | — | SA 105, DN15 SCH.XXS x 6000# BSP | Not started
320SR08 | M1-08 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | FORGING: Receipt -> Machining -> NDT -> Inspection | — | SRN SA 266 Gr 2 (DN450x22THK ASME 600CL WNRF) | Not started
320SR09 | SHELL-09 | Shell (single course) | PLATE: Receipt -> MTC Verification -> Cutting -> Edge Prep -> Rolling/Forming -> Fit-up -> Welding -> RT/UT -> Grinding -> Inspection | LS-1 | SA 516 Gr 485, normalized fine-grain fully killed | Not started
320SR09 | TOP-HEAD-09 | Top Dished End (head) | DISHED_END: Plate Cutting -> Pressing/Spinning -> Trimming -> NDT -> Inspection | CS-1 | SA 516 Gr 485 | Not started
320SR09 | BOTTOM-HEAD-09 | Bottom Dished End (head) | DISHED_END: Plate Cutting -> Pressing/Spinning -> Trimming -> NDT -> Inspection | CS-2 | SA 516 Gr 485 | Not started
320SR09 | SKIRT-09 | Skirt assembly (skirt shell + base ring + 24 gusset plates, tracked as one fabrication unit) | SKIRT: Plate Rolling -> Welding -> Machining -> Inspection | — | Skirt shell SA 516 Gr 485 (16T x 1062W x 7323 DEV.LG, 977 kg); base ring IS 2062 E 250 B (32T x 2187 ID x 2600 OD, 390 kg); 24x gusset plate IS 2062 E 250 B (12T x 127W x 150 LG, 43 kg total) | Not started
320SR09 | N1-09 | Nozzle N1 (flange, per detail) | FLANGE: Receipt -> Machining -> Facing -> Drilling -> Inspection | — | SA 105 | Not started
320SR09 | N2-09 | Nozzle N2 sub-assembly (flange + 2x pipe segments + 90 deg elbow + stiffener + support pipe) | PIPE: Receipt -> Cutting -> Beveling -> Fit-up -> Welding -> RT/PT -> Inspection | — | Flange SA 105 (DN25 class); Pipe SA 333 Gr 6 (DN25 SCH.XXS, 1270 LG + 170 LG); Elbow SA 234 Gr WPB (DN25 SCH.XXS 90deg LR); Stiffener SA 516 Gr 485 (6T x 50W x 250 LG); Support Pipe SA 106 Gr B (DN200 SCH80 x 115 LG) | Not started
320SR09 | N3-09 | Nozzle N3 (SRN forging + flange + 3x stiffener) | FORGING: Receipt -> Machining -> NDT -> Inspection | — | SRN SA 266 Gr 2; Flange SA 105 (DN125 SCH.XXS CL.600 WNRF); Stiffener SA 516 Gr 485 (6T x 82W x 80 LG) x3 | Not started
320SR09 | N4-09 | Nozzle N4 (coupling) | COUPLING: Receipt -> Thread Inspection -> Dimension Check | — | SA 105, DN15 SCH.XXS x 6000# BSP | Not started
320SR09 | N5-09 | Nozzle N5 (coupling) | COUPLING: Receipt -> Thread Inspection -> Dimension Check | — | SA 105, DN15 SCH.XXS x 6000# BSP | Not started
320SR09 | N6-09 | Nozzle N6 (coupling) | COUPLING: Receipt -> Thread Inspection -> Dimension Check | — | SA 105, DN15 SCH.XXS x 6000# BSP | Not started
320SR09 | M1-09 | Manway M1 (SRN forging; blind flange, gasket, bolting set and davit/hinge tracked as BOM hardware only, not a separate fabrication route) | FORGING: Receipt -> Machining -> NDT -> Inspection | — | SRN SA 266 Gr 2 (DN450x22THK ASME 600CL WNRF) | Not started

## Assembly & Weld Checklist
Assembly & Weld Sequence Checklist
54 QCP checkpoints, grouped by sub-assembly, already live in the app's QCP data. P=Perform W=Witness H=Hold R=Review.
Pale-yellow cells (Status / Remarks) are for QC to fill in as each checkpoint clears. Red = Hold point, amber = Witness point.
Sub-assembly | Sr No | Activity | DESPL | BUYER TPI | Process link | Status (per unit) | Remarks
A. Document & Procedure Gate | 1.1 | Drawing Approval | P | R | #1, #2 | Pending
A. Document & Procedure Gate | 1.2 | Review And Approval Of Quality Contol Plan | P | R | #1, #2 | Pending
A. Document & Procedure Gate | 1.3 | Hot Forming Proceude, Ht Procedure, Rt Procedure, Pt Procedure, Paut & Tofd Procedure | H | R | #1, #2 | Pending
A. Document & Procedure Gate | 2.1 | Welding Procedure & Performance Qualification | P | R | #2 | Pending
B. Material Inspection & Traceability | 3.1 | Pressure Part - Plates,Pipes/Forgings/Flange/ Fittings | H | W | #10, #11 | Pending
B. Material Inspection & Traceability | 3.2 | Non Pressure Parts & Attachment To Pressure Parts | H | R | #10, #11 | Pending
B. Material Inspection & Traceability | 3.3 | Welding Consumable | R | R | #10, #11 | Pending
B. Material Inspection & Traceability | 3.4 | Weld Plan/Weld Map | P | R | #10, #11 | Pending
C. Shell & Head Prep | 4.1 | Transfer Of Marking And Cutting (Shell And Dished End) | H | R | #12, #13, #14, #15, #16, #17, #18, #19, #20 | Pending
D. Head Sub-Assembly | 4.2 | Inspection Of Top & Bottom Dished | R | R | #12, #13, #14, #15, #16, #17, #18, #19, #20 | Pending
D. Head Sub-Assembly | 4.2 | Simulation Heat Treatment Of Test Coupon After Forming & Testing | R | R | #12, #13, #14, #15, #16, #17, #18, #19, #20 | Pending
D. Head Sub-Assembly | 4.4 | Weld Edge Preparation Of Top & Bottom Dished End | P | R | #12, #13, #14, #15, #16, #17, #18, #19, #20 | Pending
E. Shell Sub-Assembly (LS-1) | 4.5 | Shell Weld Edge Preparation | P | R | #12, #13, #14, #15, #16, #17, #18, #19, #20 | Pending
E. Shell Sub-Assembly (LS-1) | 4.5 | L' Seam Set Up Of Shell (Ls-1 ) Along With Ptc | P | R | #12, #13, #14, #15, #16, #17, #18, #19, #20 | Pending
E. Shell Sub-Assembly (LS-1) | 4.5 | Weld Long Seam Of Shell (Ls-1 ) | P | R | #12, #13, #14, #15, #16, #17, #18, #19, #20 | Pending
E. Shell Sub-Assembly (LS-1) | 4.5 | Weld Visual Of Ls-1 | P | R | #12, #13, #14, #15, #16, #17, #18, #19, #20 | Pending
E. Shell Sub-Assembly (LS-1) | 4.5 | Paut/Tofd Of Ls-1 | P | W | #12, #13, #14, #15, #16, #17, #18, #19, #20 | Pending
F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Nozzle To Flange/Elbow Set Up (M1/N2/N3) | P | R | #12, #13, #14, #15, #16, #17, #18, #19, #20 | Pending
F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Weld Of Nozzle To Flange/Elbow (M1/N2/N3) | P | R | #12, #13, #14, #15, #16, #17, #18, #19, #20 | Pending
F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Weld Visual Of Cs Joint Nozzle M1/N2/N3 | P | R | #12, #13, #14, #15, #16, #17, #18, #19, #20 | Pending
F. Nozzle Sub-Assembly (flange/elbow) | 4.6 | Rt Circ Seam Of Nozzle Pipe To Flange (M1/N2/N3) | P | R | #12, #13, #14, #15, #16, #17, #18, #19, #20 | Pending
G. Shell + Bottom Head (CS-2) | 4.7 | Bottom Dished End To Shell Set Up (Cs-2) | P | R | #12, #13, #14, #15, #16, #17, #18, #19, #20 | Pending
G. Shell + Bottom Head (CS-2) | 4.7 | Weld Circ Seam Of Bottom Dishend To Shell (Cs-2) | P | R | #12, #13, #14, #15, #16, #17, #18, #19, #20 | Pending
G. Shell + Bottom Head (CS-2) | 4.7 | Weld Visual Of Cs -2 | P | R | #12, #13, #14, #15, #16, #17, #18, #19, #20 | Pending
G. Shell + Bottom Head (CS-2) | 4.7 | Paut/Tofd Of Cs-2 | P | W | #12, #13, #14, #15, #16, #17, #18, #19, #20 | Pending
H. Nozzle & Manway Sub-Assembly | 4.8 | Marking For Nozzle On Shell And Dished End (M1, N1 To N6) | P | R | #12, #13, #14, #15, #16, #17, #18, #19, #20 | Pending
H. Nozzle & Manway Sub-Assembly | 4.8 | Nozzle To Shell & Dished End Set Up (M1/N1/N2/N3/N4/N5/N6) | P | R | #12, #13, #14, #15, #16, #17, #18, #19, #20 | Pending
H. Nozzle & Manway Sub-Assembly | 4.8 | Weld Of Nozzle To Shell & Dished End (M1/N1/N2/N3/N4/N5/N6) | P | R | #12, #13, #14, #15, #16, #17, #18, #19, #20 | Pending
H. Nozzle & Manway Sub-Assembly | 4.8 | Weld Visual Of Nozzle To Shell & Dished End (M1/N1/N2/N3/N4/N5/N6) | P | R | #12, #13, #14, #15, #16, #17, #18, #19, #20 | Pending
H. Nozzle & Manway Sub-Assembly | 4.8 | Ultrasonic Test Of Nozzle To Shell & Dished End (M1/N1/N2/N3) | P | R | #12, #13, #14, #15, #16, #17, #18, #19, #20 | Pending
I. Final Closure Gate | 4.9 | Clearance Of Shell Before Closing Dished End Set Up | P | R | #12, #13, #14, #15, #16, #17, #18, #19, #20 | Pending
J. Shell + Top Head (CS-1) | 4.10 | Top Dished End To Shell Set Up (Cs- 1) | P | R | #12, #13, #14, #15, #16, #17, #18, #19, #20 | Pending
J. Shell + Top Head (CS-1) | 4.10 | Weld Circ Seam Of Top Dishend To Shell (Cs-1) | P | R | #12, #13, #14, #15, #16, #17, #18, #19, #20 | Pending
J. Shell + Top Head (CS-1) | 4.10 | Weld Visual Of Cs -1 | P | R | #12, #13, #14, #15, #16, #17, #18, #19, #20 | Pending
J. Shell + Top Head (CS-1) | 4.10 | Paut/Tofd Of Cs-1 | P | W | #12, #13, #14, #15, #16, #17, #18, #19, #20 | Pending
K. Attachments Sub-Assembly | 4.11 | Lifting Lug & Name Plate Bracket Set Up | P | R | #12, #13, #14, #15, #16, #17, #18, #19, #20 | Pending
K. Attachments Sub-Assembly | 4.12 | Weld Of Lifting Lug | P | R | #12, #13, #14, #15, #16, #17, #18, #19, #20 | Pending
K. Attachments Sub-Assembly | 4.12 | Weld Of Name Plate Bracket | P | R | #12, #13, #14, #15, #16, #17, #18, #19, #20 | Pending
L. Skirt Sub-Assembly | 4.13 | Skirt Support Set Up | P | R | #12, #13, #14, #15, #16, #17, #18, #19, #20 | Pending
L. Skirt Sub-Assembly | 4.14 | Weld Skirt Support | P | R | #12, #13, #14, #15, #16, #17, #18, #19, #20 | Pending
M. Pre-PWHT Gate | 4.15 | Clearance Befor Pwht | P | W | #12, #13, #14, #15, #16, #17, #18, #19, #20 | Pending
N. Heat Treatment & Post-PWHT NDT | 5.1 | Inspection Of Vessel Heat Treatment | R | R | #21, #22 | Pending
N. Heat Treatment & Post-PWHT NDT | 5.2 | Weld Visual Of All Weld Joints | P | W | #21, #22 | Pending
N. Heat Treatment & Post-PWHT NDT | 5.3 | Mpt Of All Weld Joint | P | W | #21, #22 | Pending
N. Heat Treatment & Post-PWHT NDT | 5.4 | Rt Testing On All Butt Weld Joints(M1/N2/N3) Paut/Tofd For L'Seam & C'Seam Joints. (After Pwht). | P | W | #21, #22 | Pending
O. Hydrostatic Test | 6.1 | Clearance For Hydrostatic Test | P | R | #27, #28 | Pending
O. Hydrostatic Test | 6.2 | Before Hydrostatic Test Clearance | P | R | #27, #28 | Pending
O. Hydrostatic Test | 6.3 | Hydrostatic Test | P | W | #27, #28 | Pending
O. Hydrostatic Test | 6.4 | Mpt / Lpt All Weld Joints After Hydro Test | P | W | #27, #28 | Pending
P. Surface Treatment & Painting | 7.1 | Cleaning & Surface Preparation | P | R | #29, #30 | Pending
P. Surface Treatment & Painting | 7.2 | Painting | P | W | #29, #30 | Pending
Q. Final Inspection, Nameplate & MDR | 8.1 | Verification Of Name Plate | P | R | #31, #32 | Pending
Q. Final Inspection, Nameplate & MDR | 8.2 | Attachment Of Name Plate To Name Plate Bracket | P | R | #31, #32 | Pending
Q. Final Inspection, Nameplate & MDR | 9.1 | Documentation | R | R | #31, #32 | Pending

## Dev Notes
Dev Notes — status vs. this workbook
For whoever picks this up on the software side. Full detail in the companion .md document.
1. Live app is showing wrong dates
DESPL-320's schedule (324 ProcessPlan rows, seeded 22 Aug) was generated off a synthetic ~10-week-back placeholder date, not the real 20-Nov-2026 order date. Set Job.orderDate=2026-11-20 and Job.committedDeliveryDate=2027-04-08, then run `pnpm db:bootstrap DESPL-320` to regenerate a real ScheduleRun.
2. QCP / assembly checklist — already done
The 54-checkpoint QCP (Assembly & Weld Checklist tab) is already live in seed/qcp-templates.json and seeded into the DB. No new seeding needed here.
3. BOM / Sub-Assembly Register — missing, new work
DESPL-320 has zero BomItem or Component rows today (it was only ever seeded from the QCP document header, not a BOM CSV like DE0463/DE0467). The Sub-Assembly Register tab in this workbook is that missing data — see seed/despl-320-components.json for the machine-readable version, structured to plug into scripts/seed-despl320-and-de0467.ts the same way the existing DE0467 ingestion block does.
4. Corrected an arithmetic error
docs/DESPL-320-DEV-READY-BOM-SCHEDULE-v1.md §4.4 said '10 trackable components' but its own list sums to 11 (Shell, Top Head, Bottom Head, Skirt + M1/N1-N6). This workbook uses 11 x 9 = 99 rows.
5. Open item
C1 (docs/BUILD-SPEC-v2.md §7) — whether the 119-day envelope should exclude company holidays beyond Sundays. Still unconfirmed by SJ. Doesn't block anything above.