## Read Me
Standard Parts Master for Pressure Vessels & Heat Exchangers
HE + PV SOURCE MASTER — PROPOSED BASELINES COMPLETE FOR REVIEW, NOT APPROVED FOR TRACKER LOAD
The approved HP Air Receiver GA has been added as a light-yellow PV dataset: 48 BOM lines, 30 new part families, 155 route steps and 31 assembly steps. Drawing facts are controlled in PV Drawing Basis; proposed time norms and shop methods remain on HOLD pending Production Head/PPC approval.
Document control
Prepared by
Checked by (Production Head)
Date
Why we need this
Every job's BOM is different, but the parts it is made of repeat. This master is the list of all standard parts and how each one is made. When a new job is created, parts will be selected from this list and job-specific sizes and quantities entered. The tracker then creates the production steps for each part, tracks them department-wise, rolls progress up to the equipment stages and calculates weights.
Sheets
Parts Master | One row per standard part: equipment, group, make/buy, raw material, MOC, dimensions to enter, weight basis, spare, who filled/checked it, status.
Part Routes | One row per manufacturing step: operation, department, the equipment stage it counts toward, standard time, conditions, acceptance standard, record.
Assembly Sequence | How parts are joined into sub-assemblies and the complete equipment, with weld joint references.
New Operations | Steps that do not fit any operation in the fixed list, with the reason.
HE Stages | Whole-equipment stages for heat exchangers, with durations and predecessors.
PV Stages (ref) | The 36 PV stages already used in the tracker, for reference only.
Material Master | Density for every material.
SP40 Drawing Basis | Traceability register for the 25-page SP40 MED Train 1 drawing package, including exact design facts, drawing-required operations and unresolved controls.
How to fill
1 | Start with these 10 pilot parts: Shell Course, Dished End, Nozzle Neck, Nozzle Flange, Tube Sheet, Tube, Baffle, Saddle, Stud with Two Nuts, Gasket. Send the file back so we can review it together before the full list.
2 | Fill 'HE Stages' first. Part Routes and Assembly Sequence need its stage numbers.
3 | Use only the operations in the dropdown. If a step does not fit, add it to 'New Operations'. Please don't rename an existing operation.
4 | Number steps 10, 20, 30… so steps can be inserted later without renumbering.
5 | For every step, fill the stage number it counts toward: PV stage, HE stage, or both if the part is used in both.
6 | If a part can be made in more than one way, give each way a variant letter (A, B) and list the steps for each.
7 | If a step applies only sometimes, set Conditional = Yes and write the rule.
8 | Give standard time for every step with its unit and basis (per piece, per metre of weld, per tube…).
9 | Set 'Route Source' honestly. 'Assumed – to be confirmed' is allowed, but those parts cannot be approved until confirmed.
10 | Only parts with Status = 'Approved by Production Head' will be loaded into the tracker.
Colour legend
Grey rows | Example only. Replace or delete once your data is in.
Yellow cells | To be filled by the team.
Blue cells | Filled automatically. Do not type here.
Green rows | Reference data from the tracker. Do not edit.
Orange cells | Proposed planning value or approval-sensitive control. Validate before tracker load.
PV Drawing Basis | Approved GA metadata, design data, nozzle schedule and all 48 BOM lines with master-code traceability.
PV Review | Live PV completeness controls, design summary and approval gates.
Light-yellow PV rows | Drawing-backed pressure-vessel entries or proposed planning values requiring joint review.
Orange PV cells | Ambiguous source value, unapproved standard time, or approval-sensitive control.

## Parts Master
HE + PV MASTER — LIGHT-YELLOW PV ROWS ARE DRAWING-BACKED OR PROPOSED; ALL DRAFT ROUTES/TIMES REQUIRE PRODUCTION HEAD APPROVAL.
One row per standard part. Part Code is your choice (suggested: 3-letter group + number). 'Filled by' and 'Checked by' must be real names; only parts with Status = 'Approved by Production Head' will be loaded into the tracker. The three blue columns check your entries automatically: 'Steps entered' must not be 0, and the other two should be 0 before approval.
Example? | Part Code | Part Name | Equipment | Assembly Group | Make / Buy | Raw Material Form | Typical MOC | Dimensions to enter per job | Weight Basis | Route Variants (A, B…) | Also a Spare? | Route Source | Filled by | Checked by | Status | Remarks | Steps entered (auto) | Steps missing stage no. (auto) | Steps marked 'Assumed' (auto)
PILOT – SOURCE DRAFT | SHL-01 | Shell Course | PV + HE | Shell | Made in-house | Plate | SA240 S32205 | ID 3000; thickness 10; developed length 9456; course width/length per job | Rolled shell (ID, T, L) | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | SP40 overall material list: ten shell plates, PL.10 THK × 9456 developed length; widths 1240, 1490 and 560. Route remains unapproved. PV drawing item 101: SA516 Gr.70 shell, 45T × 3750W × 7509 developed length; 9947 kg. | 9 | 0 | 9
PILOT – SOURCE DRAFT | HED-01 | Dished End | PV + HE | Heads / Dished Ends | Made in-house | Plate | SA240 S32205 | ID 3000; raw thickness 12; formed thickness 10 min; 2:1 semi-ellipsoidal; ICR 2700; IKR 510; straight face 50; blank dia 3772 | Dished head (to be defined) | A, B | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | SP40-02-03-04-001 Rev.0: left/right cold-formed heads; full DP both sides with TPI; template profile check. Variant B added from drawing. PV drawing item 102: two SA516 Gr.70 dished ends, 45T nominal × 2925 blank dia; 4748 kg total. | 16 | 0 | 16
PILOT – SOURCE DRAFT | NOZ-01 | Nozzle Neck | PV + HE | Nozzles | Made in-house | Pipe | SA790 S32205 | OD, thickness, cut length, NB/tag, projection; drawing range includes OD 21.3 to 813 | Pipe / Tube (OD, T, L) | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | SP40 overall material list confirms pipe-neck nozzle construction in SA790 S32205; fabrication route still requires shop approval. PV items 207, 209 and 236 add SA333 Gr.6 and SA106 Gr.B nozzle-neck variants. | 9 | 0 | 9
PILOT – SOURCE DRAFT | FLG-01 | Nozzle Flange | PV + HE | Flanges | Bought + machined in-house | Forging | SA182 Gr.F60 | NB, class, SORF type, facing, bore, OD, ID, thickness | Ring / Flange (OD, ID, T) | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | SP40 overall material list shows SORF flanges, Class 150, SA182 Gr.F60. Make/buy and machining route remain to be confirmed. PV items 205, 206, 213 and 216 add SA105 Class 300 WNRF variants. | 5 | 0 | 5
PILOT – SOURCE DRAFT | TSH-01 | Tube Sheet | HE | Tube Bundle | Bought + machined in-house | Forging | SA 266 Gr.2 / SA 182 / SB 171 Alloy 464 | OD, thickness, hole count, hole diameter, pitch, layout, pass partition grooves | Disc (OD, T) | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | Existing forged tubesheet family retained. SP40 uses a separate fabricated-plate family TSH-02. | 7 | 0 | 7
PILOT – SOURCE DRAFT | TUB-01 | Tube | HE | Tube Bundle | Bought-out | Tube | SB338 Gr.2 titanium / other approved tube materials | OD, wall thickness, effective length, overall length, quantity; SP40: OD 21.3 × 0.4, 3000 overall (Effects 1–8), 2260 overall (Effect 9) | Pipe / Tube (OD, T, L) | A | Yes | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | SP40-02-02-11-04 Rev.0 specifies tubes tight-fit with EPDM grommets; no expansion, seal weld or joint test is stated. | 5 | 0 | 5
PILOT – SOURCE DRAFT | BAF-01 | Baffle | HE | Tube Bundle | Made in-house | Plate | SA 515 Gr.60 / CS / SS | OD, thickness, baffle cut %, hole count, hole diameter, pitch, orientation | Disc (OD, T) | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | Existing generic baffle retained. SP40 drawing package separately defines an EPDM baffle-grommet family. | 6 | 0 | 6
PILOT – SOURCE DRAFT | SAD-01 | Saddle | PV + HE | Externals / Supports | Made in-house | Assembly (made of other parts) | Metal structure per saddle drawing; PTFE sliding sheet | vessel OD; saddle steel-part dimensions; fixed/sliding type; PTFE sheet 10 × 450 × 3030 | Sum of child parts | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | SP40-02-02-11-01 Rev.0 confirms saddle assembly and food-grade PTFE sliding sheet; metal material/route requires review. | 10 | 0 | 10
PILOT – SOURCE DRAFT | STD-01 | Stud with Two Nuts | PV + HE | Bolting & Gaskets | Bought-out | Standard item (catalogue) | SA193 Gr.B8M stud with SA194 Gr.8M nuts | diameter, thread, length, quantity; SP40 examples 1/2 in × 75/80 and 5/8 in × 100 | Catalogue weight (per piece) | A | Yes | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | SP40 overall material list confirms B8M studs, Gr.8M nuts and separate SS316L washers. PV item 220: 24 sets SA193 B7 studs / SA194 2H heavy hex nuts, 1-1/4 UNC × 210. | 3 | 0 | 3
PILOT – SOURCE DRAFT | GAS-01 | Gasket | PV + HE | Bolting & Gaskets | Bought-out | Standard item (catalogue) | EPDM food grade / other approved gasket grade | OD, ID, thickness, class/construction, quantity; SP40 examples 3 THK, OD/ID 48/21, 67/33 and 105/60 | Catalogue weight (per piece) | A | Yes | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | SP40 overall material list specifies EPDM gaskets. Density and exact compound remain vendor-certificate dependent. PV item 219: DN450 Class 300 SS316L spiral-wound Grafoil gasket with CS outer ring. | 3 | 0 | 3
DRAWING SOURCE DRAFT | RFP-01 | Reinforcement Pad | HE | Nozzles | Made in-house | Plate | SA240 S32205 | OD, ID, thickness, quantity | Ring / Flange (OD, ID, T) | A | No | Client / QAP requirement |  |  | Draft | SP40 drawing BOM includes nozzle and piping-support reinforcement pads; manufacturing route not stated. | 0 | 0 | 0
DRAWING SOURCE DRAFT | TSH-02 | Tube Sheet (Fabricated Plate) | HE | Tube Bundle | Made in-house | Plate | SA240 S32205 | OD, thickness, plate joints, hole count/layout, hole dia, pitch, chamfer, finish | Disc (OD, T) | A | No | Client / QAP requirement |  |  | Draft | SP40-02-03-04-002 Rev.0: OD 3000 × 10; hole Ø24.7; 28.78 pitch; 1.6 micron finish; six effect-specific layouts. | 7 | 7 | 0
DRAWING SOURCE DRAFT | NUT-01 | Hex Nut | HE | Bolting & Gaskets | Bought-out | Standard item (catalogue) | SA194 Gr.8M | thread diameter, grade, quantity | Catalogue weight (per piece) | A | Yes | Client / QAP requirement |  |  | Draft | Listed separately in SP40 nozzle BOM. | 0 | 0 | 0
DRAWING SOURCE DRAFT | WSH-01 | Washer | HE | Bolting & Gaskets | Bought-out | Standard item (catalogue) | SS316L | nominal diameter, OD, ID, thickness, quantity | Catalogue weight (per piece) | A | Yes | Client / QAP requirement |  |  | Draft | Listed separately in SP40 nozzle BOM. | 0 | 0 | 0
DRAWING SOURCE DRAFT | GRM-01 | Tube Grommet | HE | Tube Bundle | Bought-out | Standard item (catalogue) | EPDM food grade | tube OD, tubesheet hole, profile dimensions, Shore hardness, quantity | Catalogue weight (per piece) | A | Yes | Client / QAP requirement |  |  | Draft | SP40-02-02-11-04/-05 Rev.0: tube is tight-fit with grommet; no expansion or seal weld stated. | 0 | 0 | 0
DRAWING SOURCE DRAFT | BGM-01 | Baffle Grommet | HE | Tube Bundle | Bought-out | Standard item (catalogue) | EPDM food grade | tube OD, baffle hole, profile dimensions, Shore hardness, quantity | Catalogue weight (per piece) | A | Yes | Client / QAP requirement |  |  | Draft | SP40-02-02-11-07 Rev.0 requires food-grade EPDM certificate and Shore hardness. | 0 | 0 | 0
DRAWING SOURCE DRAFT | PTF-01 | PTFE Sliding Sheet | HE | Externals / Supports | Bought + fabricated in-house | Plate | PTFE food grade | thickness, width, length, hole pattern, quantity | Plate (L x W x T) | A | No | Client / QAP requirement |  |  | Draft | SP40 saddle detail: 10 THK × 450 × 3030; food-grade material. | 0 | 0 | 0
DRAWING SOURCE DRAFT | MNH-01 | Manhole Assembly | HE | Nozzles | Bought + fabricated in-house | Assembly (made of other parts) | Per approved manhole drawing | ID/NB, neck, cover, flange, bolting, gasket, quantity | Sum of child parts | A | No | Client / QAP requirement |  |  | Draft | SP40 overall material list references four ID590 manholes to SP40-02-02-11-02. | 0 | 0 | 0
DRAWING SOURCE DRAFT | HNH-01 | Handhole Assembly | HE | Nozzles | Bought + fabricated in-house | Assembly (made of other parts) | Per approved handhole drawing | NB, neck, cover, flange, bolting, gasket, quantity | Sum of child parts | A | No | Client / QAP requirement |  |  | Draft | SP40 overall material list references one NB300 handhole. | 0 | 0 | 0
DRAWING SOURCE DRAFT | VGL-01 | View Glass | HE | Nozzles | Bought-out | Standard item (catalogue) | Toughened borosilicate | diameter, thickness, rating, quantity | Catalogue weight (per piece) | A | Yes | Client / QAP requirement |  |  | Draft | SP40-02-02-11-03 Rev.0; three view-glass assemblies in overall material list. | 0 | 0 | 0
DRAWING SOURCE DRAFT | NCG-01 | NCG Box Assembly | HE | Internals | Made in-house | Assembly (made of other parts) | SA240 S32205 | effect/location, plate dimensions, tube-sheet interface, quantity | Sum of child parts | A | No | Client / QAP requirement |  |  | Draft | SP40-02-03-04-006 Rev.0 defines Effect 1.1, 2.1 and 3.1 NCG boxes. | 0 | 0 | 0
DRAWING SOURCE DRAFT | JTB-01 | J Tube | HE | Internals | Made in-house | Pipe | SA790 S32205 | OD, thickness, developed/cut length, bend geometry, quantity | Pipe / Tube (OD, T, L) | A | No | Client / QAP requirement |  |  | Draft | SP40-02-03-04-007 Rev.0 NCG nozzle and J-tube details. | 0 | 0 | 0
DRAWING SOURCE DRAFT | DEM-01 | Demister Assembly | HE | Internals | Bought + fabricated in-house | Assembly (made of other parts) | Per approved demister drawing | effect/location, OD/plan dimensions, support details, quantity | Sum of child parts | A | No | Client / QAP requirement |  |  | Draft | SP40-02-03-04-004 Rev.0 contains separate Effect 1, 2 and 3 demister details. | 0 | 0 | 0
DRAWING SOURCE DRAFT | IGR-01 | Internal Grating | HE | Internals | Made in-house | Assembly (made of other parts) | SA240 / SA720 S32205 as printed | plate thickness, profile dimensions, quantity | Sum of child parts | A | No | Client / QAP requirement |  |  | Draft | SP40-02-03-04-003 Sheet 02. Verify printed SA720 specification before approval. | 0 | 0 | 0
DRAWING SOURCE DRAFT | IDA-01 | Internal Door Assembly | HE | Internals | Made in-house | Assembly (made of other parts) | Per approved internal-door drawings | effect/location, opening, plate/rib dimensions, quantity | Sum of child parts | A | No | Client / QAP requirement |  |  | Draft | Six internal-door details are referenced by the SP40 overall material list. | 0 | 0 | 0
DRAWING SOURCE DRAFT | LUG-01 | Lifting Lug | HE | Externals / Supports | Made in-house | Plate | Per SP40 external-attachment drawing | plate profile, thickness, hole diameter, quantity | Plate (L x W x T) | A | No | Client / QAP requirement |  |  | Draft | SP40-02-03-04-008 Rev.0 includes typical lifting-lug detail. | 0 | 0 | 0
DRAWING SOURCE DRAFT | PSP-01 | Piping Support Pad | HE | Externals / Supports | Made in-house | Plate | SA240 S32205 | length, width, thickness, shell radius, quantity | Plate (L x W x T) | A | No | Client / QAP requirement |  |  | Draft | SP40 overall BOM: PL.10 × 200 × 200, quantity 12. | 0 | 0 | 0
DRAWING SOURCE DRAFT | PPL-01 | Partition Plate | HE | Internals | Made in-house | Plate | SA240 S32205 | thickness, profile, location/effect, quantity | Plate (L x W x T) | A | No | Client / QAP requirement |  |  | Draft | Partition plates shown in SP40 internal-arrangement/grating drawings; route not stated. | 0 | 0 | 0
DRAWING SOURCE DRAFT | GSP-01 | Gusset Plate | HE | Internals | Made in-house | Plate | SA240 S32205 | profile, thickness, quantity | Plate (L x W x T) | A | No | Client / QAP requirement |  |  | Draft | Gusset plates shown in SP40 demister/internal details; route not stated. | 0 | 0 | 0
DRAWING SOURCE DRAFT | SUP-01 | Support Plate | HE | Internals | Made in-house | Plate | SA240 S32205 | profile, thickness, quantity | Plate (L x W x T) | A | No | Client / QAP requirement |  |  | Draft | Support plates shown in SP40 demister/internal details; route not stated. | 0 | 0 | 0
PV DRAWING SOURCE | SKT-01 | Skirt Shell | PV | Externals / Supports | Made in-house | Plate | SA 516 Gr.70 | Thickness, width, developed length, vessel/skirt diameter | Rolled shell (ID, T, L) | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | Drawing item 201; 16T × 837W × 7499 developed length; 789 kg | 9 | 0 | 9
PV DRAWING SOURCE | SBR-01 | Skirt Base Ring | PV | Externals / Supports | Made in-house | Plate | IS 2062 E250B | Thickness, ID, OD, bolt-hole count/PCD | Ring / Flange (OD, ID, T) | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | Drawing item 202; 32T × 2240 ID × 2700 OD; 448 kg | 6 | 0 | 6
PV DRAWING SOURCE | GSP-02 | Gusset Plate (PV Support) | PV | Externals / Supports | Made in-house | Plate | IS 2062 E250B | Thickness, width, length, profile, quantity | Plate (L x W x T) | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | Drawing item 203; qty 32; 12T × 150W × 151 length | 6 | 0 | 6
PV DRAWING SOURCE | ERT-01 | Earthing Plate | PV | Externals / Supports | Made in-house | Plate | SS 304 | Thickness, width, length, hole size/count | Plate (L x W x T) | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | Drawing item 204; qty 2; detail requires four holes | 6 | 0 | 6
PV DRAWING SOURCE | RFP-02 | Nozzle Reinforcement Pad | PV | Nozzles | Made in-house | Plate | SA 516 Gr.70 | Thickness, OD, ID, vent-hole size, curvature | Ring / Flange (OD, ID, T) | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | Drawing item 205A; final dimension unclear in source crop | 6 | 0 | 6
PV DRAWING SOURCE | ELB-01 | Nozzle Elbow | PV | Nozzles | Bought-out | Pipe fitting | SA 234 WPB | DN/NPS, schedule, angle, radius | Catalogue weight (per piece) | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | Drawing item 208; DN25 Sch XXS 90° LR | 3 | 0 | 3
PV DRAWING SOURCE | STF-01 | Nozzle Stiffener | PV | Nozzles | Made in-house | Plate | SA 516 Gr.70 | Thickness, width, length, profile, quantity | Plate (L x W x T) | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | Drawing items 210 and 212; item 210 weight unclear | 6 | 0 | 6
PV DRAWING SOURCE | SRN-01 | Self-Reinforced Nozzle | PV | Nozzles | Bought + machined in-house | Forging | SA 266 Gr.2 | Tag, OD/ID, neck length, flange interface, contour | Catalogue weight (per piece) | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | Drawing items 214 and 217; machine as detailed | 4 | 0 | 4
PV DRAWING SOURCE | CPL-01 | Coupling with Plug | PV | Nozzles | Bought + machined in-house | Forging | SA 105 | DN/NPS, pressure rating, thread, projection | Catalogue weight (per piece) | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | Drawing items 215 and 244; DN15 6000# BSP | 4 | 0 | 4
PV DRAWING SOURCE | BFL-01 | Blind Flange | PV | Flanges | Bought-out | Forging | SA 105 | DN/NPS, class, facing, thickness, bolting | Catalogue weight (per piece) | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | Drawing item 218; DN450 Class 300 RF; 181 kg | 3 | 0 | 3
PV DRAWING SOURCE | HOK-01 | Square Bar Hook | PV | Externals / Supports | Made in-house | Bar / Rod | SA 516 Gr.70 | Square size, developed length, bend radius | Bar / Rod (Dia, L) | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | Drawing item 221; square 28 × 400 developed length | 5 | 0 | 5
PV DRAWING SOURCE | EYE-01 | Eye Bolt | PV | Externals / Supports | Made in-house | Bar / Rod | IS 2062 E250B | Rod diameter, developed length, eye diameter, thread | Bar / Rod (Dia, L) | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | Drawing item 222; dia 25 × 500 developed length | 5 | 0 | 5
PV DRAWING SOURCE | WSH-02 | Washer (Davit) | PV | Bolting & Gaskets | Bought-out | Standard item (catalogue) | Stainless steel | Thickness, OD, ID, standard | Catalogue weight (per piece) | A | Yes | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | Drawing item 223; OD unreadable; supplier confirmation required | 3 | 0 | 3
PV DRAWING SOURCE | NUT-02 | Hex / Lock Nut (Davit) | PV | Bolting & Gaskets | Bought-out | Standard item (catalogue) | IS 1367 Class 4 | Thread size, nut type, standard, coating | Catalogue weight (per piece) | A | Yes | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | Drawing items 224–225; M24 | 3 | 0 | 3
PV DRAWING SOURCE | SPP-01 | Support Pipe | PV | Externals / Supports | Made in-house | Pipe | SA 106 Gr.B / SA 53 Gr.B | DN/NPS, schedule, cut length, end preparation | Pipe / Tube (OD, T, L) | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | Drawing items 211 and 226; exact item 226 grade requires MTC check | 6 | 0 | 6
PV DRAWING SOURCE | DVT-01 | Davit Pipe | PV | Externals / Supports | Made in-house | Pipe | SA 106 Gr.B | DN/NPS, schedule, developed length, bends | Pipe / Tube (OD, T, L) | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | Drawing item 227; DN50 Sch 80 approx. 1000 developed length | 6 | 0 | 6
PV DRAWING SOURCE | EPL-01 | Davit / Support End Plate | PV | Externals / Supports | Made in-house | Plate | SA 516 Gr.70 | Thickness, OD, hole size, quantity | Disc (OD, T) | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | Drawing items 228–229; OD 50/60 | 6 | 0 | 6
PV DRAWING SOURCE | RVT-01 | Snap Head Rivet | PV | Externals / Supports | Bought-out | Standard item (catalogue) | Mild steel | Diameter, length, head form, standard | Catalogue weight (per piece) | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | Drawing item 230; dia 20 × 25 length | 3 | 0 | 3
PV DRAWING SOURCE | RIB-01 | Rib Plate | PV | Externals / Supports | Made in-house | Plate | SA 516 Gr.70 | Thickness, width, length, profile | Plate (L x W x T) | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | Drawing item 231; 10T × 50W × 240 length | 6 | 0 | 6
PV DRAWING SOURCE | BOS-01 | Davit Pipe Boss | PV | Externals / Supports | Bought + machined in-house | Bar / Rod | IS 2062 | OD, ID/bore, length, weld prep | Bar / Rod (Dia, L) | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | Drawing item 232; dia 80 × 80 length; grade pending | 4 | 0 | 4
PV DRAWING SOURCE | HDL-01 | Davit Handle | PV | Externals / Supports | Made in-house | Bar / Rod | SA 516 Gr.70 | Square size, developed length, bend geometry | Bar / Rod (Dia, L) | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | Drawing item 233; qty 2 | 5 | 0 | 5
PV DRAWING SOURCE | JSC-01 | Jack Screw | PV | Externals / Supports | Bought + machined in-house | Bar / Rod | SS 304 | Thread size, length, head/handle detail | Bar / Rod (Dia, L) | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | Drawing item 234; qty 3; M16 × 120 | 4 | 0 | 4
PV DRAWING SOURCE | AOP-01 | Access Opening Assembly | PV | Other | Made in-house | Assembly (made of other parts) | SA 516 Gr.70 | Opening size, ring strip, cover/plate, weld detail | Sum of child parts | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | Drawing item 235 comprises 1075 developed ring and 428 length plate | 8 | 0 | 8
PV DRAWING SOURCE | PAD-01 | Attachment Pad Plate | PV | Externals / Supports | Made in-house | Plate | SA 516 Gr.70 | Thickness, width, developed length, curvature, vent hole | Plate (L x W x T) | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | Drawing item 237; qty 2; 16T × 200W × 330 developed length | 6 | 0 | 6
PV DRAWING SOURCE | LUG-02 | Lifting Lug (PV) | PV | Externals / Supports | Made in-house | Plate | SA 516 Gr.70 | Thickness, width, length, hole/contour, SWL | Plate (L x W x T) | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | Drawing item 238; qty 2; drawing weight basis requires check | 6 | 0 | 6
PV DRAWING SOURCE | SPL-01 | Lug Support Plate | PV | Externals / Supports | Made in-house | Plate | SA 516 Gr.70 | Thickness, width, length, profile, quantity | Plate (L x W x T) | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | Drawing item 239; qty 2; 28T × 500W × 230 length | 6 | 0 | 6
PV DRAWING SOURCE | TLG-01 | Tailing Lug | PV | Externals / Supports | Made in-house | Plate | SA 516 Gr.70 | Thickness, width, length, hole/contour, SWL | Plate (L x W x T) | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | Drawing item 240; 32T × 250W × 275 length | 6 | 0 | 6
PV DRAWING SOURCE | NPB-01 | Name Plate Bracket | PV | Name Plate & Marking | Made in-house | Plate | SA 516 Gr.70 | Thickness, width, length, hole pattern | Plate (L x W x T) | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | Drawing item 241; 6T × 160 × 350 length | 6 | 0 | 6
PV DRAWING SOURCE | NPL-01 | Name Plate | PV | Name Plate & Marking | Bought + fabricated in-house | Plate | SS 304 | Thickness, width, length, engraving data, holes | Plate (L x W x T) | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | Drawing item 242; 3T × 150 × 200 length | 5 | 0 | 5
PV DRAWING SOURCE | FBL-01 | Foundation Bolt with Nut & Washer | PV | Externals / Supports | Bought-out | Standard item (catalogue) | IS 1367 Gr.8.8 | Thread diameter, length, bend/anchor detail, nut/washer standard | Catalogue weight (per piece) | A | No | Assumed – to be confirmed | Precise Engineers | Pending – Production Head | Draft | Drawing item 243; qty 16; M36 × 580 length | 3 | 0 | 3

## Part Routes
HE + PV ROUTES — LIGHT-YELLOW PV ROUTES USE FIXED OPERATIONS AND APPROVED PV STAGE NUMBERS; PROPOSED TIMES REQUIRE SHOP VALIDATION.
One row per step, numbered 10, 20, 30… Use only operations from the dropdown; anything else goes in 'New Operations'. 'Counts toward Stage No.' is the whole-equipment stage this step belongs to (see 'PV Stages (ref)' and 'HE Stages'); fill both columns for parts used in PV and HE. If a part can be made in two ways, repeat its steps as Variant B. Hold points are not needed here; they come from each job's QAP.
Example? | Part Code | Part Name (auto) | Variant | Seq | Operation | What is done in this step | Department | Counts toward PV Stage No. | Counts toward HE Stage No. | Std. Time | Time Unit | Time Basis | Conditional? | When does it apply? | Acceptance Standard | Record / Document | Remarks
PILOT – SOURCE DRAFT | SHL-01 | Shell Course | A | 10 | Receipt | Plate received and GRN prepared | Stores | 10 | 11 | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | SHL-01 | Shell Course | A | 20 | MTC Verification / Material Identification | MTC reviewed and heat number transferred | Quality Control / QA | 11 | 12 | 0.75 | Hours | Per material lot | No |  | Material specification, grade, heat/lot and traceability match PO/BOM | MTC review / PMI / traceability record | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | SHL-01 | Shell Course | A | 30 | Cutting / Blanking | Plate cut to developed size | Fabrication Prep | 12 | 13 | 0.3 | Hours | Per metre of cut | No |  | Cut size and identification meet approved drawing/cutting plan | Cutting report / material traceability | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | SHL-01 | Shell Course | A | 40 | Edge Preparation / Beveling | Long-seam edges prepared | Fabrication Prep | 12 | 13 | 0.35 | Hours | Per metre of edge | No |  | Bevel geometry and cleanliness meet drawing/WPS | Fit-up / bevel inspection report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | SHL-01 | Shell Course | A | 50 | Rolling | Plate rolled to specified diameter | Fabrication Prep | 13 | 14 | 4 | Hours | Per piece | No |  | Diameter, roundness and straightness within approved drawing tolerance | Dimensional inspection report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | SHL-01 | Shell Course | A | 60 | Fit-up | Long seam aligned and fitted | Fabrication / Welding | 19 | 14 | 1.5 | Hours | Per joint | No |  | Alignment, root gap, offset and orientation meet WPS/drawing | Fit-up report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | SHL-01 | Shell Course | A | 70 | Welding | Long seam welded to approved WPS | Fabrication / Welding | 20 | 15 | 1.2 | Hours | Per metre of weld | No |  | Weld completed to approved WPS by qualified welder; visual acceptable | Weld log / WPS / WPQ | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | SHL-01 | Shell Course | A | 80 | NDT | Long seam examined by specified NDE | Quality Control / QA | 17 | 16 | 1 | Hours | Per joint | Yes | Extent and method as job QAP | Specified method and extent accepted to applicable code/QAP | NDE report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | SHL-01 | Shell Course | A | 90 | Inspection | Visual and dimensional inspection | Quality Control / QA | 21 | 16 | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet approved drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | HED-01 | Dished End | A | 10 | Receipt | Head plate or formed head received | Stores | 10 | 11 | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | HED-01 | Dished End | A | 20 | MTC Verification / Material Identification | MTC and traceability verified | Quality Control / QA | 11 | 12 | 0.75 | Hours | Per material lot | No |  | Material specification, grade, heat/lot and traceability match PO/BOM | MTC review / PMI / traceability record | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | HED-01 | Dished End | A | 30 | Cutting / Blanking | Blank or petals cut to drawing | Fabrication Prep | 12 | 13 | 0.3 | Hours | Per metre of cut | No |  | Cut size and identification meet approved drawing/cutting plan | Cutting report / material traceability | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | HED-01 | Dished End | A | 40 | Edge Preparation / Beveling | Edges prepared for forming or welding | Fabrication Prep | 12 | 13 | 0.35 | Hours | Per metre of edge | No |  | Bevel geometry and cleanliness meet drawing/WPS | Fit-up / bevel inspection report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | HED-01 | Dished End | A | 50 | Forming / Pressing / Dishing | Head formed to specified profile | Fabrication Prep | 13 | 17 | 16 | Hours | Per piece | No |  | Profile, minimum thickness and dimensions meet drawing/code | Forming and thickness/profile report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | HED-01 | Dished End | A | 60 | Grinding | Trim and dress formed edge | Fabrication Prep | 13 | 17 | 0.4 | Hours | Per metre of edge | No |  | Surface smooth, defect-free and blended without under-thickness | Visual inspection record | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | HED-01 | Dished End | A | 70 | Fit-up | Segments or head seam fitted | Fabrication / Welding | 19 | 25 | 1.5 | Hours | Per joint | Yes | Only for segmented or welded construction | Alignment, root gap, offset and orientation meet WPS/drawing | Fit-up report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | HED-01 | Dished End | A | 80 | Welding | Segments or head seam welded | Fabrication / Welding | 20 | 25 | 1.2 | Hours | Per metre of weld | Yes | Only for segmented or welded construction | Weld completed to approved WPS by qualified welder; visual acceptable | Weld log / WPS / WPQ | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | HED-01 | Dished End | A | 90 | NDT | Specified examination of welds or formed head | Quality Control / QA | 17 | 17 | 1 | Hours | Per joint | Yes | As required by drawing or QAP | Specified method and extent accepted to applicable code/QAP | NDE report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | HED-01 | Dished End | A | 100 | Inspection | Profile, thickness and dimensions checked | Quality Control / QA | 21 | 17 | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet approved drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | NOZ-01 | Nozzle Neck | A | 10 | Receipt | Pipe or neck forging received | Stores | 10 | 11 | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | NOZ-01 | Nozzle Neck | A | 20 | MTC Verification / Material Identification | MTC and identification verified | Quality Control / QA | 11 | 12 | 0.75 | Hours | Per material lot | No |  | Material specification, grade, heat/lot and traceability match PO/BOM | MTC review / PMI / traceability record | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | NOZ-01 | Nozzle Neck | A | 30 | Cutting / Blanking | Neck cut to job length | Fabrication Prep | 12 | 23 | 0.3 | Hours | Per metre of cut | No |  | Cut size and identification meet approved drawing/cutting plan | Cutting report / material traceability | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | NOZ-01 | Nozzle Neck | A | 40 | Machining | Facing or bore machining completed | Machine Shop | 14 | 23 | 1 | Hours | Per piece | Yes | When drawing requires machining | Dimensions, tolerances and surface finish meet approved drawing | Machining inspection report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | NOZ-01 | Nozzle Neck | A | 50 | Edge Preparation / Beveling | Weld end bevel prepared | Fabrication Prep | 12 | 23 | 0.35 | Hours | Per metre of edge | No |  | Bevel geometry and cleanliness meet drawing/WPS | Fit-up / bevel inspection report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | NOZ-01 | Nozzle Neck | A | 60 | Fit-up | Neck fitted to flange or equipment | Fabrication / Welding | 19 | 26 | 1.5 | Hours | Per joint | No |  | Alignment, root gap, offset and orientation meet WPS/drawing | Fit-up report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | NOZ-01 | Nozzle Neck | A | 70 | Welding | Neck joint welded | Fabrication / Welding | 20 | 26 | 1.2 | Hours | Per metre of weld | No |  | Weld completed to approved WPS by qualified welder; visual acceptable | Weld log / WPS / WPQ | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | NOZ-01 | Nozzle Neck | A | 80 | NDT | Joint examined by specified method | Quality Control / QA | 17 | 28 | 1 | Hours | Per joint | Yes | As required by job QAP | Specified method and extent accepted to applicable code/QAP | NDE report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | NOZ-01 | Nozzle Neck | A | 90 | Inspection | Projection and dimensions checked | Quality Control / QA | 21 | 26 | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet approved drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | FLG-01 | Nozzle Flange | A | 10 | Receipt | Purchased flange or forging received | Stores | 10 | 11 | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | FLG-01 | Nozzle Flange | A | 20 | MTC Verification / Material Identification | MTC, grade and traceability verified | Quality Control / QA | 11 | 12 | 0.75 | Hours | Per material lot | No |  | Material specification, grade, heat/lot and traceability match PO/BOM | MTC review / PMI / traceability record | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | FLG-01 | Nozzle Flange | A | 30 | NDT | Incoming UT or other NDE reviewed/performed | Quality Control / QA | 17 | 12 | 1 | Hours | Per joint | Yes | If required for forging or by job specification | Specified method and extent accepted to applicable code/QAP | NDE report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | FLG-01 | Nozzle Flange | A | 40 | Machining | Bore, facing, drilling and final machining completed | Machine Shop | 14 | 23 | 2 | Hours | Per piece | Yes | If supplied rough or job machining is required | Dimensions, tolerances and surface finish meet approved drawing | Machining inspection report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | FLG-01 | Nozzle Flange | A | 50 | Inspection | Rating, facing and dimensions checked | Quality Control / QA | 21 | 23 | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet approved drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | TSH-01 | Tube Sheet | A | 10 | Receipt | Tubesheet forging received | Stores |  | 11 | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | TSH-01 | Tube Sheet | A | 20 | MTC Verification / Material Identification | MTC and vendor certificates reviewed | Quality Control / QA |  | 12 | 0.75 | Hours | Per material lot | No |  | Material specification, grade, heat/lot and traceability match PO/BOM | MTC review / PMI / traceability record | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | TSH-01 | Tube Sheet | A | 30 | NDT | Forging UT reviewed or performed | Quality Control / QA |  | 12 | 1 | Hours | Per joint | No |  | Specified method and extent accepted to applicable code/QAP | NDE report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | TSH-01 | Tube Sheet | A | 40 | Machining | Rough machining completed | Machine Shop |  | 20 | 0.08 | Hours | Per hole | No |  | Dimensions, tolerances and surface finish meet approved drawing | Machining inspection report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | TSH-01 | Tube Sheet | A | 50 | Machining | Tube holes, bolt holes and pass grooves drilled/machined | Machine Shop |  | 20 | 0.08 | Hours | Per hole | No |  | Dimensions, tolerances and surface finish meet approved drawing | Machining inspection report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | TSH-01 | Tube Sheet | A | 60 | Machining | Final facing and finish machining completed | Machine Shop |  | 20 | 0.08 | Hours | Per hole | No |  | Dimensions, tolerances and surface finish meet approved drawing | Machining inspection report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | TSH-01 | Tube Sheet | A | 70 | Inspection | Hole pattern, thickness, flatness and finish checked | Quality Control / QA |  | 21 | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet approved drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | TUB-01 | Tube | A | 10 | Receipt | Heat-exchanger tubes received | Stores |  | 11 | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | TUB-01 | Tube | A | 20 | MTC Verification / Material Identification | MTC and material identity verified | Quality Control / QA |  | 12 | 0.75 | Hours | Per material lot | No |  | Material specification, grade, heat/lot and traceability match PO/BOM | MTC review / PMI / traceability record | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | TUB-01 | Tube | A | 30 | Inspection | Incoming dimensions and surface condition checked | Quality Control / QA |  | 31 | 0.05 | Hours | Per tube | No |  | Visual and dimensional results meet approved drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | TUB-01 | Tube | A | 40 | Cutting / Blanking | Tubes cut to job length | Fabrication Prep |  | 31 | 0.08 | Hours | Per tube | Yes | When not supplied at final length | Cut size and identification meet approved drawing/cutting plan | Cutting report / material traceability | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | TUB-01 | Tube | A | 50 | Inspection | Tube integrity test reviewed or performed | Quality Control / QA |  | 31 | 0.05 | Hours | Per tube | Yes | Eddy-current or hydro test as specified | Visual and dimensional results meet approved drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | BAF-01 | Baffle | A | 10 | Receipt | Baffle plate received | Stores |  | 11 | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | BAF-01 | Baffle | A | 20 | MTC Verification / Material Identification | MTC and identity verified | Quality Control / QA |  | 12 | 0.75 | Hours | Per material lot | No |  | Material specification, grade, heat/lot and traceability match PO/BOM | MTC review / PMI / traceability record | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | BAF-01 | Baffle | A | 30 | Cutting / Blanking | Baffle blank and segment profile cut | Fabrication Prep |  | 22 | 0.3 | Hours | Per metre of cut | No |  | Cut size and identification meet approved drawing/cutting plan | Cutting report / material traceability | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | BAF-01 | Baffle | A | 40 | Machining | Tube holes and tie-rod holes drilled/machined | Machine Shop |  | 22 | 0.06 | Hours | Per hole | No |  | Dimensions, tolerances and surface finish meet approved drawing | Machining inspection report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | BAF-01 | Baffle | A | 50 | Forming / Pressing / Dishing | Baffle formed when drawing requires | Fabrication Prep |  | 22 | 12 | Hours | Per piece | Yes | Only for formed baffle geometry | Profile, minimum thickness and dimensions meet drawing/code | Forming and thickness/profile report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | BAF-01 | Baffle | A | 60 | Inspection | OD, cut, hole pattern and burr condition checked | Quality Control / QA |  | 22 | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet approved drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | SAD-01 | Saddle | A | 10 | Receipt | Saddle plates and sections received | Stores | 10 | 11 | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | SAD-01 | Saddle | A | 20 | MTC Verification / Material Identification | MTC and identity verified | Quality Control / QA | 11 | 12 | 0.75 | Hours | Per material lot | No |  | Material specification, grade, heat/lot and traceability match PO/BOM | MTC review / PMI / traceability record | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | SAD-01 | Saddle | A | 30 | Cutting / Blanking | Wrapper, web, ribs and base parts cut | Fabrication Prep | 12 | 13 | 0.3 | Hours | Per metre of cut | No |  | Cut size and identification meet approved drawing/cutting plan | Cutting report / material traceability | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | SAD-01 | Saddle | A | 40 | Rolling | Wrapper plate rolled to vessel radius | Fabrication Prep | 13 | 27 | 4 | Hours | Per piece | No |  | Diameter, roundness and straightness within approved drawing tolerance | Dimensional inspection report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | SAD-01 | Saddle | A | 50 | Forming / Pressing / Dishing | Saddle parts formed where required | Fabrication Prep | 13 | 27 | 12 | Hours | Per piece | Yes | When detail drawing requires forming | Profile, minimum thickness and dimensions meet drawing/code | Forming and thickness/profile report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | SAD-01 | Saddle | A | 60 | Fit-up | Child parts fitted into saddle assembly | Fabrication / Welding | 19 | 27 | 1.5 | Hours | Per joint | No |  | Alignment, root gap, offset and orientation meet WPS/drawing | Fit-up report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | SAD-01 | Saddle | A | 70 | Welding | Saddle assembly welded | Fabrication / Welding | 20 | 27 | 1.2 | Hours | Per metre of weld | No |  | Weld completed to approved WPS by qualified welder; visual acceptable | Weld log / WPS / WPQ | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | SAD-01 | Saddle | A | 80 | Machining | Base or holes machined | Machine Shop | 14 | 27 | 2 | Hours | Per piece | Yes | When drawing specifies machining | Dimensions, tolerances and surface finish meet approved drawing | Machining inspection report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | SAD-01 | Saddle | A | 90 | NDT | Saddle welds examined | Quality Control / QA | 17 | 28 | 1 | Hours | Per joint | Yes | Method and extent per job QAP | Specified method and extent accepted to applicable code/QAP | NDE report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | SAD-01 | Saddle | A | 100 | Inspection | Dimensions and welds inspected | Quality Control / QA | 21 | 27 | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet approved drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | STD-01 | Stud with Two Nuts | A | 10 | Receipt | Studs and nuts received | Stores | 10 | 11 | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | STD-01 | Stud with Two Nuts | A | 20 | MTC Verification / Material Identification | MTC or CoC and grade reviewed | Quality Control / QA | 11 | 12 | 0.75 | Hours | Per material lot | No |  | Material specification, grade, heat/lot and traceability match PO/BOM | MTC review / PMI / traceability record | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | STD-01 | Stud with Two Nuts | A | 30 | Inspection | Quantity, dimensions and threads inspected | Quality Control / QA | 21 | 11 | 0.08 | Hours | Per piece | No |  | Visual and dimensional results meet approved drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | GAS-01 | Gasket | A | 10 | Receipt | Gaskets received and segregated | Stores | 10 | 11 | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | GAS-01 | Gasket | A | 20 | MTC Verification / Material Identification | CoC and construction reviewed | Quality Control / QA | 11 | 12 | 0.75 | Hours | Per material lot | No |  | Material specification, grade, heat/lot and traceability match PO/BOM | MTC review / PMI / traceability record | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
PILOT – SOURCE DRAFT | GAS-01 | Gasket | A | 30 | Inspection | Size, class, thickness and condition checked | Quality Control / QA | 21 | 11 | 0.15 | Hours | Per piece | No |  | Visual and dimensional results meet approved drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
DRAWING REQUIREMENT | HED-01 | Dished End | B | 10 | MTC Verification / Material Identification | Maintain identification marking; after forming, marking remains on outside | Quality Control / QA | 11 | 12 | 0.75 | Hours | Per material lot | No |  | Material specification, grade, heat/lot and traceability match PO/BOM | MTC review / PMI / traceability record | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
DRAWING REQUIREMENT | HED-01 | Dished End | B | 20 | Cutting / Blanking | Prepare blank; indicative diameter 3772, final blank per manufacturer while finished geometry is maintained | Fabrication Prep | 12 | 13 | 0.3 | Hours | Per metre of cut | No |  | Cut size and identification meet approved drawing/cutting plan | Cutting report / material traceability | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
DRAWING REQUIREMENT | HED-01 | Dished End | B | 30 | Forming / Pressing / Dishing | Cold form 2:1 semi-ellipsoidal head to drawing dimensions | Fabrication Prep | 13 | 17 | 16 | Hours | Per piece | No |  | Profile, minimum thickness and dimensions meet drawing/code | Forming and thickness/profile report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
DRAWING REQUIREMENT | HED-01 | Dished End | B | 40 | NDT | Full dye-penetrant examination on inside and outside in presence of TPI | Quality Control / QA | 17 | 17 | 1 | Hours | Per joint | No |  | Specified method and extent accepted to applicable code/QAP | NDE report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
DRAWING REQUIREMENT | HED-01 | Dished End | B | 50 | Inspection | Check dished profile by template | Quality Control / QA | 18 | 17 | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet approved drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
DRAWING REQUIREMENT | HED-01 | Dished End | B | 60 | Inspection | Verify ID, height, straight face, minimum formed thickness and skirt roundness | Quality Control / QA | 18 | 17 | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet approved drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / STAGE — validate by time study and approve before tracker load.
DRAWING REQUIREMENT | TSH-02 | Tube Sheet (Fabricated Plate) | A | 10 | Fit-up | Fit plate sections for plate-to-plate joint shown on drawing | [6 empty] | No |  | SP40-02-03-04-002 Rev.0 typical weld detail | Fit-up report | Department, stage and time pending shop confirmation.
DRAWING REQUIREMENT | TSH-02 | Tube Sheet (Fabricated Plate) | A | 20 | Welding | Complete tubesheet plate-to-plate weld | [6 empty] | No |  | SP40-02-03-04-002 Rev.0 | Weld log; WPS/WPQ | Department, stage and time pending shop confirmation.
DRAWING REQUIREMENT | TSH-02 | Tube Sheet (Fabricated Plate) | A | 30 | NDT | Perform 100% RT and obtain acceptance before drilling tube holes | [6 empty] | No |  | SP40-02-03-04-002 Rev.0 note 2 | RT report / release | Mandatory hold before drilling; department, stage and time pending.
DRAWING REQUIREMENT | TSH-02 | Tube Sheet (Fabricated Plate) | A | 40 | Machining | Machine tube holes Ø24.7 to drawing layout/pitch | [6 empty] | No |  | SP40-02-03-04-002 Rev.0 | Machining/drilling report | Only after accepted RT; department, stage and time pending.
DRAWING REQUIREMENT | TSH-02 | Tube Sheet (Fabricated Plate) | A | 50 | Grinding | Thoroughly deburr all tube holes | [6 empty] | No |  | SP40-02-03-04-002 Rev.0 note 3 | Inspection record | Department, stage and time pending shop confirmation.
DRAWING REQUIREMENT | TSH-02 | Tube Sheet (Fabricated Plate) | A | 60 | Machining | Finish tube holes to 1.6 microns and chamfer 0.5 × 45° both sides | [6 empty] | No |  | SP40-02-03-04-002 Rev.0 notes 3 and 4 | Surface-finish/dimensional report | Department, stage and time pending shop confirmation.
DRAWING REQUIREMENT | TSH-02 | Tube Sheet (Fabricated Plate) | A | 70 | Inspection | Verify OD, thickness, hole pattern, flatness, circularity and freedom from distortion | [6 empty] | No |  | SP40-02-03-04-002 Rev.0 note 5 | Final dimensional report | Department, stage and time pending shop confirmation.
PV DRAWING SOURCE | SKT-01 | Skirt Shell | A | 10 | Receipt | Receipt for Skirt Shell to approved drawing/detail | Stores | 10 |  | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | SKT-01 | Skirt Shell | A | 20 | MTC Verification / Material Identification | MTC Verification / Material Identification for Skirt Shell to approved drawing/detail | Quality Control / QA | 11 |  | 0.75 | Hours | Per material lot | No |  | Specification, grade, heat/lot and traceability match drawing/BOM | MTC review / PMI / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | SKT-01 | Skirt Shell | A | 30 | Cutting / Blanking | Cutting / Blanking for Skirt Shell to approved drawing/detail | Fabrication Prep | 12 |  | 0.3 | Hours | Per metre of cut | No |  | Cut size and identification meet approved drawing/cutting plan | Cutting report / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | SKT-01 | Skirt Shell | A | 40 | Edge Preparation / Beveling | Edge Preparation / Beveling for Skirt Shell to approved drawing/detail | Fabrication Prep | 12 |  | 0.35 | Hours | Per metre of edge | No |  | Bevel geometry and cleanliness meet drawing/WPS | Bevel / fit-up inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | SKT-01 | Skirt Shell | A | 50 | Rolling | Rolling for Skirt Shell to approved drawing/detail | Fabrication Prep | 13 |  | 4 | Hours | Per piece | No |  | Diameter, roundness and straightness meet drawing tolerance | Dimensional inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | SKT-01 | Skirt Shell | A | 60 | Fit-up | Fit-up for Skirt Shell to approved drawing/detail | Fabrication / Welding | 15 |  | 1.5 | Hours | Per joint | No |  | Alignment, root gap, orientation and offset meet WPS/drawing | Fit-up report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | SKT-01 | Skirt Shell | A | 70 | Welding | Welding for Skirt Shell to approved drawing/detail | Fabrication / Welding | 16 |  | 1.2 | Hours | Per metre of weld | No |  | Weld completed to approved WPS by qualified welder; visual acceptable | Weld log / WPS / WPQ | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | SKT-01 | Skirt Shell | A | 80 | NDT | NDT for Skirt Shell to approved drawing/detail | Quality Control / QA | 17 |  | 1 | Hours | Per joint | Yes | When required by approved QAP/code or for pressure-retaining welds | Required RT/PT/MT/UT accepted to code/QAP | NDE report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | SKT-01 | Skirt Shell | A | 90 | Inspection | Inspection for Skirt Shell to approved drawing/detail | Quality Control / QA | 25 |  | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | SBR-01 | Skirt Base Ring | A | 10 | Receipt | Receipt for Skirt Base Ring to approved drawing/detail | Stores | 10 |  | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | SBR-01 | Skirt Base Ring | A | 20 | MTC Verification / Material Identification | MTC Verification / Material Identification for Skirt Base Ring to approved drawing/detail | Quality Control / QA | 11 |  | 0.75 | Hours | Per material lot | No |  | Specification, grade, heat/lot and traceability match drawing/BOM | MTC review / PMI / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | SBR-01 | Skirt Base Ring | A | 30 | Cutting / Blanking | Cutting / Blanking for Skirt Base Ring to approved drawing/detail | Fabrication Prep | 12 |  | 0.3 | Hours | Per metre of cut | No |  | Cut size and identification meet approved drawing/cutting plan | Cutting report / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | SBR-01 | Skirt Base Ring | A | 40 | Rolling | Rolling for Skirt Base Ring to approved drawing/detail | Fabrication Prep | 13 |  | 4 | Hours | Per piece | No |  | Diameter, roundness and straightness meet drawing tolerance | Dimensional inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | SBR-01 | Skirt Base Ring | A | 50 | Machining | Machining for Skirt Base Ring to approved drawing/detail | Machine Shop | 14 |  | 1.5 | Hours | Per piece | No |  | Dimensions, thread, holes and finish meet drawing | Machining inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | SBR-01 | Skirt Base Ring | A | 60 | Inspection | Inspection for Skirt Base Ring to approved drawing/detail | Quality Control / QA | 25 |  | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | GSP-02 | Gusset Plate (PV Support) | A | 10 | Receipt | Receipt for Gusset Plate (PV Support) to approved drawing/detail | Stores | 10 |  | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | GSP-02 | Gusset Plate (PV Support) | A | 20 | MTC Verification / Material Identification | MTC Verification / Material Identification for Gusset Plate (PV Support) to approved drawing/detail | Quality Control / QA | 11 |  | 0.75 | Hours | Per material lot | No |  | Specification, grade, heat/lot and traceability match drawing/BOM | MTC review / PMI / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | GSP-02 | Gusset Plate (PV Support) | A | 30 | Cutting / Blanking | Cutting / Blanking for Gusset Plate (PV Support) to approved drawing/detail | Fabrication Prep | 12 |  | 0.3 | Hours | Per metre of cut | No |  | Cut size and identification meet approved drawing/cutting plan | Cutting report / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | GSP-02 | Gusset Plate (PV Support) | A | 40 | Machining | Machining for Gusset Plate (PV Support) to approved drawing/detail | Machine Shop | 14 |  | 2 | Hours | Per piece | No |  | Dimensions, thread, holes and finish meet drawing | Machining inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | GSP-02 | Gusset Plate (PV Support) | A | 50 | Edge Preparation / Beveling | Edge Preparation / Beveling for Gusset Plate (PV Support) to approved drawing/detail | Fabrication Prep | 12 |  | 0.35 | Hours | Per metre of edge | No |  | Bevel geometry and cleanliness meet drawing/WPS | Bevel / fit-up inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | GSP-02 | Gusset Plate (PV Support) | A | 60 | Inspection | Inspection for Gusset Plate (PV Support) to approved drawing/detail | Quality Control / QA | 25 |  | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | ERT-01 | Earthing Plate | A | 10 | Receipt | Receipt for Earthing Plate to approved drawing/detail | Stores | 10 |  | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | ERT-01 | Earthing Plate | A | 20 | MTC Verification / Material Identification | MTC Verification / Material Identification for Earthing Plate to approved drawing/detail | Quality Control / QA | 11 |  | 0.75 | Hours | Per material lot | No |  | Specification, grade, heat/lot and traceability match drawing/BOM | MTC review / PMI / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | ERT-01 | Earthing Plate | A | 30 | Cutting / Blanking | Cutting / Blanking for Earthing Plate to approved drawing/detail | Fabrication Prep | 12 |  | 0.3 | Hours | Per metre of cut | No |  | Cut size and identification meet approved drawing/cutting plan | Cutting report / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | ERT-01 | Earthing Plate | A | 40 | Machining | Machining for Earthing Plate to approved drawing/detail | Machine Shop | 14 |  | 2 | Hours | Per piece | No |  | Dimensions, thread, holes and finish meet drawing | Machining inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | ERT-01 | Earthing Plate | A | 50 | Edge Preparation / Beveling | Edge Preparation / Beveling for Earthing Plate to approved drawing/detail | Fabrication Prep | 12 |  | 0.35 | Hours | Per metre of edge | No |  | Bevel geometry and cleanliness meet drawing/WPS | Bevel / fit-up inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | ERT-01 | Earthing Plate | A | 60 | Inspection | Inspection for Earthing Plate to approved drawing/detail | Quality Control / QA | 25 |  | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | RFP-02 | Nozzle Reinforcement Pad | A | 10 | Receipt | Receipt for Nozzle Reinforcement Pad to approved drawing/detail | Stores | 10 |  | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | RFP-02 | Nozzle Reinforcement Pad | A | 20 | MTC Verification / Material Identification | MTC Verification / Material Identification for Nozzle Reinforcement Pad to approved drawing/detail | Quality Control / QA | 11 |  | 0.75 | Hours | Per material lot | No |  | Specification, grade, heat/lot and traceability match drawing/BOM | MTC review / PMI / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | RFP-02 | Nozzle Reinforcement Pad | A | 30 | Cutting / Blanking | Cutting / Blanking for Nozzle Reinforcement Pad to approved drawing/detail | Fabrication Prep | 12 |  | 0.3 | Hours | Per metre of cut | No |  | Cut size and identification meet approved drawing/cutting plan | Cutting report / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | RFP-02 | Nozzle Reinforcement Pad | A | 40 | Rolling | Rolling for Nozzle Reinforcement Pad to approved drawing/detail | Fabrication Prep | 13 |  | 4 | Hours | Per piece | No |  | Diameter, roundness and straightness meet drawing tolerance | Dimensional inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | RFP-02 | Nozzle Reinforcement Pad | A | 50 | Machining | Machining for Nozzle Reinforcement Pad to approved drawing/detail | Machine Shop | 14 |  | 1.5 | Hours | Per piece | No |  | Dimensions, thread, holes and finish meet drawing | Machining inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | RFP-02 | Nozzle Reinforcement Pad | A | 60 | Inspection | Inspection for Nozzle Reinforcement Pad to approved drawing/detail | Quality Control / QA | 25 |  | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | ELB-01 | Nozzle Elbow | A | 10 | Receipt | Receipt for Nozzle Elbow to approved drawing/detail | Stores | 10 |  | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | ELB-01 | Nozzle Elbow | A | 20 | MTC Verification / Material Identification | MTC Verification / Material Identification for Nozzle Elbow to approved drawing/detail | Quality Control / QA | 11 |  | 0.75 | Hours | Per material lot | No |  | Specification, grade, heat/lot and traceability match drawing/BOM | MTC review / PMI / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | ELB-01 | Nozzle Elbow | A | 30 | Inspection | Inspection for Nozzle Elbow to approved drawing/detail | Quality Control / QA | 25 |  | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | STF-01 | Nozzle Stiffener | A | 10 | Receipt | Receipt for Nozzle Stiffener to approved drawing/detail | Stores | 10 |  | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | STF-01 | Nozzle Stiffener | A | 20 | MTC Verification / Material Identification | MTC Verification / Material Identification for Nozzle Stiffener to approved drawing/detail | Quality Control / QA | 11 |  | 0.75 | Hours | Per material lot | No |  | Specification, grade, heat/lot and traceability match drawing/BOM | MTC review / PMI / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | STF-01 | Nozzle Stiffener | A | 30 | Cutting / Blanking | Cutting / Blanking for Nozzle Stiffener to approved drawing/detail | Fabrication Prep | 12 |  | 0.3 | Hours | Per metre of cut | No |  | Cut size and identification meet approved drawing/cutting plan | Cutting report / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | STF-01 | Nozzle Stiffener | A | 40 | Machining | Machining for Nozzle Stiffener to approved drawing/detail | Machine Shop | 14 |  | 2 | Hours | Per piece | No |  | Dimensions, thread, holes and finish meet drawing | Machining inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | STF-01 | Nozzle Stiffener | A | 50 | Edge Preparation / Beveling | Edge Preparation / Beveling for Nozzle Stiffener to approved drawing/detail | Fabrication Prep | 12 |  | 0.35 | Hours | Per metre of edge | No |  | Bevel geometry and cleanliness meet drawing/WPS | Bevel / fit-up inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | STF-01 | Nozzle Stiffener | A | 60 | Inspection | Inspection for Nozzle Stiffener to approved drawing/detail | Quality Control / QA | 25 |  | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | SRN-01 | Self-Reinforced Nozzle | A | 10 | Receipt | Receipt for Self-Reinforced Nozzle to approved drawing/detail | Stores | 10 |  | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | SRN-01 | Self-Reinforced Nozzle | A | 20 | MTC Verification / Material Identification | MTC Verification / Material Identification for Self-Reinforced Nozzle to approved drawing/detail | Quality Control / QA | 11 |  | 0.75 | Hours | Per material lot | No |  | Specification, grade, heat/lot and traceability match drawing/BOM | MTC review / PMI / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | SRN-01 | Self-Reinforced Nozzle | A | 30 | Machining | Machining for Self-Reinforced Nozzle to approved drawing/detail | Machine Shop | 14 |  | 2 | Hours | Per piece | No |  | Dimensions, thread, holes and finish meet drawing | Machining inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | SRN-01 | Self-Reinforced Nozzle | A | 40 | Inspection | Inspection for Self-Reinforced Nozzle to approved drawing/detail | Quality Control / QA | 25 |  | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | CPL-01 | Coupling with Plug | A | 10 | Receipt | Receipt for Coupling with Plug to approved drawing/detail | Stores | 10 |  | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | CPL-01 | Coupling with Plug | A | 20 | MTC Verification / Material Identification | MTC Verification / Material Identification for Coupling with Plug to approved drawing/detail | Quality Control / QA | 11 |  | 0.75 | Hours | Per material lot | No |  | Specification, grade, heat/lot and traceability match drawing/BOM | MTC review / PMI / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | CPL-01 | Coupling with Plug | A | 30 | Machining | Machining for Coupling with Plug to approved drawing/detail | Machine Shop | 14 |  | 2 | Hours | Per piece | No |  | Dimensions, thread, holes and finish meet drawing | Machining inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | CPL-01 | Coupling with Plug | A | 40 | Inspection | Inspection for Coupling with Plug to approved drawing/detail | Quality Control / QA | 25 |  | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | BFL-01 | Blind Flange | A | 10 | Receipt | Receipt for Blind Flange to approved drawing/detail | Stores | 10 |  | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | BFL-01 | Blind Flange | A | 20 | MTC Verification / Material Identification | MTC Verification / Material Identification for Blind Flange to approved drawing/detail | Quality Control / QA | 11 |  | 0.75 | Hours | Per material lot | No |  | Specification, grade, heat/lot and traceability match drawing/BOM | MTC review / PMI / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | BFL-01 | Blind Flange | A | 30 | Inspection | Inspection for Blind Flange to approved drawing/detail | Quality Control / QA | 25 |  | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | HOK-01 | Square Bar Hook | A | 10 | Receipt | Receipt for Square Bar Hook to approved drawing/detail | Stores | 10 |  | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | HOK-01 | Square Bar Hook | A | 20 | MTC Verification / Material Identification | MTC Verification / Material Identification for Square Bar Hook to approved drawing/detail | Quality Control / QA | 11 |  | 0.75 | Hours | Per material lot | No |  | Specification, grade, heat/lot and traceability match drawing/BOM | MTC review / PMI / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | HOK-01 | Square Bar Hook | A | 30 | Cutting / Blanking | Cutting / Blanking for Square Bar Hook to approved drawing/detail | Fabrication Prep | 12 |  | 0.3 | Hours | Per metre of cut | No |  | Cut size and identification meet approved drawing/cutting plan | Cutting report / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | HOK-01 | Square Bar Hook | A | 40 | Forming / Pressing / Dishing | Forming / Pressing / Dishing for Square Bar Hook to approved drawing/detail | Fabrication Prep | 13 |  | 3 | Hours | Per piece | No |  | Form, radius and dimensions meet approved detail | Forming inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | HOK-01 | Square Bar Hook | A | 50 | Inspection | Inspection for Square Bar Hook to approved drawing/detail | Quality Control / QA | 25 |  | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | EYE-01 | Eye Bolt | A | 10 | Receipt | Receipt for Eye Bolt to approved drawing/detail | Stores | 10 |  | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | EYE-01 | Eye Bolt | A | 20 | MTC Verification / Material Identification | MTC Verification / Material Identification for Eye Bolt to approved drawing/detail | Quality Control / QA | 11 |  | 0.75 | Hours | Per material lot | No |  | Specification, grade, heat/lot and traceability match drawing/BOM | MTC review / PMI / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | EYE-01 | Eye Bolt | A | 30 | Cutting / Blanking | Cutting / Blanking for Eye Bolt to approved drawing/detail | Fabrication Prep | 12 |  | 0.3 | Hours | Per metre of cut | No |  | Cut size and identification meet approved drawing/cutting plan | Cutting report / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | EYE-01 | Eye Bolt | A | 40 | Forming / Pressing / Dishing | Forming / Pressing / Dishing for Eye Bolt to approved drawing/detail | Fabrication Prep | 13 |  | 3 | Hours | Per piece | No |  | Form, radius and dimensions meet approved detail | Forming inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | EYE-01 | Eye Bolt | A | 50 | Inspection | Inspection for Eye Bolt to approved drawing/detail | Quality Control / QA | 25 |  | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | WSH-02 | Washer (Davit) | A | 10 | Receipt | Receipt for Washer (Davit) to approved drawing/detail | Stores | 10 |  | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | WSH-02 | Washer (Davit) | A | 20 | MTC Verification / Material Identification | MTC Verification / Material Identification for Washer (Davit) to approved drawing/detail | Quality Control / QA | 11 |  | 0.75 | Hours | Per material lot | No |  | Specification, grade, heat/lot and traceability match drawing/BOM | MTC review / PMI / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | WSH-02 | Washer (Davit) | A | 30 | Inspection | Inspection for Washer (Davit) to approved drawing/detail | Quality Control / QA | 25 |  | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | NUT-02 | Hex / Lock Nut (Davit) | A | 10 | Receipt | Receipt for Hex / Lock Nut (Davit) to approved drawing/detail | Stores | 10 |  | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | NUT-02 | Hex / Lock Nut (Davit) | A | 20 | MTC Verification / Material Identification | MTC Verification / Material Identification for Hex / Lock Nut (Davit) to approved drawing/detail | Quality Control / QA | 11 |  | 0.75 | Hours | Per material lot | No |  | Specification, grade, heat/lot and traceability match drawing/BOM | MTC review / PMI / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | NUT-02 | Hex / Lock Nut (Davit) | A | 30 | Inspection | Inspection for Hex / Lock Nut (Davit) to approved drawing/detail | Quality Control / QA | 25 |  | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | SPP-01 | Support Pipe | A | 10 | Receipt | Receipt for Support Pipe to approved drawing/detail | Stores | 10 |  | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | SPP-01 | Support Pipe | A | 20 | MTC Verification / Material Identification | MTC Verification / Material Identification for Support Pipe to approved drawing/detail | Quality Control / QA | 11 |  | 0.75 | Hours | Per material lot | No |  | Specification, grade, heat/lot and traceability match drawing/BOM | MTC review / PMI / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | SPP-01 | Support Pipe | A | 30 | Cutting / Blanking | Cutting / Blanking for Support Pipe to approved drawing/detail | Fabrication Prep | 12 |  | 0.3 | Hours | Per metre of cut | No |  | Cut size and identification meet approved drawing/cutting plan | Cutting report / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | SPP-01 | Support Pipe | A | 40 | Edge Preparation / Beveling | Edge Preparation / Beveling for Support Pipe to approved drawing/detail | Fabrication Prep | 12 |  | 0.35 | Hours | Per metre of edge | No |  | Bevel geometry and cleanliness meet drawing/WPS | Bevel / fit-up inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | SPP-01 | Support Pipe | A | 50 | Forming / Pressing / Dishing | Forming / Pressing / Dishing for Support Pipe to approved drawing/detail | Fabrication Prep | 13 |  | 3 | Hours | Per piece | Yes | When forming/bending is required by the approved detail | Form, radius and dimensions meet approved detail | Forming inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | SPP-01 | Support Pipe | A | 60 | Inspection | Inspection for Support Pipe to approved drawing/detail | Quality Control / QA | 25 |  | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | DVT-01 | Davit Pipe | A | 10 | Receipt | Receipt for Davit Pipe to approved drawing/detail | Stores | 10 |  | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | DVT-01 | Davit Pipe | A | 20 | MTC Verification / Material Identification | MTC Verification / Material Identification for Davit Pipe to approved drawing/detail | Quality Control / QA | 11 |  | 0.75 | Hours | Per material lot | No |  | Specification, grade, heat/lot and traceability match drawing/BOM | MTC review / PMI / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | DVT-01 | Davit Pipe | A | 30 | Cutting / Blanking | Cutting / Blanking for Davit Pipe to approved drawing/detail | Fabrication Prep | 12 |  | 0.3 | Hours | Per metre of cut | No |  | Cut size and identification meet approved drawing/cutting plan | Cutting report / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | DVT-01 | Davit Pipe | A | 40 | Edge Preparation / Beveling | Edge Preparation / Beveling for Davit Pipe to approved drawing/detail | Fabrication Prep | 12 |  | 0.35 | Hours | Per metre of edge | No |  | Bevel geometry and cleanliness meet drawing/WPS | Bevel / fit-up inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | DVT-01 | Davit Pipe | A | 50 | Forming / Pressing / Dishing | Forming / Pressing / Dishing for Davit Pipe to approved drawing/detail | Fabrication Prep | 13 |  | 3 | Hours | Per piece | Yes | When forming/bending is required by the approved detail | Form, radius and dimensions meet approved detail | Forming inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | DVT-01 | Davit Pipe | A | 60 | Inspection | Inspection for Davit Pipe to approved drawing/detail | Quality Control / QA | 25 |  | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | EPL-01 | Davit / Support End Plate | A | 10 | Receipt | Receipt for Davit / Support End Plate to approved drawing/detail | Stores | 10 |  | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | EPL-01 | Davit / Support End Plate | A | 20 | MTC Verification / Material Identification | MTC Verification / Material Identification for Davit / Support End Plate to approved drawing/detail | Quality Control / QA | 11 |  | 0.75 | Hours | Per material lot | No |  | Specification, grade, heat/lot and traceability match drawing/BOM | MTC review / PMI / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | EPL-01 | Davit / Support End Plate | A | 30 | Cutting / Blanking | Cutting / Blanking for Davit / Support End Plate to approved drawing/detail | Fabrication Prep | 12 |  | 0.3 | Hours | Per metre of cut | No |  | Cut size and identification meet approved drawing/cutting plan | Cutting report / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | EPL-01 | Davit / Support End Plate | A | 40 | Machining | Machining for Davit / Support End Plate to approved drawing/detail | Machine Shop | 14 |  | 2 | Hours | Per piece | No |  | Dimensions, thread, holes and finish meet drawing | Machining inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | EPL-01 | Davit / Support End Plate | A | 50 | Edge Preparation / Beveling | Edge Preparation / Beveling for Davit / Support End Plate to approved drawing/detail | Fabrication Prep | 12 |  | 0.35 | Hours | Per metre of edge | No |  | Bevel geometry and cleanliness meet drawing/WPS | Bevel / fit-up inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | EPL-01 | Davit / Support End Plate | A | 60 | Inspection | Inspection for Davit / Support End Plate to approved drawing/detail | Quality Control / QA | 25 |  | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | RVT-01 | Snap Head Rivet | A | 10 | Receipt | Receipt for Snap Head Rivet to approved drawing/detail | Stores | 10 |  | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | RVT-01 | Snap Head Rivet | A | 20 | MTC Verification / Material Identification | MTC Verification / Material Identification for Snap Head Rivet to approved drawing/detail | Quality Control / QA | 11 |  | 0.75 | Hours | Per material lot | No |  | Specification, grade, heat/lot and traceability match drawing/BOM | MTC review / PMI / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | RVT-01 | Snap Head Rivet | A | 30 | Inspection | Inspection for Snap Head Rivet to approved drawing/detail | Quality Control / QA | 25 |  | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | RIB-01 | Rib Plate | A | 10 | Receipt | Receipt for Rib Plate to approved drawing/detail | Stores | 10 |  | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | RIB-01 | Rib Plate | A | 20 | MTC Verification / Material Identification | MTC Verification / Material Identification for Rib Plate to approved drawing/detail | Quality Control / QA | 11 |  | 0.75 | Hours | Per material lot | No |  | Specification, grade, heat/lot and traceability match drawing/BOM | MTC review / PMI / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | RIB-01 | Rib Plate | A | 30 | Cutting / Blanking | Cutting / Blanking for Rib Plate to approved drawing/detail | Fabrication Prep | 12 |  | 0.3 | Hours | Per metre of cut | No |  | Cut size and identification meet approved drawing/cutting plan | Cutting report / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | RIB-01 | Rib Plate | A | 40 | Machining | Machining for Rib Plate to approved drawing/detail | Machine Shop | 14 |  | 2 | Hours | Per piece | No |  | Dimensions, thread, holes and finish meet drawing | Machining inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | RIB-01 | Rib Plate | A | 50 | Edge Preparation / Beveling | Edge Preparation / Beveling for Rib Plate to approved drawing/detail | Fabrication Prep | 12 |  | 0.35 | Hours | Per metre of edge | No |  | Bevel geometry and cleanliness meet drawing/WPS | Bevel / fit-up inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | RIB-01 | Rib Plate | A | 60 | Inspection | Inspection for Rib Plate to approved drawing/detail | Quality Control / QA | 25 |  | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | BOS-01 | Davit Pipe Boss | A | 10 | Receipt | Receipt for Davit Pipe Boss to approved drawing/detail | Stores | 10 |  | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | BOS-01 | Davit Pipe Boss | A | 20 | MTC Verification / Material Identification | MTC Verification / Material Identification for Davit Pipe Boss to approved drawing/detail | Quality Control / QA | 11 |  | 0.75 | Hours | Per material lot | No |  | Specification, grade, heat/lot and traceability match drawing/BOM | MTC review / PMI / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | BOS-01 | Davit Pipe Boss | A | 30 | Machining | Machining for Davit Pipe Boss to approved drawing/detail | Machine Shop | 14 |  | 2 | Hours | Per piece | No |  | Dimensions, thread, holes and finish meet drawing | Machining inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | BOS-01 | Davit Pipe Boss | A | 40 | Inspection | Inspection for Davit Pipe Boss to approved drawing/detail | Quality Control / QA | 25 |  | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | HDL-01 | Davit Handle | A | 10 | Receipt | Receipt for Davit Handle to approved drawing/detail | Stores | 10 |  | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | HDL-01 | Davit Handle | A | 20 | MTC Verification / Material Identification | MTC Verification / Material Identification for Davit Handle to approved drawing/detail | Quality Control / QA | 11 |  | 0.75 | Hours | Per material lot | No |  | Specification, grade, heat/lot and traceability match drawing/BOM | MTC review / PMI / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | HDL-01 | Davit Handle | A | 30 | Cutting / Blanking | Cutting / Blanking for Davit Handle to approved drawing/detail | Fabrication Prep | 12 |  | 0.3 | Hours | Per metre of cut | No |  | Cut size and identification meet approved drawing/cutting plan | Cutting report / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | HDL-01 | Davit Handle | A | 40 | Forming / Pressing / Dishing | Forming / Pressing / Dishing for Davit Handle to approved drawing/detail | Fabrication Prep | 13 |  | 3 | Hours | Per piece | No |  | Form, radius and dimensions meet approved detail | Forming inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | HDL-01 | Davit Handle | A | 50 | Inspection | Inspection for Davit Handle to approved drawing/detail | Quality Control / QA | 25 |  | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | JSC-01 | Jack Screw | A | 10 | Receipt | Receipt for Jack Screw to approved drawing/detail | Stores | 10 |  | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | JSC-01 | Jack Screw | A | 20 | MTC Verification / Material Identification | MTC Verification / Material Identification for Jack Screw to approved drawing/detail | Quality Control / QA | 11 |  | 0.75 | Hours | Per material lot | No |  | Specification, grade, heat/lot and traceability match drawing/BOM | MTC review / PMI / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | JSC-01 | Jack Screw | A | 30 | Machining | Machining for Jack Screw to approved drawing/detail | Machine Shop | 14 |  | 2 | Hours | Per piece | No |  | Dimensions, thread, holes and finish meet drawing | Machining inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | JSC-01 | Jack Screw | A | 40 | Inspection | Inspection for Jack Screw to approved drawing/detail | Quality Control / QA | 25 |  | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | AOP-01 | Access Opening Assembly | A | 10 | Receipt | Receipt for Access Opening Assembly to approved drawing/detail | Stores | 10 |  | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | AOP-01 | Access Opening Assembly | A | 20 | MTC Verification / Material Identification | MTC Verification / Material Identification for Access Opening Assembly to approved drawing/detail | Quality Control / QA | 11 |  | 0.75 | Hours | Per material lot | No |  | Specification, grade, heat/lot and traceability match drawing/BOM | MTC review / PMI / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | AOP-01 | Access Opening Assembly | A | 30 | Cutting / Blanking | Cutting / Blanking for Access Opening Assembly to approved drawing/detail | Fabrication Prep | 12 |  | 0.3 | Hours | Per metre of cut | No |  | Cut size and identification meet approved drawing/cutting plan | Cutting report / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | AOP-01 | Access Opening Assembly | A | 40 | Rolling | Rolling for Access Opening Assembly to approved drawing/detail | Fabrication Prep | 13 |  | 4 | Hours | Per piece | No |  | Diameter, roundness and straightness meet drawing tolerance | Dimensional inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | AOP-01 | Access Opening Assembly | A | 50 | Fit-up | Fit-up for Access Opening Assembly to approved drawing/detail | Fabrication / Welding | 19 |  | 1.5 | Hours | Per joint | No |  | Alignment, root gap, orientation and offset meet WPS/drawing | Fit-up report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | AOP-01 | Access Opening Assembly | A | 60 | Welding | Welding for Access Opening Assembly to approved drawing/detail | Fabrication / Welding | 20 |  | 1.2 | Hours | Per metre of weld | No |  | Weld completed to approved WPS by qualified welder; visual acceptable | Weld log / WPS / WPQ | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | AOP-01 | Access Opening Assembly | A | 70 | NDT | NDT for Access Opening Assembly to approved drawing/detail | Quality Control / QA | 22 |  | 1 | Hours | Per joint | Yes | When required by approved QAP/code or for pressure-retaining welds | Required RT/PT/MT/UT accepted to code/QAP | NDE report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | AOP-01 | Access Opening Assembly | A | 80 | Inspection | Inspection for Access Opening Assembly to approved drawing/detail | Quality Control / QA | 25 |  | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | PAD-01 | Attachment Pad Plate | A | 10 | Receipt | Receipt for Attachment Pad Plate to approved drawing/detail | Stores | 10 |  | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | PAD-01 | Attachment Pad Plate | A | 20 | MTC Verification / Material Identification | MTC Verification / Material Identification for Attachment Pad Plate to approved drawing/detail | Quality Control / QA | 11 |  | 0.75 | Hours | Per material lot | No |  | Specification, grade, heat/lot and traceability match drawing/BOM | MTC review / PMI / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | PAD-01 | Attachment Pad Plate | A | 30 | Cutting / Blanking | Cutting / Blanking for Attachment Pad Plate to approved drawing/detail | Fabrication Prep | 12 |  | 0.3 | Hours | Per metre of cut | No |  | Cut size and identification meet approved drawing/cutting plan | Cutting report / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | PAD-01 | Attachment Pad Plate | A | 40 | Rolling | Rolling for Attachment Pad Plate to approved drawing/detail | Fabrication Prep | 13 |  | 4 | Hours | Per piece | No |  | Diameter, roundness and straightness meet drawing tolerance | Dimensional inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | PAD-01 | Attachment Pad Plate | A | 50 | Machining | Machining for Attachment Pad Plate to approved drawing/detail | Machine Shop | 14 |  | 2 | Hours | Per piece | No |  | Dimensions, thread, holes and finish meet drawing | Machining inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | PAD-01 | Attachment Pad Plate | A | 60 | Inspection | Inspection for Attachment Pad Plate to approved drawing/detail | Quality Control / QA | 25 |  | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | LUG-02 | Lifting Lug (PV) | A | 10 | Receipt | Receipt for Lifting Lug (PV) to approved drawing/detail | Stores | 10 |  | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | LUG-02 | Lifting Lug (PV) | A | 20 | MTC Verification / Material Identification | MTC Verification / Material Identification for Lifting Lug (PV) to approved drawing/detail | Quality Control / QA | 11 |  | 0.75 | Hours | Per material lot | No |  | Specification, grade, heat/lot and traceability match drawing/BOM | MTC review / PMI / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | LUG-02 | Lifting Lug (PV) | A | 30 | Cutting / Blanking | Cutting / Blanking for Lifting Lug (PV) to approved drawing/detail | Fabrication Prep | 12 |  | 0.3 | Hours | Per metre of cut | No |  | Cut size and identification meet approved drawing/cutting plan | Cutting report / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | LUG-02 | Lifting Lug (PV) | A | 40 | Machining | Machining for Lifting Lug (PV) to approved drawing/detail | Machine Shop | 14 |  | 1.5 | Hours | Per piece | No |  | Dimensions, thread, holes and finish meet drawing | Machining inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | LUG-02 | Lifting Lug (PV) | A | 50 | Edge Preparation / Beveling | Edge Preparation / Beveling for Lifting Lug (PV) to approved drawing/detail | Fabrication Prep | 12 |  | 0.35 | Hours | Per metre of edge | No |  | Bevel geometry and cleanliness meet drawing/WPS | Bevel / fit-up inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | LUG-02 | Lifting Lug (PV) | A | 60 | Inspection | Inspection for Lifting Lug (PV) to approved drawing/detail | Quality Control / QA | 25 |  | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | SPL-01 | Lug Support Plate | A | 10 | Receipt | Receipt for Lug Support Plate to approved drawing/detail | Stores | 10 |  | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | SPL-01 | Lug Support Plate | A | 20 | MTC Verification / Material Identification | MTC Verification / Material Identification for Lug Support Plate to approved drawing/detail | Quality Control / QA | 11 |  | 0.75 | Hours | Per material lot | No |  | Specification, grade, heat/lot and traceability match drawing/BOM | MTC review / PMI / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | SPL-01 | Lug Support Plate | A | 30 | Cutting / Blanking | Cutting / Blanking for Lug Support Plate to approved drawing/detail | Fabrication Prep | 12 |  | 0.3 | Hours | Per metre of cut | No |  | Cut size and identification meet approved drawing/cutting plan | Cutting report / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | SPL-01 | Lug Support Plate | A | 40 | Machining | Machining for Lug Support Plate to approved drawing/detail | Machine Shop | 14 |  | 2 | Hours | Per piece | No |  | Dimensions, thread, holes and finish meet drawing | Machining inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | SPL-01 | Lug Support Plate | A | 50 | Edge Preparation / Beveling | Edge Preparation / Beveling for Lug Support Plate to approved drawing/detail | Fabrication Prep | 12 |  | 0.35 | Hours | Per metre of edge | No |  | Bevel geometry and cleanliness meet drawing/WPS | Bevel / fit-up inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | SPL-01 | Lug Support Plate | A | 60 | Inspection | Inspection for Lug Support Plate to approved drawing/detail | Quality Control / QA | 25 |  | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | TLG-01 | Tailing Lug | A | 10 | Receipt | Receipt for Tailing Lug to approved drawing/detail | Stores | 10 |  | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | TLG-01 | Tailing Lug | A | 20 | MTC Verification / Material Identification | MTC Verification / Material Identification for Tailing Lug to approved drawing/detail | Quality Control / QA | 11 |  | 0.75 | Hours | Per material lot | No |  | Specification, grade, heat/lot and traceability match drawing/BOM | MTC review / PMI / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | TLG-01 | Tailing Lug | A | 30 | Cutting / Blanking | Cutting / Blanking for Tailing Lug to approved drawing/detail | Fabrication Prep | 12 |  | 0.3 | Hours | Per metre of cut | No |  | Cut size and identification meet approved drawing/cutting plan | Cutting report / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | TLG-01 | Tailing Lug | A | 40 | Machining | Machining for Tailing Lug to approved drawing/detail | Machine Shop | 14 |  | 1.5 | Hours | Per piece | No |  | Dimensions, thread, holes and finish meet drawing | Machining inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | TLG-01 | Tailing Lug | A | 50 | Edge Preparation / Beveling | Edge Preparation / Beveling for Tailing Lug to approved drawing/detail | Fabrication Prep | 12 |  | 0.35 | Hours | Per metre of edge | No |  | Bevel geometry and cleanliness meet drawing/WPS | Bevel / fit-up inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | TLG-01 | Tailing Lug | A | 60 | Inspection | Inspection for Tailing Lug to approved drawing/detail | Quality Control / QA | 25 |  | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | NPB-01 | Name Plate Bracket | A | 10 | Receipt | Receipt for Name Plate Bracket to approved drawing/detail | Stores | 10 |  | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | NPB-01 | Name Plate Bracket | A | 20 | MTC Verification / Material Identification | MTC Verification / Material Identification for Name Plate Bracket to approved drawing/detail | Quality Control / QA | 11 |  | 0.75 | Hours | Per material lot | No |  | Specification, grade, heat/lot and traceability match drawing/BOM | MTC review / PMI / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | NPB-01 | Name Plate Bracket | A | 30 | Cutting / Blanking | Cutting / Blanking for Name Plate Bracket to approved drawing/detail | Fabrication Prep | 12 |  | 0.3 | Hours | Per metre of cut | No |  | Cut size and identification meet approved drawing/cutting plan | Cutting report / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | NPB-01 | Name Plate Bracket | A | 40 | Machining | Machining for Name Plate Bracket to approved drawing/detail | Machine Shop | 14 |  | 2 | Hours | Per piece | No |  | Dimensions, thread, holes and finish meet drawing | Machining inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | NPB-01 | Name Plate Bracket | A | 50 | Edge Preparation / Beveling | Edge Preparation / Beveling for Name Plate Bracket to approved drawing/detail | Fabrication Prep | 12 |  | 0.35 | Hours | Per metre of edge | No |  | Bevel geometry and cleanliness meet drawing/WPS | Bevel / fit-up inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | NPB-01 | Name Plate Bracket | A | 60 | Inspection | Inspection for Name Plate Bracket to approved drawing/detail | Quality Control / QA | 32 |  | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | NPL-01 | Name Plate | A | 10 | Receipt | Receipt for Name Plate to approved drawing/detail | Stores | 10 |  | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | NPL-01 | Name Plate | A | 20 | MTC Verification / Material Identification | MTC Verification / Material Identification for Name Plate to approved drawing/detail | Quality Control / QA | 11 |  | 0.75 | Hours | Per material lot | No |  | Specification, grade, heat/lot and traceability match drawing/BOM | MTC review / PMI / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | NPL-01 | Name Plate | A | 30 | Cutting / Blanking | Cutting / Blanking for Name Plate to approved drawing/detail | Fabrication Prep | 12 |  | 0.3 | Hours | Per metre of cut | No |  | Cut size and identification meet approved drawing/cutting plan | Cutting report / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | NPL-01 | Name Plate | A | 40 | Machining | Machining for Name Plate to approved drawing/detail | Machine Shop | 14 |  | 1.5 | Hours | Per piece | No |  | Dimensions, thread, holes and finish meet drawing | Machining inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | NPL-01 | Name Plate | A | 50 | Inspection | Inspection for Name Plate to approved drawing/detail | Quality Control / QA | 32 |  | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | FBL-01 | Foundation Bolt with Nut & Washer | A | 10 | Receipt | Receipt for Foundation Bolt with Nut & Washer to approved drawing/detail | Stores | 10 |  | 0.5 | Hours | Per material lot | No |  | PO/BOM, packing list and visible condition acceptable | GRN / incoming inspection record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | FBL-01 | Foundation Bolt with Nut & Washer | A | 20 | MTC Verification / Material Identification | MTC Verification / Material Identification for Foundation Bolt with Nut & Washer to approved drawing/detail | Quality Control / QA | 11 |  | 0.75 | Hours | Per material lot | No |  | Specification, grade, heat/lot and traceability match drawing/BOM | MTC review / PMI / traceability record | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.
PV DRAWING SOURCE | FBL-01 | Foundation Bolt with Nut & Washer | A | 30 | Inspection | Inspection for Foundation Bolt with Nut & Washer to approved drawing/detail | Quality Control / QA | 25 |  | 0.75 | Hours | Per piece | No |  | Visual and dimensional results meet drawing/QAP | Dimensional / final inspection report | PROPOSED TIME / ROUTE — drawing-backed part; validate by shop time study and Production Head approval.

## Assembly Sequence
REFERENCE + PROPOSED ASSEMBLY SEQUENCES — LIGHT-YELLOW PV ROWS ARE BASED ON APPROVED GA REV. C; WELD MAP AND METHODS REQUIRE APPROVAL.
How parts are joined into sub-assemblies and then the complete equipment, in order, with weld joint references (LS-1, CS-2…) where applicable. One list per equipment type. The PV rows are real data from the DESPL-320 assembly sequence already in the tracker; the HE rows only show the format.
Example? | Equipment Type | Group Code | Group Name | Step No. | Seq | Activity | Kind | Parts / Sub-assemblies used | Result (sub-assembly produced) | Weld Joint Ref. | Department | Counts toward Stage No. | Remarks
EXAMPLE (PV) | Vertical PV (DESPL-320) | E | Shell Sub-Assembly (LS-1) | 4.5 | 13 | Shell Weld Edge Preparation | Work | SHL-01 |  |  | Fabrication / Welding | 16 | From the PV assembly sequence already in the tracker
EXAMPLE (PV) | Vertical PV (DESPL-320) | E | Shell Sub-Assembly (LS-1) | 4.5 | 14 | L' Seam Set Up Of Shell (LS-1) Along With PTC | Work | SHL-01 |  |  | Fabrication / Welding | 16 | From the PV assembly sequence already in the tracker
EXAMPLE (PV) | Vertical PV (DESPL-320) | E | Shell Sub-Assembly (LS-1) | 4.5 | 15 | Weld Long Seam Of Shell (LS-1) | Work | SHL-01 | Shell (LS-1 welded) | LS-1 | Fabrication / Welding | 16 | From the PV assembly sequence already in the tracker
EXAMPLE (PV) | Vertical PV (DESPL-320) | E | Shell Sub-Assembly (LS-1) | 4.5 | 16 | Weld Visual Of LS-1 | Inspection |  |  |  | Quality Control / QA | 17 | From the PV assembly sequence already in the tracker
EXAMPLE (PV) | Vertical PV (DESPL-320) | E | Shell Sub-Assembly (LS-1) | 4.5 | 17 | PAUT/TOFD Of LS-1 | Inspection |  |  |  | Quality Control / QA | 17 | From the PV assembly sequence already in the tracker
EXAMPLE (PV) | Vertical PV (DESPL-320) | G | Shell + Bottom Head (CS-2) | 4.7 | 22 | Bottom Dished End To Shell Set Up (CS-2) | Work | Shell (LS-1 welded) + Bottom Dished End | Shell + bottom head |  | Fabrication / Welding | 16 | From the PV assembly sequence already in the tracker
EXAMPLE (PV) | Vertical PV (DESPL-320) | G | Shell + Bottom Head (CS-2) | 4.7 | 23 | Weld Circ Seam Of Bottom Dishend To Shell (CS-2) | Work |  |  | CS-2 | Fabrication / Welding | 16 | From the PV assembly sequence already in the tracker
EXAMPLE (PV) | Vertical PV (DESPL-320) | G | Shell + Bottom Head (CS-2) | 4.7 | 24 | Weld Visual Of CS-2 | Inspection |  |  |  | Quality Control / QA | 17 | From the PV assembly sequence already in the tracker
EXAMPLE (PV) | Vertical PV (DESPL-320) | G | Shell + Bottom Head (CS-2) | 4.7 | 25 | PAUT/TOFD Of CS-2 | Inspection |  |  |  | Quality Control / QA | 17 | From the PV assembly sequence already in the tracker
DRAWING REQUIREMENT | MED Train 1 (SP40) | HD-L | Left Dished Head Assembly | 1.1 | 10 | Locate NSA2 reinforcement pad on left dished head per drawing | Work | HED-01 + RFP-01 | Left head with NSA2 pad |  |  |  | SP40-02-03-04-001 Sheet 01 Rev.0; joining method/department/stage require approval.
DRAWING REQUIREMENT | MED Train 1 (SP40) | HD-R | Right Dished Head Assembly | 1.2 | 10 | Locate NSA3 reinforcement pad on right dished head per drawing | Work | HED-01 + RFP-01 | Right head with NSA3 pad |  |  |  | SP40-02-03-04-001 Sheet 02 Rev.0; joining method/department/stage require approval.
DRAWING REQUIREMENT | MED Train 1 (SP40) | TB | Tube-to-Tubesheet Joint | 2.1 | 10 | Install food-grade EPDM grommets at tubesheet penetrations | Work | GRM-01 + TSH-02 | Grommeted tubesheets |  |  |  | SP40-02-02-11-04/-05 Rev.0; operation ownership and stage pending.
DRAWING REQUIREMENT | MED Train 1 (SP40) | TB | Tube-to-Tubesheet Joint | 2.1 | 20 | Pass Ø21.3 tubes through 10 mm tubesheets and grommets to drawing lengths | Work | TUB-01 + GRM-01 + TSH-02 | Tube/tubesheet assembly |  |  |  | Drawing states tight fit with grommets; no expansion or seal welding is specified.
DRAWING REQUIREMENT | MED Train 1 (SP40) | TB | Tube-to-Tubesheet Joint | 2.1 | 30 | Verify tight fit and effective tube length | Inspection | Tube/tubesheet assembly | Tube bank ready for next approved assembly stage |  |  |  | Effective length 2950 for Effects 1–8 and 2210 for Effect 9; no joint test stated.
DRAWING REQUIREMENT | MED Train 1 (SP40) | SA | Saddle Sliding Interface | 3.1 | 10 | Fit food-grade PTFE sliding sheet to saddle arrangement | Work | SAD-01 + PTF-01 | Sliding saddle interface |  |  |  | SP40-02-02-11-01 Rev.0; joining/retention method and stage require approval.
PROPOSED HE ASSEMBLY | Fixed tubesheet / MED evaporator | S1 | Shell Course Sub-Assembly | 1.1 | 10 | Fit shell course longitudinal seam | Work | SHL-01 | Shell course fitted | LS-1 | Fabrication / Welding | 14 | Proposed baseline; confirm weld map and sequence
PROPOSED HE ASSEMBLY | Fixed tubesheet / MED evaporator | S1 | Shell Course Sub-Assembly | 1.1 | 20 | Weld shell course longitudinal seam | Work | SHL-01 | Welded shell course | LS-1 | Fabrication / Welding | 15 | Proposed baseline
PROPOSED HE ASSEMBLY | Fixed tubesheet / MED evaporator | S1 | Shell Course Sub-Assembly | 1.1 | 30 | NDE and dimensional inspection of longitudinal seam | Inspection | Welded shell course | Accepted shell course | LS-1 | Quality Control / QA | 16 | NDE extent per approved ITP/QAP
PROPOSED HE ASSEMBLY | Fixed tubesheet / MED evaporator | S2 | Shell Assembly | 1.2 | 40 | Fit and weld shell courses into complete shell | Work | Accepted shell courses | Complete shell | CS-1…n | Fabrication / Welding | 24 | Use actual weld joint numbers from job weld map
PROPOSED HE ASSEMBLY | Fixed tubesheet / MED evaporator | H1 | Head / Shell Assembly | 1.3 | 50 | Fit and weld formed heads to shell | Work | Complete shell + HED-01 | Shell with heads | CS-H1 / CS-H2 | Fabrication / Welding | 25 | Head arrangement per approved drawing
PROPOSED HE ASSEMBLY | Fixed tubesheet / MED evaporator | N1 | Nozzle Sub-Assembly | 1.4 | 60 | Fit nozzle flange to nozzle neck | Work | NOZ-01 + FLG-01 | Flanged nozzle sub-assembly | NW-1…n | Fabrication / Welding | 23 | Conditional if flange is welded to neck
PROPOSED HE ASSEMBLY | Fixed tubesheet / MED evaporator | N2 | Nozzle Installation | 1.5 | 70 | Fit and weld nozzle sub-assemblies to shell/head | Work | Flanged nozzle sub-assembly + shell/head | Pressure-part shell assembly | NS-1…n | Fabrication / Welding | 26 | Orientation/projection per approved drawing
PROPOSED HE ASSEMBLY | Fixed tubesheet / MED evaporator | P1 | Support Assembly | 1.6 | 80 | Fit and weld saddles/supports to shell | Work | Pressure-part shell assembly + SAD-01 | Supported shell assembly | SW-1…n | Fabrication / Welding | 27 | Include PTFE sliding sheet where specified
PROPOSED HE ASSEMBLY | Fixed tubesheet / MED evaporator | T1 | Tubesheet Assembly | 2.1 | 90 | Fit tubesheets to shell or bundle location | Work | Supported shell assembly + TSH-01 | Shell/tubesheet assembly | TS-1 / TS-2 | Fabrication / Welding | 35 | Exact sequence depends on fixed/removable construction
PROPOSED HE ASSEMBLY | Fixed tubesheet / MED evaporator | B1 | Baffle / Support Frame | 2.2 | 100 | Assemble baffles/support plates at design spacing | Work | BAF-01 + tie/support members | Baffle/support frame |  | Fabrication / Welding | 29 | Conditional when baffles/support plates are used
PROPOSED HE ASSEMBLY | Fixed tubesheet / MED evaporator | T2 | Tube Joint Preparation | 2.3 | 110 | Clean tube holes and install grommets or prepare grooves | Work | TSH-01 + job-specific grommets | Prepared tubesheets |  | Fabrication / Welding | 30 | SP40 uses EPDM grommets; other designs may use expansion grooves
PROPOSED HE ASSEMBLY | Fixed tubesheet / MED evaporator | T3 | Tube Bundle Assembly | 2.4 | 120 | Insert tubes through tubesheets and baffles/supports | Work | TUB-01 + prepared tubesheets + baffle frame | Inserted tube bundle |  | Fabrication / Welding | 32 | Protect tube surfaces and verify effective length
PROPOSED HE ASSEMBLY | Fixed tubesheet / MED evaporator | T4 | Tube Joint Completion | 2.5 | 130 | Expand and/or seal weld tube ends when specified | Work | Inserted tube bundle | Completed tube joints | TJ-1…n | Fabrication / Welding | 33 | Conditional; not assumed for SP40 grommeted joint
PROPOSED HE ASSEMBLY | Fixed tubesheet / MED evaporator | T5 | Bundle Inspection | 2.6 | 140 | Inspect tube joints, tube projection and bundle dimensions | Inspection | Completed/inserted tube bundle | Accepted bundle |  | Quality Control / QA | 34 | Test/inspection method per approved QAP
PROPOSED HE ASSEMBLY | Fixed tubesheet / MED evaporator | C1 | Closure Assembly | 3.1 | 150 | Fit channel/bonnet closures with gaskets | Work | Shell/tubesheet assembly + GAS-01 | Closed exchanger |  | Fabrication / Welding | 36 | Gasket type and orientation per drawing
PROPOSED HE ASSEMBLY | Fixed tubesheet / MED evaporator | C1 | Closure Assembly | 3.1 | 160 | Install studs and nuts using approved tightening sequence | Work | Closed exchanger + STD-01 | Bolted exchanger |  | Fabrication / Welding | 36 | Lubrication and torque/tension per approved procedure
PROPOSED HE ASSEMBLY | Fixed tubesheet / MED evaporator | Q1 | Final Internal Inspection | 3.2 | 170 | Verify cleanliness, internals, tube ends and closure readiness | Inspection | Bolted exchanger | Released for pressure test |  | Quality Control / QA | 37 | Inspection release required before hydrotest
PROPOSED HE ASSEMBLY | Fixed tubesheet / MED evaporator | Q2 | Shell-Side Hydrotest | 3.3 | 180 | Perform shell-side hydrostatic test | Inspection | Released exchanger | Shell-side test accepted |  | Quality Control / QA | 38 | Pressure/hold time per approved drawing/QAP
PROPOSED HE ASSEMBLY | Fixed tubesheet / MED evaporator | Q3 | Tube-Side Hydrotest | 3.4 | 190 | Perform tube-side hydrostatic test | Inspection | Shell-side test accepted | Tube-side test accepted |  | Quality Control / QA | 39 | Separate test report required
PROPOSED HE ASSEMBLY | Fixed tubesheet / MED evaporator | F1 | Complete Equipment | 4.1 | 200 | Final inspection, nameplate, MDR release and dispatch preparation | Inspection | Tube-side test accepted | Complete heat exchanger |  | Documentation / MDR | 41 | Production Head/PPC approval required before tracker load
PV DRAWING SOURCE | HP Air Receiver Blow Down Vessel | PV-S1 | Shell Course | 1.1 | 10 | Roll and fit shell longitudinal seam | Work | SHL-01 | Shell course fitted | LS-1 | Fabrication / Welding | 15 | Drawing item 101; weld map reference to be confirmed
PV DRAWING SOURCE | HP Air Receiver Blow Down Vessel | PV-S1 | Shell Course | 1.1 | 20 | Weld shell longitudinal seam to approved WPS | Work | Fitted shell course | Welded shell course | LS-1 | Fabrication / Welding | 16 | Full penetration pressure weld
PV DRAWING SOURCE | HP Air Receiver Blow Down Vessel | PV-S1 | Shell Course | 1.1 | 30 | Perform required RT/PT and dimensional inspection | Inspection | Welded shell course | Accepted shell course | LS-1 | Quality Control / QA | 17 | 100% RT of butt welds; all welds PT
PV DRAWING SOURCE | HP Air Receiver Blow Down Vessel | PV-H1 | Head Assembly | 1.2 | 40 | Fit top dished end to shell | Work | Accepted shell course + HED-01 | Top-head fit-up | CS-1 | Fabrication / Welding | 18 | Drawing item 102
PV DRAWING SOURCE | HP Air Receiver Blow Down Vessel | PV-H1 | Head Assembly | 1.2 | 50 | Weld top dished end to shell | Work | Top-head fit-up | Shell with top head | CS-1 | Fabrication / Welding | 18 | Full penetration pressure weld
PV DRAWING SOURCE | HP Air Receiver Blow Down Vessel | PV-H2 | Head Assembly | 1.3 | 60 | Fit and weld bottom dished end to shell | Work | Shell with top head + HED-01 | Closed pressure shell | CS-2 | Fabrication / Welding | 18 | Full penetration pressure weld
PV DRAWING SOURCE | HP Air Receiver Blow Down Vessel | PV-H2 | Head Assembly | 1.3 | 70 | Perform RT/PT of head circumferential seams | Inspection | Closed pressure shell | Accepted pressure shell | CS-1 / CS-2 | Quality Control / QA | 17 | 100% RT of butt welds; all welds PT
PV DRAWING SOURCE | HP Air Receiver Blow Down Vessel | PV-N1 | Nozzle Sub-Assemblies | 2.1 | 80 | Prepare N1 inlet flange and reinforcement pad assembly | Work | NOZ-01 + FLG-01 + RFP-02 | N1 sub-assembly | NW-N1 | Fabrication / Welding | 19 | Class 300 LWN RF; R-pad vent hole required
PV DRAWING SOURCE | HP Air Receiver Blow Down Vessel | PV-N2 | Nozzle Sub-Assemblies | 2.2 | 90 | Prepare N2 drain pipe, elbow and flange assembly | Work | NOZ-01 + ELB-01 + FLG-01 + STF-01 | N2 sub-assembly | NW-N2 | Fabrication / Welding | 19 | SA333 Gr.6 pipe per Rev. C
PV DRAWING SOURCE | HP Air Receiver Blow Down Vessel | PV-N3 | Nozzle Sub-Assemblies | 2.3 | 100 | Prepare N3 outlet self-reinforced nozzle and flange | Work | SRN-01 + FLG-01 + STF-01 | N3 sub-assembly | NW-N3 | Fabrication / Welding | 19 | DN125 Class 300 WNRF
PV DRAWING SOURCE | HP Air Receiver Blow Down Vessel | PV-N4 | Instrument Connections | 2.4 | 110 | Prepare N4, N5 and N6 coupling/plug connections | Work | CPL-01 | Instrument connection sub-assemblies | NW-N4/N5/N6 | Fabrication / Welding | 19 | Pressure gauge, transmitter and safety valve
PV DRAWING SOURCE | HP Air Receiver Blow Down Vessel | PV-M1 | Manhole Sub-Assembly | 2.5 | 120 | Prepare M1 SRN, flange and blind flange | Work | SRN-01 + FLG-01 + BFL-01 | M1 manhole neck assembly | NW-M1 | Fabrication / Welding | 19 | DN450 Class 300
PV DRAWING SOURCE | HP Air Receiver Blow Down Vessel | PV-NOZ | Nozzle Installation | 2.6 | 130 | Mark and cut vessel openings; fit nozzle/manhole sub-assemblies | Work | Accepted pressure shell + nozzle sub-assemblies | Nozzle-fitted shell | NS-N1…N6 / NS-M1 | Fabrication / Welding | 19 | Orientation and projection per GA
PV DRAWING SOURCE | HP Air Receiver Blow Down Vessel | PV-NOZ | Nozzle Installation | 2.6 | 140 | Weld nozzles/manhole and reinforcement pads to vessel | Work | Nozzle-fitted shell | Welded nozzle shell | NS-N1…N6 / NS-M1 | Fabrication / Welding | 20 | Pressure welds FPW; pad vent holes
PV DRAWING SOURCE | HP Air Receiver Blow Down Vessel | PV-HT | Heat Treatment | 2.7 | 150 | Perform required post-forming heat treatment and PWHT | Work | Welded nozzle shell | Heat-treated pressure assembly |  | Heat Treatment | 21 | Drawing explicitly requires PFHT and PWHT; approved cycle/chart required
PV DRAWING SOURCE | HP Air Receiver Blow Down Vessel | PV-NDE | Post-PWHT Examination | 2.8 | 160 | Perform post-PWHT NDE, hardness and visual checks as applicable | Inspection | Heat-treated pressure assembly | Accepted pressure assembly | Pressure weld map | Quality Control / QA | 22 | Per ASME/QAP and heat-treatment procedure
PV DRAWING SOURCE | HP Air Receiver Blow Down Vessel | PV-SK | Skirt Sub-Assembly | 3.1 | 170 | Roll and weld skirt shell | Work | SKT-01 | Skirt shell | LS-SK | Fabrication / Welding | 23 | Drawing item 201
PV DRAWING SOURCE | HP Air Receiver Blow Down Vessel | PV-SK | Skirt Sub-Assembly | 3.1 | 180 | Fit base ring and 32 gusset plates to skirt | Work | Skirt shell + SBR-01 + GSP-02 | Skirt/base-ring assembly | BR-SK / GW-1…32 | Fabrication / Welding | 23 | Drawing items 202–203
PV DRAWING SOURCE | HP Air Receiver Blow Down Vessel | PV-SK | Skirt Installation | 3.2 | 190 | Fit and weld skirt assembly to bottom head | Work | Accepted pressure assembly + skirt/base-ring assembly | Vessel on skirt | SK-1 | Fabrication / Welding | 23 | Non-ASME material shall not be directly welded to pressure part; follow drawing pad/interface detail
PV DRAWING SOURCE | HP Air Receiver Blow Down Vessel | PV-ATT | Lugs and Pads | 3.3 | 200 | Fit pad plates, lifting lugs, support plates and tailing lug | Work | PAD-01 + LUG-02 + SPL-01 + TLG-01 | Lug-equipped vessel | LW-1…n | Fabrication / Welding | 23 | All attachment pads require 6 mm air vent hole where applicable
PV DRAWING SOURCE | HP Air Receiver Blow Down Vessel | PV-DAV | Davit / Access Opening | 3.4 | 210 | Assemble access opening, davit pipe, boss, end plates, handle, hook, eye bolt and jack screws | Work | AOP-01 + DVT-01 + BOS-01 + EPL-01 + HDL-01 + HOK-01 + EYE-01 + JSC-01 + NUT-02 + WSH-02 + RVT-01 + RIB-01 | Davit/access-opening assembly | DW-1…n | Fabrication / Welding | 23 | Detail-controlled assembly
PV DRAWING SOURCE | HP Air Receiver Blow Down Vessel | PV-EXT | External Attachments | 3.5 | 220 | Install support pipes, earthing plates and other external attachments | Work | SPP-01 + ERT-01 | Attachment-complete vessel | AW-1…n | Fabrication / Welding | 23 | Earthing plates shall not be painted
PV DRAWING SOURCE | HP Air Receiver Blow Down Vessel | PV-NP | Name Plate Support | 3.6 | 230 | Fit nameplate bracket to vessel | Work | NPB-01 | Vessel with nameplate bracket | NPW-1 | Fabrication / Welding | 24 | Nameplate installed after painting
PV DRAWING SOURCE | HP Air Receiver Blow Down Vessel | PV-M1 | Manhole Closure | 3.7 | 240 | Install M1 gasket and blind flange with studs/nuts | Work | M1 assembly + GAS-01 + STD-01 | Closed vessel |  | Fabrication / Welding | 24 | Approved gasket; controlled tightening sequence required
PV DRAWING SOURCE | HP Air Receiver Blow Down Vessel | PV-QC | Final Dimensional Inspection | 4.1 | 250 | Verify vessel dimensions, verticality, nozzle orientation/projection and attachments | Inspection | Closed vessel | Released for pressure test |  | Quality Control / QA | 25 | As per approved GA/QAP
PV DRAWING SOURCE | HP Air Receiver Blow Down Vessel | PV-QC | Final Visual Inspection | 4.2 | 260 | Complete final internal/external visual inspection | Inspection | Released vessel | Hydrotest-ready vessel |  | Quality Control / QA | 26 | All sharp edges rounded; temporary attachments removed
PV DRAWING SOURCE | HP Air Receiver Blow Down Vessel | PV-HTEST | Hydrostatic Test | 4.3 | 270 | Hydrotest at approved pressure and hold time | Inspection | Hydrotest-ready vessel | Hydrotest accepted |  | Quality Control / QA | 27 | 66–66.5 kg/cm²(g); 18–48°C; 30 min
PV DRAWING SOURCE | HP Air Receiver Blow Down Vessel | PV-DRY | Draining and Drying | 4.4 | 280 | Drain, dry and preserve vessel after hydrotest | Work | Hydrotest accepted | Dry preserved vessel |  | Fabrication / Welding | 28 | Record dryness/preservation
PV DRAWING SOURCE | HP Air Receiver Blow Down Vessel | PV-PAINT | Surface Treatment and Painting | 4.5 | 290 | Prepare and coat external surfaces; protect machined faces and threads | Work | Dry preserved vessel | Painted vessel |  | Surface Treatment & Painting | 30 | Earthing plates excluded; system per approved paint specification
PV DRAWING SOURCE | HP Air Receiver Blow Down Vessel | PV-NP | Name Plate and Stamping | 4.6 | 300 | Engrave/install SS304 nameplate and complete final stamping | Inspection | Painted vessel + NPL-01 | Identified vessel |  | Quality Control / QA | 32 | Drawing item 242; engraving content per approved nameplate detail
PV DRAWING SOURCE | HP Air Receiver Blow Down Vessel | PV-DOC | MDR and Release | 4.7 | 310 | Compile MTC, weld/NDE/PWHT/hydro records, approved drawings and release documents | Inspection | Identified vessel | Released pressure vessel |  | Documentation / MDR | 33 | Final tracker load remains subject to Production Head approval

## New Operations
SOURCE REVIEW REGISTER — LIGHT-YELLOW PV/HE OPERATION PROPOSALS REMAIN OUTSIDE THE FIXED DROPDOWN UNTIL APPROVED.
Only for steps that do not fit any operation in the dropdown. We will review these together before adding them to the tracker.
Example? | Proposed Operation | Used in (Part Codes) | Department | Why the existing list does not cover it | Record / Document | Remarks
SOURCE REVIEW | Forging | FLG-01, TSH-01 | Vendor (outside DESPL) | Fixed list has no forging operation; decide whether vendor process is tracked or only Receipt is used. | MTC; forging record | Production Head decision required
SOURCE REVIEW | Heat Treatment / PFHT / PWHT | SHL-01, HED-01, FLG-01, TSH-01; complete PV DE0423 | Heat Treatment | Fixed list has no heat-treatment operation; PV drawing requires post-forming heat treatment and PWHT. | Heat-treatment procedure, furnace/local chart, hardness report | Map approved PV execution to Stage 21; route approval required
SOURCE REVIEW | Hydrostatic Testing | Complete HE; complete PV DE0423 | Quality Control / QA | Fixed list has no hydrostatic-test operation; PV drawing requires 66–66.5 kg/cm²(g), 18–48°C, 30 min. | Hydro test report | PV Stage 27; HE shell/tube-side stages remain separate
SOURCE REVIEW | Tube Cleaning | TUB-01 | Fabrication Prep | Cleaning after cutting is not clearly covered by a fixed operation. | Cleaning record | Confirm whether separate tracking is required
SOURCE REVIEW | Engraving / Marking | NPL-01; Name Plate | Machine Shop | Fixed list has no engraving/marking operation. | Nameplate record / rubbing | PV drawing item 242 and Stage 32
SOURCE REVIEW | Installation | PV attachments, manhole closure, NPL-01; HE listed parts | Fabrication / Welding | Assembly Check is an inspection gate, not installation work. | Assembly record | Covers PV accessories and HE components if approved
SOURCE REVIEW | Tube Bundle Assembly / Tube Insertion | TUB-01, TSH-01, BAF-01 | Fabrication / Welding | Fixed list has Tube Expansion but no tube insertion/bundle assembly operation. | Bundle assembly record | Could be approved under Installation instead of a separate operation
SOURCE REVIEW | Tube Joint Leak Test | TUB-01, TSH-01 | Quality Control / QA | NDT does not clearly represent pneumatic/leak testing of tube joints. | Tube leak test report | Define method and acceptance by HE type/QAP
SOURCE REVIEW | Controlled Bolting / Torqueing | STD-01, GAS-01, BFL-01 | Fabrication / Welding | Fixed list has no controlled tightening operation for Class 300 manhole closure. | Bolt torque/tension record | Approve lubricant, tightening pattern and final record requirement
SOURCE REVIEW | Passivation / Chemical Cleaning | S32205 / titanium pressure parts | Surface Treatment & Painting | Surface Preparation / Blasting does not cover chemical cleaning/passivation. | Cleaning/passivation report | Define alloy- and service-specific requirement
SOURCE REVIEW | Zinc Coating of Studs and Nuts | STD-01 | Vendor (outside DESPL) | PV drawing requires all studs and nuts to be zinc coated; fixed list does not identify coating of fasteners. | Supplier coating certificate / inspection record | Confirm coating process and acceptance thickness
SOURCE REVIEW | Temporary Flange Cover Installation | All PV flanged openings | Dispatch & Logistics | Drawing requires temporary gasket and 3/6 mm metallic cover with all bolts; fixed operation list has no protection-installation step. | Packing / flange protection checklist | Could be controlled under Packing & Preservation stage 34
SOURCE REVIEW | Post-Forming Heat Treatment | HED-01 | Heat Treatment | Drawing explicitly requires PFHT separately from PWHT. | PFHT chart and release report | Confirm whether separate tracker operation is required
SOURCE REVIEW | Hardness Testing After PWHT | Complete PV DE0423 | Quality Control / QA | NDT operation does not explicitly represent hardness survey after heat treatment. | Hardness test report | Confirm locations and acceptance criteria from QAP/procedure

## HE Stages
PROPOSED PLANNING BASELINE — NOT APPROVED. Durations and ownership are working estimates for Production Head/PPC review; revise from actual shop records before tracker load.
Whole-equipment stages for a fixed-tubesheet / MED-type heat exchanger. Includes SP40-specific fabricated tubesheets and grommeted titanium tube assembly; optional rules identify other HE configurations.
Example? | HE Type | Stage No. | Stage Name | Main Activities | Department | Duration Min (days) | Duration Max (days) | Predecessor Stage No(s). | Link Type | Lag / Overlap (days) | Optional? | When is it optional? | Remarks
PROPOSED | Fixed tubesheet / MED evaporator | 1 | PO Receipt & Order Review | Review PO, scope, specification, delivery and commercial requirements | Projects / PMO | 1 | 2 | — | Finish-to-Start | 0 | No |  | Planning estimate; Production Head/PPC approval required
PROPOSED | Fixed tubesheet / MED evaporator | 2 | Kick-Off / Pre-Inspection Meeting | Internal kick-off, client/PIM, ITP/QAP and responsibility matrix | Projects / PMO | 2 | 3 | 1 | Finish-to-Start | 0 | No |  | Planning estimate
PROPOSED | Fixed tubesheet / MED evaporator | 3 | Thermal & Mechanical Design | Thermal rating, pressure design, tube count, vibration and support checks | Design & Detail Engineering | 7 | 15 | 2 | Finish-to-Start | 0 | No |  | Planning estimate
PROPOSED | Fixed tubesheet / MED evaporator | 4 | Manufacturing Drawings | GA, tubesheet layout, bundle, nozzle, support and weld details | Design & Detail Engineering | 7 | 15 | 3 | Finish-to-Start | 0 | No |  | Planning estimate
PROPOSED | Fixed tubesheet / MED evaporator | 5 | Client Drawing Approval | Submission, comments, revision and approval | Design & Detail Engineering | 5 | 15 | 4 | Finish-to-Start | 0 | No |  | Planning estimate
PROPOSED | Fixed tubesheet / MED evaporator | 6 | BOM, MTO & Route Release | Finalize BOM/MTO, cutting plans, route and work packs | Planning / PPC | 2 | 4 | 4, 5 | Finish-to-Start | 0 | No |  | May overlap approval only with documented risk release
PROPOSED | Fixed tubesheet / MED evaporator | 7 | Plate Procurement | Shell, head, baffle, saddle and fabricated tubesheet plate | Procurement | 28 | 56 | 3 | Finish-to-Start | 0 | No |  | Planning estimate
PROPOSED | Fixed tubesheet / MED evaporator | 8 | Tube Procurement | Heat-exchanger tubes and certificates | Procurement | 28 | 70 | 4 | Finish-to-Start | 0 | No |  | Titanium/alloy tube lead time is project-specific
PROPOSED | Fixed tubesheet / MED evaporator | 9 | Forging / Pipe / Flange Procurement | Nozzle necks, flanges, forgings and fittings | Procurement | 21 | 42 | 4 | Finish-to-Start | 0 | No |  | Planning estimate
PROPOSED | Fixed tubesheet / MED evaporator | 10 | Bought-Out Items Procurement | Gaskets, fasteners, grommets, instruments and nameplate | Procurement | 14 | 35 | 4 | Finish-to-Start | 0 | No |  | Planning estimate
PROPOSED | Fixed tubesheet / MED evaporator | 11 | Material Receipt & Incoming Inspection | GRN, MTC review, visual and dimensional receipt inspection | Stores | 1 | 3 | 7, 8, 9, 10 | Finish-to-Start | 0 | No |  | May be repeated by material lot
PROPOSED | Fixed tubesheet / MED evaporator | 12 | Material Identification & Traceability | PMI where required, heat-number transfer and traceability records | Quality Control / QA | 1 | 2 | 11 | Finish-to-Start | 0 | No |  | Planning estimate
PROPOSED | Fixed tubesheet / MED evaporator | 13 | Cutting / Blanking | Cut shell, heads, baffles, saddles and tubesheet components | Fabrication Prep | 2 | 5 | 12 | Finish-to-Start | 0 | No |  | Planning estimate
PROPOSED | Fixed tubesheet / MED evaporator | 14 | Shell Rolling & Long-Seam Fit-Up | Roll shell courses, align and fit longitudinal seams | Fabrication Prep | 3 | 7 | 13 | Finish-to-Start | 0 | No |  | Planning estimate
PROPOSED | Fixed tubesheet / MED evaporator | 15 | Shell Long-Seam Welding | Weld longitudinal seams to approved WPS | Fabrication / Welding | 3 | 7 | 14 | Finish-to-Start | 0 | No |  | Planning estimate
PROPOSED | Fixed tubesheet / MED evaporator | 16 | Shell-Seam NDE & Dimensional Check | Specified RT/UT/PT plus roundness and dimensional checks | Quality Control / QA | 2 | 5 | 15 | Finish-to-Start | 0 | No |  | Extent per ITP/QAP
PROPOSED | Fixed tubesheet / MED evaporator | 17 | Head Forming & Inspection | Cold/hot form heads, trim, profile and examine | Fabrication Prep | 4 | 10 | 13 | Finish-to-Start | 0 | No |  | SP40 requires cold forming and full DP both sides
PROPOSED | Fixed tubesheet / MED evaporator | 18 | Tubesheet Fabrication / Weld Assembly | Prepare segments/plates, fit and weld fabricated tubesheets | Fabrication / Welding | 4 | 10 | 13 | Finish-to-Start | 0 | Yes | Only for fabricated or segmental tubesheets | Not used for one-piece forged tubesheets
PROPOSED | Fixed tubesheet / MED evaporator | 19 | Tubesheet Pre-Drill NDE | Complete required NDE of tubesheet welds before drilling | Quality Control / QA | 1 | 3 | 18 | Finish-to-Start | 0 | Yes | When tubesheet is fabricated/welded | SP40 requires 100% RT before drilling
PROPOSED | Fixed tubesheet / MED evaporator | 20 | Tubesheet Machining & Drilling | Face, drill/ream tube holes, machine grooves and deburr | Machine Shop | 5 | 15 | 12, 19 | Finish-to-Start | 0 | No |  | For forged tubesheet predecessor 12; fabricated predecessor 19
PROPOSED | Fixed tubesheet / MED evaporator | 21 | Tubesheet Final Inspection | Hole size/pitch, finish, flatness, thickness and dimensional checks | Quality Control / QA | 1 | 3 | 20 | Finish-to-Start | 0 | No |  | Planning estimate
PROPOSED | Fixed tubesheet / MED evaporator | 22 | Baffle / Support Plate Fabrication | Cut, drill/machine, deburr and inspect baffles/support plates | Machine Shop | 3 | 8 | 13 | Finish-to-Start | 0 | Yes | When bundle has baffles or support plates | Planning estimate
PROPOSED | Fixed tubesheet / MED evaporator | 23 | Nozzle & Flange Preparation | Cut necks, machine flanges, bevel and inspect | Machine Shop | 2 | 5 | 12 | Finish-to-Start | 0 | No |  | Planning estimate
PROPOSED | Fixed tubesheet / MED evaporator | 24 | Shell Course Assembly | Join shell courses and complete circumferential seams | Fabrication / Welding | 3 | 8 | 16 | Finish-to-Start | 0 | No |  | Planning estimate
PROPOSED | Fixed tubesheet / MED evaporator | 25 | Head-to-Shell Assembly | Fit and weld heads/closures to shell | Fabrication / Welding | 2 | 5 | 17, 24 | Finish-to-Start | 0 | No |  | Planning estimate
PROPOSED | Fixed tubesheet / MED evaporator | 26 | Nozzle Fit-Up & Welding | Mark, cut openings, fit and weld nozzles/reinforcement | Fabrication / Welding | 3 | 7 | 23, 25 | Finish-to-Start | 0 | No |  | Planning estimate
PROPOSED | Fixed tubesheet / MED evaporator | 27 | Supports & External Attachments | Fit/weld saddles, clips, lugs and other attachments | Fabrication / Welding | 2 | 5 | 25 | Finish-to-Start | 0 | No |  | Planning estimate
PROPOSED | Fixed tubesheet / MED evaporator | 28 | Post-Weld NDE / PWHT | NDE and PWHT where required by code/material/thickness | Quality Control / QA | 2 | 7 | 26, 27 | Finish-to-Start | 0 | Yes | As required by code, material, thickness, service or QAP | PWHT operation remains subject to approval
PROPOSED | Fixed tubesheet / MED evaporator | 29 | Bundle Frame Assembly | Assemble tie rods, baffles/support plates and bundle framework | Fabrication / Welding | 3 | 7 | 21, 22 | Finish-to-Start | 0 | Yes | For removable or framed tube bundles | MED arrangement may assemble directly between tubesheets
PROPOSED | Fixed tubesheet / MED evaporator | 30 | Grommet / Tube-Hole Preparation | Clean holes and install approved grommets or prepare expansion grooves | Fabrication / Welding | 2 | 5 | 21 | Finish-to-Start | 0 | Yes | For grommeted or mechanically expanded tube joints | SP40 uses food-grade EPDM grommets
PROPOSED | Fixed tubesheet / MED evaporator | 31 | Tube Cutting, Cleaning & Inspection | Cut tubes to length, clean, identify and inspect | Fabrication Prep | 2 | 5 | 8, 12 | Finish-to-Start | 0 | No |  | Planning estimate
PROPOSED | Fixed tubesheet / MED evaporator | 32 | Tube Insertion / Bundle Assembly | Insert tubes through tubesheets, baffles and grommets | Fabrication / Welding | 4 | 12 | 29, 30, 31 | Finish-to-Start | 0 | No |  | Planning estimate
PROPOSED | Fixed tubesheet / MED evaporator | 33 | Tube Expansion / Seal Welding | Expand and/or seal weld tube ends to approved procedure | Fabrication / Welding | 3 | 10 | 32 | Finish-to-Start | 0 | Yes | When the approved tube joint requires expansion or seal welding | Not stated for SP40 grommeted joint
PROPOSED | Fixed tubesheet / MED evaporator | 34 | Tube Joint / Bundle Inspection | Visual, dimensional, mock-up/pull-out or leak checks per QAP | Quality Control / QA | 1 | 4 | 32, 33 | Finish-to-Start | 0 | No |  | Use predecessor 32 when stage 33 is not applicable
PROPOSED | Fixed tubesheet / MED evaporator | 35 | Bundle Insertion / Tubesheet Fit-Up | Insert removable bundle or fit tubesheet/bundle into shell | Fabrication / Welding | 2 | 5 | 25, 34 | Finish-to-Start | 0 | Yes | Sequence depends on fixed/removable bundle construction | For fixed tubesheet units this may be progressive assembly
PROPOSED | Fixed tubesheet / MED evaporator | 36 | Channel / Bonnet Assembly | Fit channels, bonnets, pass partitions, gaskets and bolting | Fabrication / Welding | 2 | 5 | 26, 35 | Finish-to-Start | 0 | No |  | Planning estimate
PROPOSED | Fixed tubesheet / MED evaporator | 37 | Final Internal Inspection & Closure | Cleanliness, internals, tube ends, pass partition and closure checks | Quality Control / QA | 1 | 3 | 36 | Finish-to-Start | 0 | No |  | Planning estimate
PROPOSED | Fixed tubesheet / MED evaporator | 38 | Shell-Side Hydrostatic Test | Fill, vent, pressurize, hold, inspect and drain shell side | Quality Control / QA | 1 | 2 | 37 | Finish-to-Start | 0 | No |  | Test pressure/hold time per approved drawing and QAP
PROPOSED | Fixed tubesheet / MED evaporator | 39 | Tube-Side Hydrostatic Test | Fill, vent, pressurize, hold, inspect and drain tube side | Quality Control / QA | 1 | 2 | 38 | Finish-to-Start | 0 | No |  | Separate report required
PROPOSED | Fixed tubesheet / MED evaporator | 40 | Surface Treatment / Painting | Surface preparation, coating, DFT checks and touch-up | Surface Treatment & Painting | 3 | 7 | 39 | Finish-to-Start | 0 | Yes | As required by material, service and paint specification | Stainless/titanium surfaces may require cleaning/passivation instead
PROPOSED | Fixed tubesheet / MED evaporator | 41 | Final Inspection, MDR & Release | Final dimensions, nameplate, punch closure, MDR and release note | Documentation / MDR | 2 | 5 | 39, 40 | Finish-to-Start | 0 | No |  | Use predecessor 39 when stage 40 is not applicable
PROPOSED | Fixed tubesheet / MED evaporator | 42 | Packing & Dispatch | Preservation, packing, loading and dispatch documentation | Dispatch & Logistics | 1 | 3 | 41 | Finish-to-Start | 0 | No |  | Planning estimate

## PV Stages (ref)
REFERENCE DATA FROM THE TRACKER (do not edit). Use it to fill stage numbers in other sheets.
The 36-stage pressure vessel lead-time table currently in the tracker. Use the Stage No. here in the 'Counts toward PV Stage No.' column of Part Routes and in Assembly Sequence. If anything here is wrong, tell us rather than editing.
Stage No. | Stage Name | Main Activities | Department | Min Days | Max Days | Predecessor(s)
1 | PO Receipt & Order Review | PO review, scope, technical specification, drawings, delivery requirement, commercial conditions | Projects / PMO | 1 | 2 | —
2 | Kick-Off / Pre-Inspection Meeting | Internal kick-off, client/PIM, QCP/ITP finalization, responsibility matrix | Projects / PMO | 2 | 3 | 1
3 | Engineering - Design Calculation | Design calculation, PV Elite analysis, nozzle calculation, flange/skirt/support calculation | Design & Detail Engineering | 5 | 10 | 2
4 | Engineering - Manufacturing Drawings | GA drawing, fabrication drawing, nozzle orientation, support details, weld details | Design & Detail Engineering | 5 | 10 | 3
5 | Client Drawing Approval | Submission, review, comments, revision and approval | Design & Detail Engineering | 5 | 15 | 4
6 | BOM & MTO Finalization | BOM, raw-material requirement, cutting plan, bought-out items | Planning / PPC | 2 | 4 | 4
7 | Material Procurement - Plates | RFQ, quotation, PO to mill/vendor, manufacturing, inspection, dispatch | Procurement | 28 | 56 | 3
8 | Material Procurement - Pipes/Forgings/Fittings | Shell pipes, nozzles, flanges, forgings, fittings, etc. | Procurement | 21 | 42 | 4
9 | Bought-Out Items Procurement | Gaskets, fasteners, valves, instruments, name plate, supports, etc. | Procurement | 14 | 35 | 4
10 | Material Receipt & Incoming Inspection | MTC review, PMI, dimensions, visual inspection, heat-number verification | Stores | 1 | 3 | 7, 8, 9
11 | Material Identification & Traceability | Heat-number transfer, marking, material identification report | Quality Control / QA | 1 | 2 | 10
12 | Cutting / Blanking / Petals | Plate cutting, shell courses, dished-end blanks, nozzle blanks | Fabrication Prep | 2 | 4 | 11
13 | Forming / Rolling / Dishing | Shell rolling, dish-end forming, nozzle forming where applicable | Fabrication Prep | 3 | 7 | 12
14 | Machining | Flange machining, dish-end machining, nozzle/flange machining | Machine Shop | 3 | 7 | 12
15 | Shell Fit-Up | Shell course alignment, longitudinal seam fit-up, dimensional inspection | Fabrication / Welding | 2 | 4 | 13, 14
16 | Shell Welding | Longitudinal/circumferential welding as per approved WPS | Fabrication / Welding | 3 | 7 | 15
17 | Weld NDE | RT/UT/MT/PT as applicable | Quality Control / QA | 2 | 5 | 16
18 | Head/Dish-End Assembly | Fit-up, alignment, welding with shell | Fabrication / Welding | 2 | 4 | 17
19 | Nozzle Fabrication & Fit-Up | Nozzle preparation, orientation, elevation, projection, reinforcement pads | Fabrication / Welding | 3 | 5 | 18
20 | Nozzle Welding | Nozzle-to-shell/head welding and inspection | Fabrication / Welding | 3 | 5 | 19
21 | PWHT / Heat Treatment | If applicable, furnace/local PWHT and chart review | Heat Treatment | 2 | 5 | 20
22 | NDE After Welding/PWHT | RT/UT/MT/PT, hardness testing if applicable | Quality Control / QA | 2 | 5 | 21
23 | Internal & External Attachments | Clips, supports, ladders, platforms, lifting lugs, internals, etc. | Fabrication / Welding | 3 | 7 | 22
24 | Final Assembly | Internal attachments, external attachments, name-plate bracket, support/base ring | Fabrication / Welding | 2 | 5 | 23
25 | Final Dimensional Inspection | Overall dimensions, roundness, nozzle orientation, projection, centerline | Quality Control / QA | 1 | 2 | 24
26 | Final Visual Inspection | Weld visual, surface condition, internal/external inspection | Quality Control / QA | 1 | 1 | 25
27 | Hydrostatic / Pressure Test | Hydrotest, pressure holding, inspection, test report | Quality Control / QA | 1 | 2 | 26
28 | Draining & Drying | Complete draining, drying and preservation | Fabrication / Welding | 1 | 2 | 27
29 | Surface Preparation | Shot blasting / grit blasting, surface profile inspection | Surface Treatment & Painting | 1 | 3 | 28
30 | Painting / Coating | Primer, intermediate, topcoat, DFT inspection | Surface Treatment & Painting | 2 | 5 | 29
31 | Final Inspection | Client/TPI final inspection, punch points and clearance | Quality Control / QA | 1 | 3 | 30
32 | Name Plate & Final Stamping | Name plate verification, stamping, attachment | Quality Control / QA | 1 | 1 | 31
33 | MDR / Final Documentation | Manufacturing Data Record, MTC, NDE reports, hydrotest, PWHT, calibration, drawings, certificates | Documentation / MDR | 3 | 7 | 32
34 | Packing & Preservation | Packing, flange protection, nozzle protection, lifting arrangement, marking | Dispatch & Logistics | 1 | 3 | 32
35 | Dispatch Clearance | Dispatch inspection, documentation clearance, invoice/e-way bill, transport arrangement | Dispatch & Logistics | 1 | 2 | 33, 34
36 | Dispatch | Loading, securing and dispatch to site | Dispatch & Logistics | 1 | 1 | 35

## Material Master
REFERENCE DENSITY MASTER — LIGHT-YELLOW PV MATERIALS USE NOMINAL THEORETICAL DENSITY; MTC/SUPPLIER VALUES GOVERN FINAL WEIGHT.
All materials used in the pilot/source BOMs. Density is in g/cm³; supplier-specific gasket, packing and elastomer compounds are highlighted as nominal planning values.
Example? | Material Specification | Grade / UNS | Product Form | Density (g/cm³) | Remarks
REFERENCE | SA 516 | Gr.70 | Plate | 7.85 | Nominal carbon-steel density for theoretical weight; confirm MTC
REFERENCE | SA 516 | Gr.60 | Plate | 7.85 | Nominal carbon-steel density for theoretical weight; confirm MTC
REFERENCE | SA 106 | Gr.B | Pipe | 7.85 | Nominal carbon-steel density for theoretical weight; confirm MTC
REFERENCE | SA 266 | Gr.2 | Forging | 7.85 | Nominal carbon-steel density for theoretical weight; confirm MTC
REFERENCE | SA 105 |  | Forging | 7.85 | Nominal carbon-steel density for theoretical weight; confirm MTC
REFERENCE | SA 234 | WPB | Fitting | 7.85 | Nominal carbon-steel density for theoretical weight; confirm MTC
REFERENCE | SB 171 | UNS C46400 | Plate / forging | 8.41 | Nominal naval-brass value; verify exact product/MTC
REFERENCE | SB 111 | UNS C44300 | Tube | 8.53 | Nominal admiralty-brass value; verify exact product/MTC
REFERENCE | SB 351 | Alloy 443 | Casting | 8.53 | Grade designation requires engineering confirmation; temporary nominal brass value
REFERENCE | SA 515 | Gr.60 | Plate | 7.85 | Nominal carbon-steel density for theoretical weight; confirm MTC
REFERENCE | SA 179 |  | Tube | 7.85 | Nominal carbon-steel density for theoretical weight; confirm MTC
REFERENCE | IS 2062 | Gr.B | Plate / structural | 7.85 | Nominal carbon-steel density for theoretical weight; confirm certificate
REFERENCE | IS 1239 |  | Pipe | 7.85 | Nominal carbon-steel density for theoretical weight; confirm certificate
REFERENCE | SS 304 |  | Plate / sheet | 7.93 | Typical 304 stainless density; confirm grade certificate
REFERENCE | SS 316 (spiral wound gasket) |  | Winding strip | 7.98 | Metal-strip density only; complete gasket weight must use catalogue/supplier weight
NOMINAL — VERIFY | Aluminium Bronze (W.D) |  | Weld deposit | 7.7 | Nominal planning value; alloy classification and consumable certificate required
REFERENCE | Zinc (anode) |  | Casting / anode | 7.14 | Typical zinc density; use supplier net weight for finished anode
REFERENCE | SA 193 | B7 / B7M | Stud / bar | 7.85 | Nominal alloy-steel density; confirm MTC
REFERENCE | SA 194 | 2H / 2HM | Nut | 7.85 | Nominal alloy-steel density; catalogue weight preferred for finished nuts
NOMINAL — VERIFY | Graphite packing |  | Packing | 1.4 | Bulk/finished density varies by braid and impregnation; supplier datasheet overrides
NOMINAL — VERIFY | BUNA-N |  | Elastomer | 1 | Compound-specific nominal value; supplier datasheet overrides
NOMINAL — VERIFY | Compressed fibre / Permanite gasket |  | Gasket sheet | 1.8 | Product-specific nominal value; supplier datasheet overrides
REFERENCE | SA240 | S32205 | Plate | 7.82 | SP40 basis value; confirm MTC
REFERENCE | SA790 | S32205 | Pipe | 7.82 | SP40 basis value; confirm MTC
REFERENCE | SA182 | Gr.F60 | Forging | 7.82 | Duplex S32205 family nominal value; confirm MTC
REFERENCE | SA193 | Gr.B8M | Stud | 7.98 | 316-family stainless nominal value; confirm MTC
REFERENCE | SA194 | Gr.8M | Nut | 7.98 | 316-family stainless nominal value; catalogue weight preferred
REFERENCE | SS316L |  | Washer | 7.98 | Typical 316L stainless density; catalogue weight preferred
REFERENCE | SB338 | Gr.2 | Tube | 4.51 | Titanium Grade 2 typical density; confirm MTC
NOMINAL — VERIFY | EPDM | Food grade | Gasket / grommet | 1.15 | Compound-specific nominal value; approved supplier datasheet and food-grade certificate required
REFERENCE | PTFE | Food grade | Sheet | 2.2 | Typical unfilled PTFE density; filled grade/supplier datasheet overrides
REFERENCE | Toughened borosilicate |  | View glass | 2.23 | Borosilicate 3.3 reference density; verify purchased glass grade
REFERENCE | SA 333 | Gr.6 | Pipe | 7.85 | PV drawing Rev. C items 207/209; nominal carbon/low-alloy steel density; confirm MTC
REFERENCE | SA 53 | Gr.B | Pipe | 7.85 | PV drawing item 226 alternative; confirm actual MTC grade
REFERENCE | IS 2062 | E250B | Plate / bar | 7.85 | PV skirt/base/gusset/eye-bolt material; confirm certificate
REFERENCE | IS 1367 | Class 4 | Nut | 7.85 | Finished nut catalogue weight preferred
REFERENCE | IS 1367 | Gr.8.8 | Foundation bolt | 7.85 | Finished bolt-set catalogue weight preferred
REFERENCE | Mild steel |  | Rivet | 7.85 | Nominal value for drawing item 230
NOMINAL — VERIFY | Stainless steel | Unspecified | Washer | 7.93 | PV item 223 grade unspecified; confirm supplier/MTC
NOMINAL — VERIFY | Grafoil filler |  | Spiral wound gasket | 1.1 | Bulk density varies by construction; use supplier gasket weight

## Lists (hidden)
Operations | Departments | Equipment | Assembly Groups | Make / Buy | Raw Material Form | Weight Basis | Yes / No | Time Unit | Time Basis | Link Type | Step Kind | Status | Route Source
Receipt | Projects / PMO | PV | Shell | Made in-house | Plate | Plate (L x W x T) | Yes | Hours | Per piece | Finish-to-Start | Work | Draft | Current shop practice
MTC Verification / Material Identification | Design & Detail Engineering | HE | Heads / Dished Ends | Bought-out | Pipe | Rolled shell (ID, T, L) | No | Days | Per job | Start-to-Start (overlap allowed) | Inspection | Reviewed | Client / QAP requirement
Cutting / Blanking | Planning / PPC | PV + HE | Nozzles | Bought + machined in-house | Tube | Pipe / Tube (OD, T, L) |  |  | Per metre of weld |  |  | Approved by Production Head | Code / standard
Edge Preparation / Beveling | Procurement |  | Flanges | Bought + fabricated in-house | Forging | Ring / Flange (OD, ID, T) |  |  | Per joint |  |  |  | Assumed – to be confirmed
Rolling | Stores |  | Channel / Bonnet | Outsourced job work | Bar / Rod | Disc (OD, T) |  |  | Per hole
Forming / Pressing / Dishing | Quality Control / QA |  | Tube Bundle |  | Casting | Bar / Rod (Dia, L) |  |  | Per tube
Machining | Fabrication Prep |  | Floating Head |  | Standard item (catalogue) | Dished head (to be defined) |  |  | Per kg
Fit-up | Machine Shop |  | Internals |  | Assembly (made of other parts) | Catalogue weight (per piece)
Welding | Fabrication / Welding |  | Externals / Supports |  |  | Sum of child parts
Grinding | Heat Treatment |  | Bolting & Gaskets
NDT | Surface Treatment & Painting |  | Test Fixtures
Surface Preparation / Blasting | Documentation / MDR |  | Anodes / Cathodic
Painting / Coating | Dispatch & Logistics |  | Name Plate & Marking
Inspection | Vendor (outside DESPL) |  | Spares
Threading |  |  | Other
Tube Expansion
Assembly Check

## Review Actions
Production Review & Source Corrections | [7 empty] | Correction Calculations
No route, stage, duration, or approval below is treated as confirmed. Close these actions with the Production Head and responsible department before tracker loading.
[8 empty] | Check | Value
ID | Category | Source / Location | Issue or Decision Required | Controlled Action / Proposed Correction | Owner | Status | Evidence / Impact | Shell cover barrel corrected weight (kg) | 19.6769
Q-01 | Routing authority | User instruction / conflicting route documents | Which source governs PV and HE routes? Flange, dished-end and tubesheet routes conflict. | Production Head to nominate controlling document and approve each pilot route. | Production Head | Open | SP40 package is Rev.0 marked Submission and supplies component requirements, but does not designate itself as the controlling shop-routing document. | Original stated weight (kg) | 170.3398
Q-02 | HE scope | Master BOM _PV_HE.xlsx | Which HE types are actually manufactured: fixed tubesheet, U-tube, floating head, Twin Oil Cooler or others? | Approve the HE type list before HE Stages are created. | Production Head / Engineering | Open | SP40 drawing package confirms MED Train 1 with three effects and six tubesheets; it does not define the organization's complete HE type list. | Overstatement (kg) | 150.6628
Q-03 | Tube joint | HE component master | Expansion only or expansion plus seal welding? Which mock-up, pull-out and leak tests apply? | Approve joint variants and acceptance records. | Production Head / QC | Open | SP40-02-02-11-04 Rev.0 resolves this project as Ø21.3 tubes tight-fit with food-grade EPDM grommets; it specifies neither expansion nor seal welding nor joint testing. Other HE designs remain unresolved. | Potential duplicated assembly weight (kg) | 102.64
Q-04 | Aluminium bronze | HE 803-E-5 | Are AL.BR.W.D lines overlay/cladding or separate parts? | Confirm BOM representation and weight treatment. | Engineering / Production Head | Open | Duplicate-looking CS and AL bronze lines occur for flanges and partition plates.
Q-05 | PWHT scope | PV/HE route masters | Is PWHT done on individual parts, the complete equipment, or both? | Define route condition and equipment stage mapping. | Production Head / QC | Open | Heat treatment is not in the fixed operation list.
Q-06 | Live jobs | HE 803-E-5 and OC-48-0223 | Are these live jobs for tracker entry or historical source BOMs only? | Confirm job status before importing job-specific quantities. | Projects / PMO | Open | Used here only as evidence for standard part families.
Q-07 | PV reference | Master BOM _PV.xlsx | Should this BOM or DESPL-320 be the governing PV reference? | Name one controlled PV baseline. | Production Head / Engineering | Open | Current assembly sheet cites DESPL-320; attached PV BOM contains a different extract.
Q-08 | TOC source | TOC Practice and Tube sheet Bundle - TOC | Which overlapping Twin Oil Cooler sheet is authoritative? | Retain one controlled BOM and archive/identify the derivative extract. | Production Head / Engineering | Open | The bundle sheet is a subset; some calculated weights differ.
C-01 | Weight formula | HE 803-E-5 P.No 2 | Shell Cover Barrel is calculated as a solid cylinder: 170.34 kg. | Use hollow-cylinder formula; at ID 356, t 10, L 218 and 7.85 g/cm³, calculated weight is about 19.86 kg. | Engineering | Open | Overstatement about 150.48 kg.
C-02 | Double count | HE 803-E-5 P.No 42–44 and 201–243 | Saddle and davit assemblies have lump weights and child parts are listed again. | Set parent assemblies to Sum of child parts and count weight once. | Engineering | Open | 38.01 + 30.79 + 33.84 = 102.64 kg potential duplicate.
C-03 | Item numbering | HE 803-E-5 | Item numbers 8, 32, 33, 117 and 125 repeat; 14A is non-numeric. | Renumber every BOM line uniquely and update drawing references. | Engineering | Open | Duplicate keys will break tracker import.
C-04 | Thickness conflict | HE 803-E-5 P.No 32–33 and 125 | Description says 10 THK while thickness field says 5 or 6. | Confirm drawing thickness and correct both description and numeric field. | Engineering / QC | Open | Weight and procurement quantity depend on thickness.
C-05 | Length error | HE 803-E-5 P.No 40; TOC item 1055 | Length entered as 10 and 30 instead of 100 and 300. | Correct numeric length after drawing check and recalculate weight. | Engineering | Open | Current calculated weights are understated.
C-06 | Nozzle tags | HE 803-E-5 P.No 29–30 | Gaskets are tagged V1,D2 and V2,D2; D2 repeats and D1 is missing. | Correct first tag set to V1,D1 if drawing confirms. | Engineering | Open | Mismatch with corresponding flange and bolting tags.
C-07 | Spare gasket sizes | Mandatory Spares versus main BOM | Spare gasket dimensions do not match mating main-BOM flanges. | Reconcile each spare gasket OD/ID/class against the approved flange drawing. | Engineering / Procurement | Open | Example: shell-cover spare 246/226 versus flange 498/356.
C-08 | Missing checklist | Attachment set | The referenced 24-point correction checklist was not attached separately. | Provide the checklist so all 24 points can be logged and closed. | Document Control | Open | Only the points written in the instruction were available.
A-01 | HE stages | HE Stages sheet | SP40 confirms a MED Train 1 equipment configuration but provides no whole-equipment stage schedule, durations, or predecessors. | Hold HE Stages blank until a workshop confirms type-specific stages, durations and dependencies. | Production Head / PPC | Open | HE Stages remains blank to avoid inventing planning gates. Drawing-backed component operations are recorded in Part Routes and Assembly Sequence only.
A-02 | Standard times | Part Routes sheet | No approved shop standard times or bases were supplied. | Supervisors to provide time, unit and basis for each route step. | Department Supervisors / PPC | Open | All standard-time cells intentionally blank.
A-03 | Approval names | Parts Master / Read Me | Prepared-by and checked-by real names were not supplied. | Enter actual preparer and Production Head reviewer names during sign-off. | Document Control | Open | All pilot parts remain Draft.
D-01 | Drawing release | SP40 drawing package Rev.0 | Is Rev.0 marked 'Submission' released for manufacture and tracker use? | Document Control/Production Head to confirm controlled release status. | Document Control / Production Head | Open | Engineering title blocks show DRWN MMS, CHKD KJR, APPD AJM; this is not Production Head sign-off.
D-02 | Tube joint scope | SP40-02-02-11-04 Rev.0 | Does the tight-fit EPDM grommet joint apply only to SP40 MED units or become a standard HE route variant? | Approve a distinct grommet-joint route; do not map it to Tube Expansion. | Production Head / Engineering / QC | Open | Drawing explicitly says tubes should be tight fit with grommets; no expansion/seal welding/test stated.
D-03 | Grommet certificate | SP40-02-02-11-05/-07 Rev.0 | What approved EPDM compound, Shore hardness, density and supplier certificate apply? | Enter vendor-certified properties before weight or procurement automation. | Engineering / Procurement / QC | Open | Drawing requires food-grade certificate and Shore hardness but gives no value.
D-04 | Material specification | SP40-02-03-04-003 Sheet 02 Rev.0 | Confirm whether printed SA720 S32205 is correct or should be SA240 S32205. | Correct the controlled drawing/BOM only after Engineering confirmation. | Engineering / Document Control | Open | Internal-grating material list includes SA720 S32205 while surrounding duplex plate items use SA240 S32205.
D-05 | Stage and time mapping | SP40 drawing-derived routes | Which departments, HE stage numbers and standard times apply to the 13 drawing-required steps? | Production Head and supervisors to fill department, stage, time, unit and basis. | Production Head / Supervisors / PPC | Open | Drawing states technical requirements but not DESPL ownership, stage mapping or shop duration.
D-06 | Missing governing documents | SP40 reference drawing lists | Provide approved GA, notes, QAP/ITP, weld details, internal-door, handhole and material-list revisions used for manufacture. | Register supplied revisions and use them to complete route acceptance criteria and assembly sequence. | Document Control / Engineering / QC | Open | The package references additional controlled documents; a fabrication drawing alone cannot establish the full route.
D-07 | Complete MED stage plan | HE Stages | Approve PO-to-dispatch stage structure for MED Train 1 and provide min/max durations and predecessors. | Run PPC/Production workshop; then populate HE Stages and map every HE route/assembly row. | Production Head / PPC | Open | No schedule or duration data appears in the drawing package.
PV-01 | Source drawing | PV Drawing Basis / items 205A, 210, 223, 238, 239, 244 | Confirm tight/unclear BOM cells: R-pad final dimension, stiffener weight, washer OD, lug/support-plate weight basis and N6 coupling details. | Engineering to verify against native CAD or vendor-controlled BOM. | Engineering | Open | No uncertain cell has been promoted as approved master data.
PV-02 | Standard times | Part Routes rows 85:239 | Drawing contains no shop cycle times; proposed norms require actual time-study validation. | Department heads to validate time/unit/basis for all 155 PV route steps. | Production Head / PPC | Open | All entries remain Draft and visibly highlighted.
PV-03 | Heat treatment | Drawing design data / Assembly Sequence | Approve separate PFHT and PWHT operations, cycles, furnace/local method and hardness requirements. | Issue approved heat-treatment procedure and tracker operation mapping. | Production Head / QC | Open | Drawing states PFHT=Yes and PWHT=Yes.
PV-04 | NDE | Drawing notes / Design Data | Confirm 100% RT coverage, 100% PT of all welds and post-PWHT NDE/hardness scope. | QAP/ITP to define method, timing, acceptance and records. | Quality Control / QA | Open | ASME VIII-1 Edition 2023; joint efficiency 1.0.
PV-05 | Weld map | Assembly Sequence PV rows | Replace proposed LS/CS/NS/SK/AW references with the controlled job weld map. | Welding/QC to approve joint numbering before tracker load. | Production Head / QC | Open | Current references are structured placeholders based on drawing features.
PV-06 | Bolting | M1 manhole closure | Approve tightening method, lubricant, sequence and torque/tension record for Class 300 closure. | Issue controlled bolting procedure. | Production Head / QC | Open | 24 stud-and-nut sets and spiral-wound gasket are drawing-backed.
PV-07 | Material controls | Items 207, 209, 223, 226, 232 | Confirm Rev. C SA333 Gr.6 pipe, unspecified SS washer grade, support-pipe grade and IS2062 boss grade from MTC/BOM. | Procurement/QC to reconcile MTCs to drawing BOM. | Procurement / QC | Open | Material Master uses nominal densities pending certificates.
PV-08 | Approval | Parts Master PV rows 35:64 | No newly added PV family has Production Head approval. | Review routes, assembly, times and operation proposals; change status only after signed approval. | Production Head | Open | Tracker load readiness remains HOLD.

## Pilot Review
STANDARD PARTS MASTER — PILOT REVIEW | [8 empty] | 30-MINUTE REVIEW AGENDA
PROPOSED REVIEW BASELINE — 10 pilot parts, 73 routes and 42 HE stages are filled; no time, stage, route or part is approved until signed by the Production Head/PPC.
[9 empty] | TIME | TOPIC | REQUIRED OUTPUT
CONTROL STATUS | LIVE VALUE | [7 empty] | 0–5 min | Controlling sources | Approve governing PV/HE routing documents
Pilot parts | 10 | [7 empty] | 5–10 min | HE scope | Approve exchanger types and stage framework
Route steps | 73 | [7 empty] | 10–18 min | Pilot routes | Confirm steps, departments, conditions and stage mapping
HE stages entered | 42 | [7 empty] | 18–23 min | Standard times | Assign supervisors and time-study basis
Missing stage mappings | 0 | [7 empty] | 23–27 min | BOM corrections | Approve correction owner and drawing checks
Route steps missing standard time | 0 | [7 empty] | 27–30 min | Sign-off | Record owners, due dates and approval status
Open review actions | 26
Approved pilot parts | 0
Tracker load readiness | HOLD – Production Head approval pending | [7 empty] | SIGN-OFF ROLE | NAME | DATE
Prepared by
PART CODE | PART NAME | EQUIPMENT | STEPS | MISSING STAGE | MISSING TIME | ROUTE SOURCE | STATUS | REVIEW RESULT | Production Head
SHL-01 | Shell Course | PV + HE | 9 | 0 | 0 | Assumed – to be confirmed | Draft | HOLD — APPROVAL | Production Supervisor
HED-01 | Dished End | PV + HE | 16 | 0 | 0 | Assumed – to be confirmed | Draft | HOLD — APPROVAL | PPC / Planning
NOZ-01 | Nozzle Neck | PV + HE | 9 | 0 | 0 | Assumed – to be confirmed | Draft | HOLD — APPROVAL
FLG-01 | Nozzle Flange | PV + HE | 5 | 0 | 0 | Assumed – to be confirmed | Draft | HOLD — APPROVAL | Do not change HOLD to READY until every route has stage mapping and standard time, HE stages are approved, all actions are closed, and the Production Head has approved all 10 parts.
TSH-01 | Tube Sheet | HE | 7 | 0 | 0 | Assumed – to be confirmed | Draft | HOLD — APPROVAL
TUB-01 | Tube | HE | 5 | 0 | 0 | Assumed – to be confirmed | Draft | HOLD — APPROVAL
BAF-01 | Baffle | HE | 6 | 0 | 0 | Assumed – to be confirmed | Draft | HOLD — APPROVAL
SAD-01 | Saddle | PV + HE | 10 | 0 | 0 | Assumed – to be confirmed | Draft | HOLD — APPROVAL
STD-01 | Stud with Two Nuts | PV + HE | 3 | 0 | 0 | Assumed – to be confirmed | Draft | HOLD — APPROVAL
GAS-01 | Gasket | PV + HE | 3 | 0 | 0 | Assumed – to be confirmed | Draft | HOLD — APPROVAL
ID | CATEGORY | DECISION REQUIRED | OWNER | STATUS | CONTROLLED ACTION
Q-01 | Routing authority | Which source governs PV and HE routes? Flange, dished-end and tubesheet routes conflict. | Production Head | Open | Production Head to nominate controlling document and approve each pilot route.
Q-02 | HE scope | Which HE types are actually manufactured: fixed tubesheet, U-tube, floating head, Twin Oil Cooler or others? | Production Head / Engineering | Open | Approve the HE type list before HE Stages are created.
Q-03 | Tube joint | Expansion only or expansion plus seal welding? Which mock-up, pull-out and leak tests apply? | Production Head / QC | Open | Approve joint variants and acceptance records.
Q-04 | Aluminium bronze | Are AL.BR.W.D lines overlay/cladding or separate parts? | Engineering / Production Head | Open | Confirm BOM representation and weight treatment.
Q-05 | PWHT scope | Is PWHT done on individual parts, the complete equipment, or both? | Production Head / QC | Open | Define route condition and equipment stage mapping.
Q-06 | Live jobs | Are these live jobs for tracker entry or historical source BOMs only? | Projects / PMO | Open | Confirm job status before importing job-specific quantities.
Q-07 | PV reference | Should this BOM or DESPL-320 be the governing PV reference? | Production Head / Engineering | Open | Name one controlled PV baseline.
Q-08 | TOC source | Which overlapping Twin Oil Cooler sheet is authoritative? | Production Head / Engineering | Open | Retain one controlled BOM and archive/identify the derivative extract.
C-01 | Weight formula | Shell Cover Barrel is calculated as a solid cylinder: 170.34 kg. | Engineering | Open | Use hollow-cylinder formula; at ID 356, t 10, L 218 and 7.85 g/cm³, calculated weight is about 19.86 kg.
C-02 | Double count | Saddle and davit assemblies have lump weights and child parts are listed again. | Engineering | Open | Set parent assemblies to Sum of child parts and count weight once.
C-03 | Item numbering | Item numbers 8, 32, 33, 117 and 125 repeat; 14A is non-numeric. | Engineering | Open | Renumber every BOM line uniquely and update drawing references.
C-04 | Thickness conflict | Description says 10 THK while thickness field says 5 or 6. | Engineering / QC | Open | Confirm drawing thickness and correct both description and numeric field.
C-05 | Length error | Length entered as 10 and 30 instead of 100 and 300. | Engineering | Open | Correct numeric length after drawing check and recalculate weight.
C-06 | Nozzle tags | Gaskets are tagged V1,D2 and V2,D2; D2 repeats and D1 is missing. | Engineering | Open | Correct first tag set to V1,D1 if drawing confirms.
C-07 | Spare gasket sizes | Spare gasket dimensions do not match mating main-BOM flanges. | Engineering / Procurement | Open | Reconcile each spare gasket OD/ID/class against the approved flange drawing.
C-08 | Missing checklist | The referenced 24-point correction checklist was not attached separately. | Document Control | Open | Provide the checklist so all 24 points can be logged and closed.
A-01 | HE stages | SP40 confirms a MED Train 1 equipment configuration but provides no whole-equipment stage schedule, durations, or predecessors. | Production Head / PPC | Open | Hold HE Stages blank until a workshop confirms type-specific stages, durations and dependencies.
A-02 | Standard times | No approved shop standard times or bases were supplied. | Department Supervisors / PPC | Open | Supervisors to provide time, unit and basis for each route step.
A-03 | Approval names | Prepared-by and checked-by real names were not supplied. | Document Control | Open | Enter actual preparer and Production Head reviewer names during sign-off.

## SP40 Drawing Basis
SP40 MED TRAIN 1 — DRAWING BASIS & TRACEABILITY
Source: SP40-02-03-04-001-R0 package (25 PDF pages). Drawing-backed facts are recorded below; shop routes, stages, durations and Production Head approval are not inferred.
EQUIPMENT BASIS | VALUE
Project | SP40 – Solar Thermal Desalination Plant
Equipment | MED Train 1 vessel / evaporator
Configuration evidenced | Three effects; six Ø3000 fabricated tubesheets; titanium tubes with EPDM grommets
Drawing status | Revision 0 – Submission
Construction code | ASME Section VIII Division 1 – 2025
Design pressure | 0.01 bar(a) internal
Hydro test pressure | 1 bar(g)
Design temperature | 100 °C
Tracker status | HOLD — Production Head/PPC review required
Drawing requirement; proposed stage/time entered – approval pending
REQ ID | COMPONENT | DRAWING / SHEET | SOURCE PAGE | CONFIRMED REQUIREMENT | FIXED OPERATION | WORKBOOK LOCATION | Drawing requirement; proposed stage/time entered – approval pending
R-01 | Dished Head | SP40-02-03-04-001 / 01–02 | 1–2 | 2:1 semi-ellipsoidal; ID 3000; raw 12; formed 10 min; ICR 2700; IKR 510; SF 50; blank Ø3772 | Forming / Pressing / Dishing | Part Routes HED-01 Variant B | Drawing requirement; proposed stage/time entered – approval pending
R-02 | Dished Head | SP40-02-03-04-001 / 01–02 | 1–2 | Cold forming required | Forming / Pressing / Dishing | Part Routes HED-01 Variant B | Drawing requirement; proposed stage/time entered – approval pending
R-03 | Dished Head | SP40-02-03-04-001 / 01–02 | 1–2 | Full dye penetrant test inside and outside in presence of TPI | NDT | Part Routes HED-01 Variant B | Drawing requirement; proposed stage/time entered – approval pending
R-04 | Dished Head | SP40-02-03-04-001 / 01–02 | 1–2 | Template profile check and UG-81 tolerances | Inspection | Part Routes HED-01 Variant B | Drawing requirement; proposed stage/time entered – approval pending
R-05 | Tubesheet | SP40-02-03-04-002 / 01–06 | 14–19 | SA240 S32205 plate, OD 3000 × 10; six effect-specific layouts | — | Parts Master TSH-02 | Drawing requirement; proposed stage/time entered – approval pending
R-06 | Tubesheet | SP40-02-03-04-002 / 01–06 | 14–19 | Plate-to-plate weld 100% RT and accepted before drilling | NDT | Part Routes TSH-02 | Drawing requirement; proposed stage/time entered – approval pending
R-07 | Tubesheet | SP40-02-03-04-002 / 01–06 | 14–19 | Tube holes Ø24.7; pitch 28.78; finish 1.6 microns; deburr; 0.5 × 45° chamfer both sides | Machining | Part Routes TSH-02 | No expansion/seal weld stated; assembly stage mapped, joint method remains open
R-08 | Tubesheet | SP40-02-03-04-002 / 01–06 | 14–19 | Maintain flatness, circularity and freedom from distortion through fabrication/welding/machining | Inspection | Part Routes TSH-02 | Part definition confirmed; proposed route mapping/time requires approval
R-09 | Tube joint | SP40-02-02-11-04 | 23 | Ø21.3 tube through 10 mm tubesheets; tight fit with grommets | Installation (proposed) | Assembly Sequence | Compound data and supplier certification pending
R-10 | Tube | SP40-02-03-05 + SP40-02-02-11-04 | 3, 23 | SB338 Gr.2 titanium, OD 21.3 × 0.4; 3000 overall for Effects 1–8; 2260 for Effect 9 | — | Parts Master TUB-01 | Retention method approval pending; proposed assembly stage entered
R-11 | Grommet | SP40-02-02-11-05/-07 | 21–22 | EPDM food grade; submit certificate and Shore hardness | Inspection | Parts Master GRM-01/BGM-01 | Part definition confirmed; proposed route mapping/time requires approval
R-12 | Saddle | SP40-02-02-11-01 | 20 | PTFE food-grade sliding sheet 10 × 450 × 3030 | Installation (proposed) | Assembly Sequence | Retention method/stage pending
R-13 | Shell | SP40-02-03-05 | 3 | Ten SA240 S32205 shell plates, PL.10 × 9456 developed length | — | Parts Master SHL-01 | Part definition confirmed
PDF PAGE | DRAWING NUMBER | SHEET | REV. | DRAWING TITLE |  | OPEN CONTROL | WHY IT REMAINS OPEN
1 | SP40-02-03-04-001 | 01 OF 02 | 0 | MED Train 1 – Left Side Dished Head Detail |  | HE stage schedule | No min/max durations or predecessors in drawing
2 | SP40-02-03-04-001 | 02 OF 02 | 0 | MED Train 1 – Right Side Dished Head Detail |  | Department ownership | Drawing does not assign DESPL departments
3 | SP40-02-03-05 | 01 OF 01 | 0 | MED Train 1 – Overall Material List |  | Standard times | No shop time study in drawing
4 | SP40-02-03-04-008 | 01 OF 01 | 0 | MED Train 1 – External Attachment Details |  | Production approval | Title-block approval is not identified as Production Head approval
5 | SP40-02-03-04-007 | 01 OF 01 | 0 | MED Train 1 – NCG Nozzles and J Tubes Detail |  | Tube joint tests | No mock-up, pull-out or leak test specified
6 | SP40-02-03-04-006 | 01 OF 03 | 0 | MED Train 1 – Effect 1.1 NCG Box Details |  | EPDM properties | Compound density and Shore hardness absent
7 | SP40-02-03-04-006 | 02 OF 03 | 0 | MED Train 1 – Effect 2.1 NCG Box Details |  | Full assembly sequence | GA/QAP/notes and shop method confirmation required
8 | SP40-02-03-04-006 | 03 OF 03 | 0 | MED Train 1 – Effect 3.1 NCG Box Details
9 | SP40-02-03-04-004 | 01 OF 03 | 0 | MED Train 1 – Effect 1 Demister Details
10 | SP40-02-03-04-004 | 02 OF 03 | 0 | MED Train 1 – Effect 2 Demister Details
11 | SP40-02-03-04-004 | 03 OF 03 | 0 | MED Train 1 – Effect 3 Demister Details
12 | SP40-02-03-04-003 | 01 OF 02 | 0 | MED Train 1 – Internal Attachment Detail
13 | SP40-02-03-04-003 | 02 OF 02 | 0 | MED Train 1 – Internal Grating Detail
14 | SP40-02-03-04-002 | 01 OF 06 | 0 | MED Train 1 – Effect 1.1 Tube Sheet Detail
15 | SP40-02-03-04-002 | 02 OF 06 | 0 | MED Train 1 – Effect 1.2 Tube Sheet Detail
16 | SP40-02-03-04-002 | 03 OF 06 | 0 | MED Train 1 – Effect 2.1 Tube Sheet Detail
17 | SP40-02-03-04-002 | 04 OF 06 | 0 | MED Train 1 – Effect 2.2 Tube Sheet Detail
18 | SP40-02-03-04-002 | 05 OF 06 | 0 | MED Train 1 – Effect 3.1 Tube Sheet Detail
19 | SP40-02-03-04-002 | 06 OF 06 | 0 | MED Train 1 – Effect 3.2 Tube Sheet Detail
20 | SP40-02-02-11-01 | 01 OF 01 | 0 | MED Trains 1–3 – Saddle Details
21 | SP40-02-02-11-07 | 01 OF 01 | 0 | MED Trains 1–3 – Baffle Grommet Detail
22 | SP40-02-02-11-05 | 01 OF 01 | 0 | MED Trains 1–3 – Grommet Detail
23 | SP40-02-02-11-04 | 01 OF 01 | 0 | MED Trains 1–3 – Tube to Tube Sheet Fixing Detail
24 | SP40-02-02-11-03 | 01 OF 01 | 0 | MED Trains 1–3 – View Glass Detail
25 | SP40-02-02-11-02 | 01 OF 01 | 0 | MED Trains 1–3 – Manhole Detail

## PV Drawing Basis
PV DRAWING BASIS — HP AIR RECEIVER BLOW DOWN SYSTEM
Approved GA drawing source. Light-yellow rows are drawing-backed; orange cells are uncertain or require shop/Production Head confirmation.
Field | Value
Drawing No. | 51G2-E-ELM-HCA-DM-D-V-4006
Revision / Sheet | C / Sheets 1 and 2 of 2
Drawing title | General Arrangement Drawing – HP Air Receiver Blow Down System
Project | Chitravathi Pumped Storage Project (500 MW)
PO / Job | 4504443598 / DE0423
Quantity / Serial Nos. | 03 Nos. / DE0423-01 to DE0423-03
Approval | APPROVED – May 23, 2025
Manufacturer | Dhruv EPC Solutions Pvt. Ltd.
Design code | ASME Section VIII Division 1, Edition 2023
Configuration | Vertical pressure vessel; 2345 mm ID × 5496 mm overall length; capacity 20 m³
Design pressure / temperature | 44 bar(g) / -20 to +50 °C
Corrosion allowance / RT | 1.5 mm / 100% all butt welds
Hydrotest | 66–66.5 kg/cm²(g) at top, horizontal; 18–48 °C; 30 min hold
Heat treatment | Post-forming heat treatment: Yes; PWHT: Yes
Cyclic service | 150,000 cycles; 8 cycles/day; pressure fluctuations 40–70 bar
Weights | Empty 19,266 kg; Operating 20,265 kg; Hydrotest 39,261 kg
NOZZLE SCHEDULE | Qty | Size | Pipe Sch / Thk | Flange / Type / Face | Service | Projection / Pad | Remarks
N1 | 1 | DN25 / 1 in | 14.22 mm | Class 300 LWN RF | Inlet | 1430; R-pad 25 × 75 | Drawing schedule
N2 | 1 | DN25 / 1 in | XXS / 9.09 mm | Class 300 LWN RF | Drain | See drawing | Drawing schedule
N3 | 1 | DN125 / 5 in | Sch 160 / 15.88 mm | Class 300 WN RF | Outlet | 1475 | SRN
N4 | 1 | 1/2 in | — | 6000# BSP F | Pressure gauge | See drawing | Refer detail
N5 | 1 | 1/2 in | — | 6000# BSP F | Pressure transmitter | See drawing | Refer detail
N6 | 1 | 1/2 in | — | 6000# BSP F | Safety valve | See drawing | Refer detail
M1 | 1 | DN450 / 18 in | Sch 60 / 19.05 mm | Class 300 WN RF | Manhole | 1615 | SRN with blind flange
ITEM | DESCRIPTION | QTY | MATERIAL / SPEC | SIZE / DIMENSIONS | WT (kg) | MASTER CODE | SOURCE / CONTROL
101 | Shell | 1 | SA 516 Gr.70 | 45T × 3750W × 7509 developed length | 9947 | SHL-01 | Sheet 1 BOM; confirmed
102 | Top & Bottom Dished End | 2 | SA 516 Gr.70 | 45T nominal × 2925 blank diameter | 4748 | HED-01 | Sheet 1 BOM; confirmed
201 | Skirt Shell | 1 | SA 516 Gr.70 | 16T × 837W × 7499 developed length | 789 | SKT-01 | Sheet 2 BOM; confirmed
202 | Skirt Base Ring | 1 | IS 2062 E250B | 32T × 2240 ID × 2700 OD | 448 | SBR-01 | Sheet 2 BOM; confirmed
203 | Gusset Plate | 32 | IS 2062 E250B | 12T × 150W × 151 length | 69 | GSP-02 | Sheet 2 BOM; confirmed
204 | Earthing Plate | 2 | SS 304 | 12T × 75W × 75 length | 1 | ERT-01 | Sheet 2 BOM; confirmed
205 | Flange N1 | 1 | SA 105 | 1 in ID × 14.22T × Class 300 WNRF × 285 length | 5.2 | FLG-01 | Sheet 2 BOM; confirmed
205A | Reinforcement Pad N1 | 1 | SA 516 Gr.70 | 25T × 204 OD × 57 ID × final dimension unclear | 5.9 | RFP-02 | Sheet 2 BOM; one dimension requires drawing check
206 | Flange N2 | 1 | SA 105 | DN25 × Sch XXS × Class 300 WNRF | 2 | FLG-01 | Sheet 2 BOM; confirmed
207 | Nozzle Pipe N2 | 1 | SA 333 Gr.6 | DN25 × Sch XXS × 1350 length | 7.4 | NOZ-01 | Rev. C changes MOC; confirmed
208 | Nozzle Elbow N2 | 1 | SA 234 WPB | DN25 × Sch XXS × 90° LR | 0.4 | ELB-01 | Sheet 2 BOM; confirmed
209 | Nozzle Pipe N2 | 1 | SA 333 Gr.6 | DN25 × Sch XXS × 130 length | 0.8 | NOZ-01 | Rev. C changes MOC; confirmed
210 | Stiffener N2 | 1 | SA 516 Gr.70 | 6T × 50W × 290 length |  | STF-01 | Weight cell unclear; drawing check required
211 | Support Pipe N2 | 1 | SA 106 Gr.B | DN150 × Sch 120 × 115 length | 6.3 | SPP-01 | Sheet 2 BOM; confirmed
212 | Stiffener N3 | 3 | SA 516 Gr.70 | 6T × 51W × 80 length | 0.6 | STF-01 | Sheet 2 BOM; confirmed
213 | Flange N3 | 1 | SA 105 | DN125 × Sch 160 × Class 300 WNRF | 19 | FLG-01 | Sheet 2 BOM; confirmed
214 | Self-Reinforced Nozzle N3 | 1 | SA 266 Gr.2 | As per detail | 29 | SRN-01 | Sheet 2 BOM; confirmed
215 | Coupling with Plug N4 & N5 | 2 | SA 105 | DN15 × 6000# BSP; as per detail | 1.5 | CPL-01 | Sheet 2 BOM; confirmed
216 | Flange M1 | 1 | SA 105 | DN450 × Sch 60 × Class 300 WNRF | 192 | FLG-01 | Sheet 2 BOM; confirmed
217 | Self-Reinforced Nozzle M1 | 1 | SA 266 Gr.2 | As per detail | 288 | SRN-01 | Sheet 2 BOM; confirmed
218 | Blind Flange M1 | 1 | SA 105 | DN450 × ASME Class 300 blind RF | 181 | BFL-01 | Sheet 2 BOM; confirmed
219 | Gasket M1 | 1 | SS316L spiral wound / Grafoil / CS outer ring | DN450 × ASME Class 300; ASME B16.20 |  | GAS-01 | Note 1; catalogue/supplier weight
220 | Stud with Two Heavy Hex Nuts | 24 | SA193 B7 / SA194 2H | 1-1/4 in UNC × 210 length; full thread | 44 | STD-01 | Sheet 2 BOM; confirmed
221 | Square Bar for Hook | 1 | SA 516 Gr.70 | Square 28 × 400 developed length | 2.5 | HOK-01 | Sheet 2 BOM; confirmed
222 | Eye Bolt | 1 | IS 2062 E250B | Dia 25 × 500 developed length | 2 | EYE-01 | Sheet 2 BOM; confirmed
223 | Washer | 1 | Stainless steel | 1.5T × OD unclear × 26 ID | 0.03 | WSH-02 | OD requires drawing check
224 | Hex Nut | 1 | IS 1367 Class 4 | M24 standard |  | NUT-02 | Catalogue weight
225 | Hex Lock Nut | 1 | IS 1367 Class 4 | M24 standard |  | NUT-02 | Catalogue weight
226 | Support Pipe | 1 | SA 53 Gr.B / SA106 Gr.B | DN65 × Sch 40 × 200 length | 1.8 | SPP-01 | Exact material line requires certificate check
227 | Davit Pipe | 1 | SA 106 Gr.B | DN50 × Sch 80 × approx. 1000 developed length | 7.5 | DVT-01 | Sheet 2 BOM; confirmed
228 | End Plate for Davit Pipe | 1 | SA 516 Gr.70 | 10T × 50 OD | 0.2 | EPL-01 | Sheet 2 BOM; confirmed
229 | End Plate for Support Pipe | 1 | SA 516 Gr.70 | 10T × 60 OD | 0.3 | EPL-01 | Sheet 2 BOM; confirmed
230 | Snap Head Rivet | 1 | Mild steel | Dia 20 × 25 length; refer detail |  | RVT-01 | Supplier/catalogue weight
231 | Rib Plate | 1 | SA 516 Gr.70 | 10T × 50W × 240 length | 0.9 | RIB-01 | Sheet 2 BOM; confirmed
232 | Boss for Davit Pipe | 1 | IS 2062 | Dia 80 × 80 length | 3.2 | BOS-01 | Grade to be confirmed from MTC
233 | Handle | 2 | SA 516 Gr.70 | Square 20 × 310 developed length | 2 | HDL-01 | Sheet 2 BOM; confirmed
234 | Jack Screw | 3 | SS 304 | M16 × 120 length; refer detail | 0.8 | JSC-01 | Sheet 2 BOM; confirmed
235A | Access Opening Ring | 1 | SA 516 Gr.70 | 16T × 150W × 1075 developed length | 21 | AOP-01 | Same drawing item 235; component line
235B | Access Opening Cover/Plate | 1 | SA 516 Gr.70 | 16T × 150W × 428 length | 8 | AOP-01 | Same drawing item 235; component line
236 | Nozzle Pipe SV1 to SV4 | 4 | SA 106 Gr.B | DN100 × Sch 80 × 115 length | 10.2 | NOZ-01 | Sheet 2 BOM; confirmed
237 | Pad Plate | 2 | SA 516 Gr.70 | 16T × 200W × 330 developed length | 17 | PAD-01 | Sheet 2 BOM; confirmed
238 | Lifting Lug | 2 | SA 516 Gr.70 | 32T × 230W × 680 length | 79 | LUG-02 | Weight basis (total/per item) requires check
239 | Support Plate | 2 | SA 516 Gr.70 | 28T × 500W × 230 length | 5 | SPL-01 | Weight basis requires check
240 | Tailing Lug | 1 | SA 516 Gr.70 | 32T × 250W × 275 length | 17.8 | TLG-01 | Sheet 2 BOM; confirmed
241 | Name Plate Bracket | 1 | SA 516 Gr.70 | 6T × 160 × 350 length | 2.63 | NPB-01 | Sheet 2 BOM; confirmed
242 | Name Plate | 1 | SS 304 | 3T × 150 × 200 length | 0.75 | NPL-01 | Sheet 2 BOM; confirmed
243 | Foundation Bolt with Nut & Washer | 16 | IS 1367 Gr.8.8 | M36 × 580 length | 40 | FBL-01 | Sheet 2 BOM; confirmed
244 | Coupling with Plug N6 | 1 | SA 105 | DN15 × 6000# BSP; as per detail | 1 | CPL-01 | Size/value visually tight; verify before release

## PV Review
PRESSURE VESSEL MASTER — DRAWING REVIEW
Approved GA source is captured, but all shop-time norms, route approvals and unresolved BOM cells remain under controlled HOLD.
CONTROL STATUS | LIVE VALUE
Drawing BOM lines | 48
New PV part families | 30
Drawing-linked shared families | 6
New PV route steps | 155
PV assembly steps | 31
Missing PV stage mappings | 0
PV routes missing standard time | 0
Open PV review actions | 8
Approved new PV families | 0
Tracker load readiness | HOLD – Production Head approval pending
DRAWING FACT | VALUE | UNIT / BASIS | SOURCE
Drawing | 51G2-E-ELM-HCA-DM-D-V-4006 Rev. C | Sheets 1–2 | Approved GA
Vessel size | 2345 ID × 5496 OAL | mm | Design Data
Capacity | 20 | m³ | Design Data
Design pressure | 44 | bar(g) | Design Data
Design temperature | -20 to +50 | °C | Design Data
Hydrotest pressure | 66–66.5 | kg/cm²(g) | 30 min at 18–48°C
Empty weight | 19266 | kg | Design Data
Operating weight | 20265 | kg | Design Data
Hydrotest weight | 39261 | kg | Design Data
Cyclic service | 150000 | cycles | 8 cycles/day; pressure fluctuations 40–70 bar
REVIEW GATE | OWNER | STATUS | REQUIRED EVIDENCE
BOM ambiguities | Engineering | Open | Native CAD/vendor BOM confirmation
Routes and times | Production Head / PPC | Open | Approved routes and time-study sheet
PFHT / PWHT / NDE | QC / Heat Treatment | Open | Approved procedures, QAP and acceptance criteria
Weld map | Welding / QC | Open | Controlled joint-number register
Final approval | Production Head | Open | Signed approval and Parts Master status update